## PRISM SCORE CARD
Form Version : | 2.04 | Fields highlighted are essential and should be completed before submission of this form. The number of incomplete fields is : 27 | [21 empty] | Supplier Name: | Supplier Oracle Number: | Parent Company: | Supplier if not avaliable | OProject number (6 Digits): | Project Title: | Contract Title: | PO Number/Contract Reference: | Primary Category: | Region / Route: | Contract Type: | Current Contract Value (nearest thousand £): | Date of Review | Name of Supplier Reviewer:- | Job Title:- | Email Address:- | Commercial Managers Name:- | Name of Network Rail Reviewer:- | Job Title:- | Commercial Managers Name:- | DOT | EA | DAS | BA | SI | CA | S | DOT | EA | DAS | BA | SI | CA | S
On Completion, please email this signed form to: PRISM@Networkrail.co.uk
PRISM | [8 empty] | Scoring Breakdown | [11 empty] | Errors = |  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Below is a scoring guide to help determine the scores for each category. This simply breaks down the overall score for each category into its constituent parts to arrive at an average category score. The average score when clicked will populate the PRISM form to the left. It is not necessary to complete - but is provided to assist you arrive at a fair score for each category.
Supplier Identification Details
Supplier Name: |  |  |  |  | Supplier Name, if not available above: NOTE:- You must select "Other" in the Supplier Name field | [15 empty] | 1 | 0 | 1
Supplier Oracle Number:
Parent Company:
Contract Identification Details
OProject number (6 Digits): |  |  |  |  | Primary Category: | [15 empty] | 1 | 1 | 2
Project Title: |  |  |  |  | Region / Route: | [15 empty] | 1 | 1 | 2
Contract Title: |  |  |  |  | Contract Type: | [15 empty] | 1 |  | 1
PO Number/Contract Reference: |  |  |  |  | Current Contract Value (nearest thousand £): | [15 empty] | 1 | 1 | 2
Review Details
Date of Review | [20 empty] | 1 |  | 1
Name of Supplier Reviewer:- |  |  |  |  | Name of Network Rail Reviewer:- | [15 empty] | 1 | 1 | 2
Job Title:- |  |  |  |  | Job Title:-
Email Address:- |  |  |  |  | Email Address:- | [15 empty] | 1 | 1 | 2
Commercial Managers Name:- |  |  |  |  | Commercial Managers Name:-
The Review
Click - "Click for Scoring Guidance" if guidance is required. Click anywhere on guidance note to remove guidance. | [8 empty] | Scoring Breakdown
RATING : | Very Poor | Poor |  | Adequate |  | Good | Very Good
SCORE : | 1 | 2 |  | 3 |  | 4 | 5
SUPPLIERS FEEDBACK |  |  | Score |  | NETWORK RAIL'S FEEDBACK |  |  | Score | SUPPLIER FEEDBACK - BREAKDOWN | [5 empty] | NETWORK RAIL FEEDBACK - BREAKDOWN
Supplier's Comments and Feedback on Network Rail's Performance |  |  |  |  | Network Rail's Comments and Feedback on the Supplier's Performance
Delivery On Time | [8 empty] | Documentation | Variations | Variation Impact on Programme | Programme Detail | Activities | Average (dbl click to use) | Documentation | Variations | Variation Impact on Programme | Programme Detail | Activities | Average (dbl click to use)
[21 empty] | 1 | 1 | 2 |  | 12 | [5 empty] | 13
Engineering Assurance | [8 empty] | Management of Risk | Review Levels | Safe By Design | Communication |  |  | Management of Risk | Review Levels | Safe By Design | Communication |  | Average (dbl click to use)
[21 empty] | 1 | 1 | 2 |  | 12 | [5 empty] | 13
Delivery as Specified |  |  | Delivery as Specified | [5 empty] | Specification | Information Provision | Health & Safety | Quality of Work | Sustainability |  | Specification | Information Provision | Health & Safety | Quality of Work | Sustainability | Average (dbl click to use)
[21 empty] | 1 | 1 | 2 |  | 12 | [5 empty] | 13
Behavioural Aspects | [8 empty] | Agreed Behaviours | Collaboration | Seeking Improvement | Skill |  | Average (dbl click to use) | Agreed Behaviours | Collaboration | Seeking Improvement | Skill |  | Average (dbl click to use)
[21 empty] | 1 | 1 | 2 |  | 12 | [5 empty] | 13
Stakeholder Interface
[21 empty] | 1 | 1 | 2
Contract Administration |  |  | Contract Administration | [5 empty] | Contract Obligations | Forecasting Accuracy | Notices & Communications | Close As You Go |  | Average (dbl click to use) | Contract Obligations | Forecasting Accuracy | Notices & Communications | Close As You Go |  | Average (dbl click to use)
[21 empty] | 1 | 1 | 2 |  | 12 | [5 empty] | 13
Safety |  |  | Safety Performance | [5 empty] | S&SD Documentation | Performance Monitoring | Inititiatives | S&SD Documentation |  | Average (dbl click to use) | S&SD Documentation | Performance Monitoring | Inititiatives | S&SD Documentation |  | Average (dbl click to use)
[21 empty] | 1 | 1 | 2 |  | 12 | [5 empty] | 13
Supplier Signature:- |  |  |  |  | Network Rail Signature:-
The undersigned hereby agree that the comments and feedback provided by either party have been discussed in an open and honest manner. Where an action is required these have been clearly defined and a mutually acceptable timescale has been agreed between both parties for the completion of the action (s).
Action Plan (enter details of Open and Closed improvement initiatives)
Category | Action (less than 256 characters) |  |  |  | Who (inits) | By When (date) | Status | Ref
Asset Group List | Category Group |  | REGION |  | Contract Type | Accounting Period
AM ASPRO | Ballast |  | SNE - Scotland |  | Construction | 1
AM Civils | Buildings |  | SNE - LNE |  | Design AND Construction | 2
AM Electrification | Business Consultancy |  | CEN - LNW |  | Design Services no construction | 3
AM Plant | CTRL |  | CEN - East Midlands |  | Goods/Materials | 4
AM Signalling | Contingent Labour |  | CEN - Building & Civils Design Group |  | Other Professional Services | 5
AM Telecoms | Electrification and Fixed Plant |  | SOU - Anglia |  | Other | 6
Birmingham New Street | Facilities |  | SOU - Kent |  |  | 7
Buildings | General Civils |  | SOU - Sussex |  |  | 8
Civils | HR and Training |  | SOU - Wessex |  |  | 9
Crossrail/Reading | Information Technology |  | W&W - Wales |  |  | 10
Enhancements | Infrastructure Support Services |  | W&W - Western |  |  | 11
ERTMS | Intelligent Infrastructure |  | W&W - Crossrail |  |  | 12
FTN/GSM-R | Logistics |  | W&W - Reading |  |  | 13
IP Electrification | Non Procurement |  | W&W - Electric Trains
IP Signalling | On Track Machines |  | SIGNALLING - SNE
Kings Cross | On Track Plant |  | SIGNALLING - W&W
Thameslink | Plant and Tools |  | SIGNALLING - STH |  |  | Amey UK Plc
Track | Professional Services Direct |  | SIGNALLING - CEN |  |  | Arup
Other | Rail Fleet |  | TRACK - SNE |  |  | Atkins Plc
| Rail and Ancillaries |  | TRACK - W&W |  |  | Babcock Rail
| Railway Spares |  | TRACK - STH |  |  | Balfour Beatty Civil Engineering
| Recruitment Services |  | TRACK - CEN |  |  | Balfour Beatty Rail
| Road Fleet |  | FTN/GSMER |  |  | BAM Construction
| Signalling |  | THAMESLINK |  |  | BAM Nuttall
| Sleepers and Bearers |  | IP HQ |  |  | C Spencer Ltd
| Supplies and Services |  | NON IP |  |  | Carillion Plc
| Switches and Crossings |  |  |  |  | Geoffrey Osborne
| Telecoms |  |  |  |  | GE Transportation System
| Track |  |  |  |  | Invensys Rail
| Utilities |  |  |  |  | J Murphy & Sons
| Other |  |  |  |  | Jacobs Engineering
Kier Group
May Gurney
Morgan Sindall plc
Mott MacDonald Group Ltd
Siemens Rail Automation
WSP UK Ltd
WYG Engineering
Delivery On Time | [5 empty] | - - -
Engineering Assurance | [5 empty] | ABB Ltd
Delivery as Specified | [5 empty] | AECOM
Behavioural Aspects | [5 empty] | Alan Baxter & Associates LLP
Stakeholder Interface | [5 empty] | Alan Dick Communications
Contract Administration | [5 empty] | Alun Griffiths (Contractors) Ltd
Safety | [5 empty] | Amalgamated Construction Ltd
Amey Colas JV
Ansaldo
Antagrade
APB Group
Aspin Foundation Ltd
B & M Mchugh
Bailey Rail
Barhale
BCM Construction
Bechtel
Braybrook Ltd
Bridgeway Consulting Ltd
Buckingham Group
Building & Civils Design Group
Cairn Cross Civil Engineering Ltd
Capita Property and Infrastructure Ltd
Capita Symonds
Centurion Site Services
Clancy Docwra
Colas Rail
Colas Rail Morgan Sindall JV
Construction Marine Ltd
Costain ltd
Dean & Dyball
DeltaRail
Dyer & Butler
ECHarris
EDF Energy
Faithful & Gould
Fonealarm
Forkers
Frequentis UK Ltd
Furrer+Frey
Galliford Try
Giffen Group
Giffords
H&M Security Services
Halcrow
Hawker Siddeley Switchgear
Hochtief
HomeGrown Timber Group
HVMS
Hyder consulting
Infrasig
Integrated Utility Services
John Graham Holdings Limited
Kelly I.T.S
Keltbray Rail
Kent PHK
Laing O'Rourke
Lend Lease
Linbrooke
Lloyds
LNW Works Delivery
Lowery
Lundy Projects
Mace
Mansell Construction
McNicholas Construction
Miller Construction
Morrison Utility Services
Mouchel Rail
MPB
MVA Consultancy Ltd
National Grid
National Signalling (Network Rail)
National Supply Chain
NDS
Northcroft
NR: OCR Team
OTHER
Park Signalling
Parsons Brinckerhoff
Pell Frischmann
QTS Group
Railsafe
Robert West
Robinson Kenning & Gallagher
S&T Cover
Schneider
Schofield Lothian Limited
Shilcocks
Signalling Solutions Ltd
Skanska
Sky High Count On Us
Sonic Rail Services
Sotera
Spence
Starc Ltd
Stobarts Rail
Story Contracting
Tata Steel Ltd
Taziker Industrial Ltd
Telent
Thales Group
The Trevor Patrick Partnership
Tony Gee & Partners
Tony Gee and Partners LLP
Turner and Townsend
UKPN Services
URS Corp
Vinci
Vital Human Resource
VolkerFitzpatrick
VolkerRail
Walker Construction
White Young Green and Scott Wilson
Works Infrastructure
WPS Group
WSP UK Ltd
YJLi
Insert Signature Image
Insert Signature Image
Guess Email Address
Click for Scoring Guidance
Click for Scoring Guidance
Todays Date
Click for Scoring Guidance
Click for Scoring Guidance
Click for Scoring Guidance
Click for Scoring Guidance
Click for Scoring Guidance
PDF This Form
Clear Comments & Scores Only
Clear Form
Clear Supplier Sig.
Clear NR Sig.
NEW PRISM FORM (version 2.04)
Please be aware that this is a new version of the PRISM form - Click anywhere on this message to remove.
Changes
1. Introduction of an 'Action Plan' section below the standard PRISM form
Please complete to show the intended actions to improve contract delivery/enablement (if any improvements are required).
2. Scoring Breakdown to the right of the standard PRISM form
Provided to assist scoring - It is not essential that this section is used. It is provided to assist project managers score more consistently and in line with the scoring guidance.

## Detailed Guidance
Scoring Criteria | 5 = Very Good | 4 = Good
3 = Adequate | 2 = Poor | 1 = Very Poor
In the event that both Network Rail and the Supplier's representative are unable to reach agreement on the scoring to be applied, this matter and details of the disagreement are to be escalated via the SAM (Supplier Account Management) process. If the contract is not subject to SAM process then the issues shall be escalated via the same hierarchy as is applied to the contract.
Delivery On Time
1 off Action At the project kick off meeting both parties are to agree the mobilisation periods for the project start up
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
Timely contract award for adequate lead times (including for design) | Timeliness of assurance, quality documentation and other submitted documentation (including for design) | 5 = Assessed party consistently provides all relevant documentation / approvals / acceptance etc in advance of the agreed programme requirements. Where variations to the contract scope are required they are agreed within a timescale relevant to the nature of the variation (ie:- simple, non complex within less than 5 working days, complex within a timescale as mutually agreed between the parties). They should have an appropriate timescale allowed for in order to undertake the additional activities in a safe and cost effective way, without negatively impacting upon other areas of the programme. Programme contains detailed activities in regards to the requirements for permanent and temporary works design, resources (plant, materials and labour), or other 3rd party influences and the lead time for these requirements are sufficiently detailed such that all orders / interactions are completed well in advance of the back stop date. The programme is continually monitored with a view to improving the delivery timescales (at levels 3 and 4) , reported against and all activities are delivered on time or in advance of the programme dates.
Effective and timely management of changes and variations (including for design) | Development, maintenance and adherence to programmes and plans (including integrated programmes for temporary and permanent works design) | 4 = Assessed party consistently provides all relevant documentation / approvals / acceptance etc in accordance with the agreed programme requirements, and occasionally in advance of the programme. Where variations to the contract scope are required they are agreed within a timescale relevant to the nature of the variation (ie:- simple, non complex within less than 10 working days, complex within a timescale as mutually agreed between the parties). They have been agreed with an appropriate timescale allowed for in order to undertake the additional activities in a safe and cost effective way, but they may have an impact upon other areas of the programme. Programme contains outline level activities in regards to the requirements for permanent and temporary works design, resources (plant, materials and labour), or other 3rd party influences. The programme is continually monitored, reported against and all activities are delivered on time.
Timely provision of NR free issued materials and plant (including information for design) | Timely site provision of plant and materials (and temporary and permanetn works design submissions to avoid late or last minute processing of certification) | 3 = Assessed party provides all relevant documentation / approvals / acceptance in accordance with the agreed programme. Where variations to the contract scope are required they are agreed within a timescale relevant to the nature of the variation (ie:- simple, non complex within less than 21 working days, complex within a timescale as mutually agreed between the parties). They are agreed with an appropriate timescale to complete the additional activity in a safe but not necessarily cost effective way, the additional requirements may have a negative impact on other areas of the programme. Programme contains high level activities in regards to the requirements for permanent and temporary works design, resources (plant, materials and labour) and other 3rd party influences. The programme is continually monitored, reported against and the majority of activities are delivered on time, and those which aren't achieved on time have limited impact upon the overall programme.
Realistic timescales set for the safe delivery of the requirements:- possessions, lead times etc (including for design) | Timely provision of team resources, site and off site (including for design) | 2 = Assessed party consistently provides all relevant documentation / approvals / acceptance late but within 10 working days of the agreed programme. Where variations to the contract scope are required they take time to agree regardless as to the nature of the variation. The additional requirements will have a negative impact on other areas of the programme. Programme contains high level activities in regards to the requirements for permanent and temporary works design, resources (plant, materials and labour) and other 3rd party influences. The programme is occasionally monitored and reported against however, a proportion of the activities are delivered late, requiring some mitigation / intervention in order to meet the overall programme.
Timely approval of submitted documentation; including assurance submissions and quality documentation, planning permissions temporary and permanent works design submissions etc | Impact of re-work, remediation and late changes to temporary and permanent works design | 1 = Assessed party consistently provides all relevant documentation / approvals / acceptance late (greater than 10 days) against agreed programme. Where variations to the contract scope are required they take significant time (greater than 21 working days) to agree regardless as to the nature of the variation and they are unrealistic / unacceptable in regards to timescales to complete the activity and potentially introduce safety risk to the programme. The additional requirements will have a negative impact on other areas of the programme. Programme doesn't contain sufficient detail in order to ensure that permanent and temporary works design, resources (plant, materials and labour) and other 3rd party influences are provided in a timely manner to meet programme. The programme is occasionally monitored and reported against however, a significant proportion of the activities are delivered late, requiring continual mitigation / intervention in order to meet the overall programme.
Engineering Assurance
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
5 = Management of risk and engineering assurance review requirements completely aligned between supplier and Network Rail. Low levels of review or review levels reduced progressively following consistently high quality of deliverables. Good evidence of application of Safe by Design principles. Effective 2 way communication optimising the management of engineering risk and communicating client requirements clearly and efficiently
4 = No resubmissions necessary and comments are minimal with low or reducing levels of assurance required. Responses to queries consistently high quality and risks managed proactively. Clear evidence of application of Safe by Design principles.
3 =No resubmissions necessary due to either Supplier or Network Rail deficiencies. Only minor comments requiring action and consistently good quality deliverables provided. Risk management effective. Evidence of application of Safe by Design principles. Dialogue and comments associated with engineering assurance is clear and actionable.
2 = Some deliverables requiring resubmission and regular comments requiring actions result in high levels of review. Higher levels of review being carried out than considered necessary for a project with the risk profile presented. Modest evidence of Safe by Design principles. Dialogue regarding comments through engineering assurance not helping the progress of the project. Considering or already escalating issues to national SAM meetings. Risk management a concern requiring the involvement of senior people.
1 = Poor quality deliverables, requiring high levels of review and frequent resubmissions necessary to achieve suitable deliverables. Key risks not managed effectively without intervention typically involving senior people within both organisations. No evidence of application of Safe by Design principles. Dialogue regarding comments through engineering assurance process blocking the progress of the project. Supplier or Network Rail Engineering Assurance performance has been escalated to national SAM meetings
Delivery as Specified
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
Clarity of Scope, at contract award and in any ensuing variations. Clear, unambiguous and consistent communication of standards and expectations | Quality of permanent and temporary works design and integration of same physical workmanship, waste management | 5 = Significantly exceeds specification but achieved the cost and programme milestones successfully. Provided innovation or functionality that exceeded specification and was aligned to Network Rail objectives. Provision of information and deliverables from either parties that are consistently high quality and exceeding requirements and therefore providing additional project benefits. Delivers health and safety risks mitigations through the design process. High quality of workmanship and documentation providing a legacy that exceeds client expectations. Environmental management exceeds expectations and is reflected in a culture that supports all aspects of sustainability.
Fully documented contract variation instructions which are clear and unambiguous | Corrective action reports including for design | 4 = Specification exceeded and additional benefits achieved but achieved the cost and programme milestones successfully achieved. Good quality of workmanship and documentation. Delivers health and safety risks mitigations through the design process. Both parties provide information and deliverables that are high quality with additional benefits to the projects. Environmental and sustainability exceed minimum requirements of the project consistently
Availability of "as is" drawings and other information required to identify risks. | Sub-contractor management including coordination of permanent and temporary works design | 3 = Achieved the specification without the need for intervention. Adequate workmanship and documentation as required by the specification. Information and deliverables consistently high quality. Delivers health and safety risks mitigations through the design process. Environmental management compliant and sustainability objectives achieved.
Quality of Design's or other documentation including assessment of health and safety risks and opportunities to design risk out and residual risks thereafter. | Quality management including for design | 2 = Failed to achieve the specification or had significant intervention to achieve the specification. Workmanship and documentation have deficiencies that require correction. Information and deliverables from either party fail to meet expectations. Delivers health and safety risks mitigations occasinally through the design process. Environmental and Sustainability issues not addressed adequately.
Support to contractor initiatives and standards in regards to Environmental matters, Response to environmental plan | Environmental Management - consider any specific requirements and adherence to environmental plan, responses to environmental incidents, Environmental management culture on site | 1 = Consistently fail to achieve the requirements of the specification. Workmanship is consistently poor with significant areas incomplete or failing to achieve functional requirements. Outputs of the project would not be possible without significant intervention. Consistently poor quality deliverables and information. Health and safety risk mitigations never or hardly ever delivered through the design process. Understanding of requirements regularly confused and delivery reflects lack of common understanding and/or competence
Waste Management | Compliance with the specification, NR Standards and quality assurance procedure
Behavioural Aspects
1 off action At the project kick off meeting both parties shall review their corporate values / behaviours and agree on the behaviours that they wish to see exhibited throughout the contract duration.
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
Teamwork Joint pursuit of whole life best value Collaborative and support both on and off the worksite Timely, open communication and issues visibility Pro-active risk management | Teamwork Collaborative and support both on and off the worksite Timely, open communication and issues visibility Pro-active risk management | 5 = Assessed party consistently demonstrates the behaviours that have been agreed at the project kick off meeting, regardless as to whether the project is progressing on time and to cost etc. Works in a collaborative manner and proactively seeks and values all contributions to resolve issues and conflicts regardless as to source. Is always seeking ways to improve performance for the contract as a whole, not just their team. All members of the team are skilled appropriately for the tasks that they are undertaking. Continually promotes success, and additionally reviews how things can be improved throughout the life of the contract/project, regardless as to standard of performance and without the need to be prompted by the other party.
Determination Culture of performance and continuous improvement Appropriately trained, skilled and experienced people to manage the contract | Determination Culture of performance and continuous improvement Appropriately trained, skilled and experienced people to manage the contract Seeking whole life best value at all times | 4 = Assessed party demonstrates the behaviours that have been agreed at the project kick off meeting, regardless as to whether the project is progressing on time and to cost etc. Works in a collaborative manner and values all contributions. Seeks ways to improve performance albeit mainly centred around their own companies improvement, rather than specifically to improve contract/project performance. The majority of the team (and all key posts) are appropriately skilled for the tasks that they are undertaking. Occasionally considers improvements that may be made, but as a result of an issue that has arisen, rather than on a pro-active basis.
Respect Honesty Courtesy Integrity Willingness to comply with the contract, including timely payments | Respect Honesty Courtesy Integrity Willingness to comply with the contract | 3 = Assessed party generally demonstrates the behaviours that have been agreed at the project kick off meeting, however, in times of poor performance (of either party) does not adhere to them. Tends to worked in a silo mentality when issues arise rather than working together to resolve. Works in accordance with the "contract requirements" and is unwilling to consider alternative ways to improve the contract/project output. Some, but not all, key personnel are skilled appropriately for the tasks that they are undertaking. Rarely considers opportunity to improve performance, albeit does undertaken lessons learnt in the event of poor performance of a key activity.
Pride Taking appropriate responsibility to issue ownership Ethical behaviour Innovative solutions Pro-actively striving for excellence | Pride Responsible behaviour Innovative solutions Pro-actively striving for excellence | 2 = Assessed party understands that there are NR values which represent ideal working relationships, however, fails to work in accordance with the majority of them, regardless as to whether the project is progressing on time and to cost. Works strictly in accordance with the contract conditions and predominantly in a confrontational/adversarial manner whenever issues arise. A significant proportion (including key personnel) of their team is not skilled appropriately for the tasks that they are undertaking. Fails to undertake any form of lessons learnt review in the event of an issue arising, albeit does not seek to apportion blame.
1 = Assessed party consistently dismisses the NR values and works in a confrontational / adversarial manner regardless as to whether the project is progressing on time and to cost etc. the majority of personnel (key or otherwise) do not have the skills required to carry out the tasks that they are undertaking. Apportions blame at times of poor performance rather than attempt to determine what could be done to improve performance for the good of the contract
Stakeholder Interface
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
Interface with Project Sponsors, LUL etc | Interface with project sponsors | 5 = Continually and pro-actively engages with 3rd party stakeholders to seek their input into matters from the contract commencement, regardless as to whether there is a programme / contractual obligation to do so.
Network Rail NDS, Operations and Customer Service, Maintenance (if applicable) | Network Rail NDS, Operations and Customer Service, Maintenance (if applicable) | 4 = Ensures that 3rd party engagement is considered during the contract, and identifies any specific requirements. Makes all necessary contact at the earliest opportunity with such 3rd parties.
Network Rail 3rd party suppliers | If applicable - Assurance documentation to LUL If applicable - Access Planning with LUL | 3 = Ensures that 3rd party engagement is carried out in accordance with the contract requirements.
2 = Accepts that 3rd party engagement is required, but fails to do this in a timely manner, such that the project delivery is negatively impacted.
1 = Fails to undertake any 3rd party engagement, with significant detrimental impact on the project delivery.
Contract Administration
1 off Action:- Both parties should review the contract award timescales and determine whether these were achieved in accordance with the declared tender programme and capture commentary within the scorecard as to any impacts of over / under achievement
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
Fair and measured response to valuations, claims and final account discussions | Timely response to instructions | 5 = All contracting obligations are exceeded for all payments, changes, notices such that project delivery is improved. Systems for timely capture and allocation of costs are fully understood and effectively used by all members of the team. Payment process is consistently completed to time (or ahead of time) without any "surprises". Short term and AFC forecasts are consistently accurate, updated and maintained throughout the life of the contract. Assessments of costs of change are accurate and kept up to date. The opportunity for resource savings (methodology, productivity, waste, better buying etc) are constantly reviewed identified and delivered. All contract notices and communications are up to date (at all times) agreed and recorded. Change and claims are collaboratively managed, fully controlled and up to date.
Closing out claims as they arise | Appropriate resources employed to delivery the requirements (in accordance with resource loaded programme) increased / decreased as necessary to ensure satisfactory delivery of the requirements | Throughout the life of the project a "close as you go" commercial approach is adopted to facilitate timely final accounting. Final accounts are completed in advance of the contractual timescales following Substantial Completion. Aspirational targets are mutually agreed and widely distributed across both teams. Lessons learnt process is effective in securing continuous improvements. The resources employed to deliver the requirements are at an appropriate level required at any given point during the contract period.
Avoidance of waste and re-work | Efficiency methods being employed and visible | 4 = The majority of contracting obligations are exceeded (if not exceeded, then all met) for all payments, changes, notices such that project delivery is improved. Systems for timely capture of allocation of costs are implemented; the commercial team and the key personnel understand and effectively use the systems. Short term and AFC forecasts are generally accurate, updated and maintained throughout the life of the contract. All commercial contracting obligations are met and some aspirational targets (namely; Savings, innovations, relationships, lessons learnt) are achieved. The opportunity for resource savings (methodology, productivity, waste, better buying etc) are occasionally reviewed (on a pro-active basis), identified and delivered. The resources employed to deliver the requirements are appropriate to deliver the requirements and do vary appropriately throughout the contract duration, but are slow to react to increases / decreases in scope.
Co-operating in mitigating the cost impact of disruptive events | Pro-active identification of potential waste and re-work in a timely manager - any such occurrences being duly mitigated wherever possible | At key stages or milestones of the project lifecycle a "close as you go" commercial approach is adopted to facilitate timely final accounting. Final accounts are completed within the contractual timescales following Substantial Completion. Aspirational targets are widely distributed across both teams. Change and claims are collaboratively managed, fully controlled and up to date. Aspirational targets are agreed and distributed to relevant personnel across both teams.
Access to complete resolution of snagging items | Satisfactory quality of evidence to support application | 3 = All contracting obligations are met for all payments, changes, notices such that project delivery is not inhibited. Systems for timely capture of allocation of costs are implemented; the commercial team and the some of the key personnel understand and effectively use the systems. Short term and AFC forecasts are generally accurate, updated and maintained throughout the life of the contract. Some aspirational targets (namely; Savings, innovations, relationships, lessons learnt) are achieved. The opportunity for resource savings (methodology, productivity, waste, better buying etc) are occasionally reviewed (only at the request of the other party). The resources employed to deliver the requirements are generally appropriate to deliver the requirements, but do not flex with increases / decreases in scope.
Continuity of management throughout the close-out period | Mitigation of the costs of variations | Final accounts are completed within the contractual timescales following Substantial Completion. Aspirational targets are distributed but not across both teams. Change and claims are managed but may not be up to date. Aspirational targets are occasionally considered. Apps and Payments generally agreed in accordance with the contract and on time and they are accurate. The opportunity for resource savings (methodology, productivity, waste, better buying etc) are occasionally reviewed as and when requested by either party.
Effectiveness of hand back | Realism of Claims | 2 = Contracting obligations are consistently missed for payments, changes, notices and as such have a negative impact on project delivery. Systems for timely capture and allocation of costs are not understood or implemented appropriately. Payment process is consistently incomplete, late, or contains elements unknown to the other party. Short term and AFC forecasts are rarely completed and when they are they are consistently inaccurate and out of date. Assessments of costs of change are consistently inaccurate and out of date. No consideration is given to the opportunity for resource savings (methodology, productivity, waste, better buying etc). Contract notices and communications are inaccurate, and not agreed. Final accounts exceed the contract obligation by greater than 50% in time.
Close out review for shared lessons learned / continuous improvement | Mitigation of possession / train delays | No aspirational targets are set. No consideration is given to lessons learnt or continuous improvement. The resources employed to deliver the requirements are inappropriate (be that too many or too few) for the majority of the contract period
| ` | 1 = Contracting obligations are always missed for payments, changes, notices and as such have a significant impact on project delivery. Systems for timely capture and allocation of costs are not understood or implemented appropriately. Payment process is consistently incomplete, late, or contains elements unknown to the other party. No Short term and AFC forecasts provided throughout the life of the contract. Assessments of costs of change are inaccurate and out of date. No consideration is given to the opportunity for resource savings (methodology, productivity, waste, better buying etc). Contract notices and communications are inaccurate, and not agreed.
Final accounts exceed the contract obligation by greater than 75% in time. No aspirational targets are set. No consideration is given to lessons learnt or continuous improvement. The resources employed to deliver the requirements are inappropriate (be that too many or too few) at all times during the contract period
Safety & Sustainable Developemnt (To include Helath, Safety & Environment)
1. S & S D Documentation
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
The Principal Contractor is to comment on the quality and submission of Pre-construction S&SD Information submitted to them by the Project Team. S&SD Documentation, includes all Health, Safety and Environmental information supplied to the Principal Contractor by the Project Team, that takes into consideration the risks, threats, constraints and opportunities in relation to the project from a health, safety and environmental perspective S&SD Documentation includes all: a) Pre-Construction Information, as required by the Construction (Design and Management) Regulations 2007 b) Specific Environmental information in relation to the project. The timely high quality provision of pre-construction S&SD information by Network Rail is an essential activity. Please consider and provide feedback to Network Rail on the following; - Documentation is of high quality. - Documentation was provided on time - Documentation is relevant. - Document is accurate. | The Network Rail Project Team is to comment on the quality and submission of all S&SD Documentation submitted to the Project Team for it's consideration and review. This could include: a) The Construction Phase Plan b) Information in relation to the Environmental Management Plan for the Project c) Project Specific Safety and Environment Risk Registers d) Work Package Plans If Construction Safety and Sustainable Development information is not submitted in a timely manner and it does not address the specific risks associated with the project, this will have an impact on the ability of the project to be delivered in a safe and compliant manner. - Documentation is of high quality. - Documentation was provided on time - Documentation is relevant and project specific - Documentation identifies the specific risks and mitigations on the project - Document is accurate. | 5. Outstanding: a) The documentation submitted is project specific b) It has been submitted in advance of timescales to enable timely review c) It identifies all high risk activities/concerns and provides assurance that these risks have been mitigated against d) Evidence of innovation can be found within approach taken in respect of safety and environmental management on the project e) The detail contained within the documentation is appropriate to the risk f) The quality of the documentation, it's accuracy and it's ability to engage the reader is of very high standard. 4. Exceeded: a) The documentation submitted is project specific b) It has been submitted in advance of timescales to enable timely review c) It identifies all high risk activities/concerns and provides assurance that these risks have been mitigated against d) The detail contained within the documentation is appropriate to the risk e) The quality of the documentation, it's accuracy and it's ability to engage the reader is of very high standard. 3. Good: a) The documentation submitted is project specific b) It has been submitted on time c) It identifies all high risk activities/concerns and provides assurance that these risks have been mitigated against d) The detail contained within the documentation is appropriate to the risk e) The documentation is adequate and meets requirements
2. Poor a) The documentation submitted is non-project specific b) It has been submitted on time c) It contains a broad range of risk information, that make it difficult to identify the significant risks on the project d) The documentation is either over excessive or little value e) There is evidence of cut and pasting information from other similar documents within it f) The information has had to be resumitted as it was deemed inadequate on it's first review 1. Significant Room for Improvement a) The documentation is non-project specific b) It has been submitted late c) The risk information contained within it is of little value d) There is wide scale evidence of cutting and pasting information from similar documentation e) The information has had to be resumitted as it was deemed inadequate on it's first review
2. Performance Monitoring
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
The Principal Contractor is to comment on their experience of reporting Safety & Sustainable Development Performance Indicators/Data to the project. a) Has the project team explained what needs to be measured and why we are collecting the information requested. b) Has the project set up the KPI Reporting tool correctly to enable the supplier to submit their periodic data against relevant project code(s) c) Where data has been submitted, has the project team validated this information in a timely manner to enable the supplier's data to be included within the overall Infrastructure Project S&SD submission to the Board d) Is the data that has been submitted by the supplier discussed at Project Review Meetings and is it used to inform decision making and generate initiatives to improve Safety and Sustainable Development Performance and behaviours on the project. | The Project Team is to comment on the S&SD data supplied by the PC at period end. a) Did the supplier submit their KPI data within the required timescales at period end. b) Was the data submitted accurate or did the Project Team have to query the data submitted c) Did the data submitted include data relating to the non-mandatory Indicators: Close Call information; Health Surveillance; Safety Inspections; Safety Tours on the project d) Is the data that has been submitted by the supplier discussed at Project Review Meetings and is it used to inform decision making and generate initiatives to improve Health, Safety and Environmental Performance and behaviours on the project. | 5. Outstanding: a) All data is supplied well in advance of deadlines b) It is accurate and has been reviewed by the Project Team c) All mandatory data requirements are included in the submission d) All non-mandatory, proactive safety and sustainable development performance indicators has been competed, including details of: Close Call; Health Surveillance; Safety and Environmental Inspections; Safety Tours information on for the project e) The data is reviewed each month by both the supplier and project team and it is used to inform decison making and generate an improvement plan on the project to enhance S&SD performance. f) Through these discussions additional matrix are suggested as means of measuring and improving S&SD performance on the project. 4. Exceeded: a) All data is supplied well in advance of deadlines b) It is accurate and has been reviewed by the Project Team c) All mandatory data requirements are included in the submission d) Three non-mandatory, proactive safety and sustainable development performance indicators has been competed that may include details of: Close Call; Health Surveillance; Safety and Environmental Inspections; Safety Tours information on for the project e) The data is reviewed each month by both the supplier and project team and it is used to inform decision making and generate an improvement plan on the project to enhance S&SD performance. 3. Good: a) All data is supplied on time b) It is accurate and has been reviewed by the project team c) All mandatory data requirements are included in the submission d) At least one non-mandatory, proactive safety and sustainable development performance indicators has been competed that may include details of: Close Call; Health Surveillance; Safety and Environmental Inspections; Safety Tours information on for the project e) The data is reviewed each month by both the supplier and project team.
2. Poor: a) Data is supplied late and/or. b) Data is supplied, but the NR Proeject Team are routinely required to chase the PC for it, and/or c) It is accurate, but did not get reviewed by the project team in a timely manner, which meant it could not be submitted and/or d) The data reviewed by the Project Team contained inaccuracies and the supplier was questioned over their submission e) None of the non-mandatory fields have been completed f) The data is not used to generate discussions at regular project progress meetings. 1. Significant Room for Improvement: a) Data cannot be submitted as the project has not been set up by the NR Project Team to enable the data to be supplied and/pr b) The system has been set up, but the PC fails to routinely to submit their data and/or c) No data is reviewed at regular project progress meetings. d) There is a lack of understanding as to why data is being collected on the project.
3. S & S D Initiatives
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
The Principal Contractor has created an environment on the project where improving S&SD performance is of paramount importance. The Principal Contractor is to comment on how receptive and supportive the Project Team is of them implementing a mature S&SD culture on the project: This could include but is not restricted to: a) Bespoke Behaviour/S&SD/Designing out Waste Workshops b) Health and Wellbeing initiatives c) Innovation is used to promote and mitigate risks to people and the environment d) The wider community is consulted on project activities and are advised of mitigations to reduce the impact of project activities on them. e) The workforce are regularly consulted on S&SD performance and their ideas are sought in order can be improve S&SD performance | The Project Team is to comment on the Principal Contractors focus on improving S&SD performance the project. How receptive is the Principal Contractor in implementing a mature S&SD culture on the project:that will help create the right environment where improved S&SD performance is its core focus. Initiates could include but are not restricted to: a) Bespoke Behaviour/S&SD/Designing out Waste Workshops are delivered on the Project b) Health and Wellbeing initiatives being implemented on the project c) Innovation used to promote and mitigate risks to people and the environment d) Evidence that the wider community is regularly consulted about project activities and are advised of the mitigations in place to reduce the impact of project activities may have on them. e) The workforce are regularly consulted on S&SD performance and their ideas are sought in order can be improve S&SD performance | 5. Outstanding: a) The Project Team and the Principal Contractor meet to discuss how S&SD performance can improved on the project b) Both parties work together to implement initiatives and there are examples of several proactive S&SD initiatives implemented on the project that both parties would recognise c) Feedback from the workforce (from Safety Truck visits/Surveys etc) in respect of improving S&SD performance is sought and acted upon d) Feedback from the wider community (from consultative meetings/project communications), in respect, of reducing the impact of the project on the community is actively sought and acted upon on the project d) There is recognition that those undertaking, supervising and managing construction activity, are motivated and engaged in improving S&SD performance e) There is recognition that a mature S&SD culture exists on the project and is recognised by both parties on the project 4. Exceeded a) The Project Team and the Principal Contractor meet to discuss how S&SD performance can be improved on the project b) Both parties work together to implement initiatives and there are examples of at least two proactive S&SD initiatives implemented on the project that both parties would recognise c) Feedback from the workforce (from Safety Truck visits/Surveys etc) in respect of improving S&SD performance is sought and acted upon d) Feedback from the wider community (from consultative meetings/project communications) in respect of reducing the impact of the project on the community is actively sought and acted upon on the project e) There is an recognition that those supervising and managing the project are activity, are motivated and engaged in improving S&SD performance f) There is recognition that a mature S&SD culture exists on the project and is recognised by both parties on the project
3. Good: a) The Project Team and the Principal Contractor meet to discuss how S&SD performance can be improved on the project b) Both parties work together to implement initiatives and there is at least one example of a proactive S&SD initiative implemented on the project, that both parties would recognise c) Feedback from the workforce (from Safety Truck visits/Surveys etc) in respect of improving S&SD performance is sought and acted upon d) Management is committed and motivated in improving S&SD performance e) S&SD performance on the project has not got any worse throughout the life of the project. 2. Poor: a) The Project Team and the Principal Contractor meet but spend little, if any time discussing S&SD performance. b) Management say that they are committed and motivated in improving S&SD performance on the project, but there is little evidence of this. c) There is no recognition that specific S&SD initiatives have been implemented on the project. d) S&SD performance has not improved and there are concerns about the S&SD performance on the project. 1. Significant Room for Improvement: a) The Project Team and the Principal Contractor meet but no time is spent reviewing S&SD performance b) There is a perception that lip service is paid to S&SD performance and that delivery is of paramount importance. c) There is no recognition that specific S&SD initiatives have been implemented on the project. d) S&SD performance has got worse throughout the life of the project.
4. Competence of S&SD Staff
Performance Indicators for Consideration for the Supplier | Performance Indicators for Consideration of Network Rail | Scoring Guidance
The Principal Contractor is to comment on the performance of the S&SD resource allocated by the NR Project Team to the project and/or the ability of the NR Project Teams to respond to S&SD queries, concerns and requests for information | The NR Project Team is to comment on the performance of the S&SD resource allocated by the project by the PC and/or the ability of the PC to respond to S&SD queries, concerns and requests for information, which includes information arising from accidents and incidents. | 5. Outstanding: The NR Project Team/PC has dedicated S&SD resource(s) attributed to it that is/are: a) Competent b) Professional c) Strategic and collaborative in their approach; - they work with other suppliers and NR in order to embed current S&SD best practice onto their project. d) Is visible to those delivering the project and is proactive in their dealings with them e) Offers solutions and ideas to the Project Team/PC f) Is able to communcate and articulate their concerns and ideas to workforce/Management g) Always responds to requests for information and assistance promptly 4. Exceeded: The NR Project Team/PC has dedicated S&SD or shared resource(s), determined by risk, attributed to it that is: a) Competent b) Professional c) Is visible to those delivering the project is proactive in their dealings with them d) Offers solutions and ideas to the Project Team/PC e) Is able to communicate and articulate their concerns and ideas to workforce/Management f) Always responds to requests for information and assistance promptly 3. Good: The NR Project Team/PC has a S&SD resource, but it is shared amongst a number of projects, but is deemed adequate for the risk profile of the project, that is regarded as: a) Competent b) Professional c) Is visible to those delivering the project d) Is able to communicate and articulate their concerns to workforce/Management e) Always responds to requests for information and assistance, but may need to be reminded 2. Poor: The NR Project Team/PC has a S&SD resource, but it is shared amongst a number of projects, the resource is deemed inadequate in respect of the risk profile of the project. The resource provided is however regarded as: a) Competent b) Professional c) Is not visible enough on the project d) Is able to communicate and articulate their concerns to workforce/Management e) Responds to requests for information and assistance, but the response may take some time to be given. 1. Significant Room for Improvement: The NR Project Team/PC has no dedicated S&SD resource on the project. The resource is ad hoc. a) Competence is questioned b) Is not visible enough on the project c) There is no evidence of communication between the S&SD resource and the workforce d) Responses to requests for information and assistance are rarely answered. e) Demonstrates unprofessional behaviours
Appendix : Safe by Design Guidance
(a) Clear evidence of the concurrence of Health and Safety risk identification and management all documentation from PCIP through design information to method statements and programme for implementation on site and maintenance of the asset thereafter.
"Good" would be prominent evidence, "Poor" would be no evidence
b) Effective coordination and management of integrated permanent works and temporary works design
"Good" would be well documented procedures including clear definition of rles and responsibilities and timely information transfer. Poor" would be reflect lack of suitably defined procedures, role definition and information distribution.

## Sheet3 (hidden)
Supplier Number | Supplier Name | Supplier Number
85 | ADAS UK | 85
3125 | AECOM Ltd | 3125
9216 | Alan Baxter & Associates LLP | 9216
6517 | Altran UK Ltd | 6517
15787 | Amey LG Ltd | 15787
219 | Appleyards Ltd | 219
25067 | Arcadis (UK) Ltd | 25067
14723 | Arrowvale Electronics | 14723
276 | Asset Management Consulting Ltd | 276
16610 | Atkins Ltd | 16610
1564 | Babcock Rail Ltd | 1564
16739 | Balfour Beatty Management Ltd | 16739
346 | Balfour Beatty Rail Projects Ltd | 346
3443 | Balfour Beatty Rail Technologies Ltd | 3443
7981 | Bellwether Enterprises Ltd | 7981
460 | Birse Rail Ltd | 460
13256 | Bovis Lend Lease Consulting Ltd | 13256
549 | Bridgeway Consulting Ltd | 549
18146 | Brunswick Infrastructure Services Ltd | 18146
5573 | Butler & Young Lift Consultants Ltd | 5573
729 | Capita Symonds Ltd | 729
8442 | Carter Jonas | 8442
763 | Cass Hayward & Partners | 763
774 | CCD Design & Ergonomics Ltd | 774
996 | Competence Assurance Solutions Ltd | 996
1118 | Crouch Waterfall & Partners | 1118
102 | DeltaRail Group Ltd | 102
1295 | Donaldson Associates Ltd | 1295
1347 | EC Harris LLP | 1347
9163 | Environmental Scientifics Group Ltd. | 9163
15392 | ESR Technology Ltd | 15392
11584 | Faithful + Gould | 11584
3991 | Frankham Consultancy Group Ltd | 3991
1617 | Franklin & Andrews Limited | 1617
7779 | Frazer-Nash Consultancy Ltd | 7779
1666 | Gardiner & Theobald | 1666
1706 | George Corderoy & Co | 1706
13684 | Gleeds (Nottingham) | 13684
5365 | Grontmij | 5365
16923 | GS Partnership Ltd | 16923
17061 | Gutteridge Haskins & Davey Ltd | 17061
3846 | Halcrow Group Ltd | 3846
1856 | Haleys Ltd | 1856
8372 | Hurley Palmer Flatt Ltd | 8372
2030 | Hyder Consulting (UK) Ltd | 2030
11795 | I S Consulting Limited | 11795
7145 | IDP Architects LLP | 7145
8077 | Infrasafe Ltd | 8077
16106 | Initiate Consulting Ltd | 16106
4681 | Invensys Rail Ltd | 4681
328 | Jacobs UK Ltd | 328
2244 | Jeremy Benn Associates Limited | 2244
2804 | Lloyd's Register Rail Ltd | 2804
5071 | LR Scandpower Ltd | 5071
2654 | Mace Ltd | 2654
2739 | May Gurney Ltd | 2739
9878 | McNicholas Construction Services Limited | 9878
15384 | MGB Signalling Ltd | 15384
5537 | MLM Consulting Engineers | 5537
2885 | Mott MacDonald Ltd | 2885
3774 | Mouchel Rail Ltd | 3774
4277 | MVA Consultancy Ltd | 4277
4572 | Opus International Consultants (UK) Ltd | 4572
3133 | Ove Arup & Partners | 3133
8460 | Parsons Brinckerhoff Ltd | 8460
3217 | Pell Frischmann Consulting Engineers Ltd | 3217
3392 | QSS (Quality and Safety Services) Group | 3392
3470 | Railway Systems Consultants Ltd | 3470
33991 | Ramboll UK Ltd | 33991
3577 | Robert West Consulting Ltd | 3577
3581 | Robinson Kenning & Gallagher | 3581
9496 | RWA Rail Ltd | 9496
17130 | Savills (L&P) Ltd | 17130
18316 | Schofield Lothian Ltd | 18316
5137 | Sinclair Knight Merz Europe Ltd | 5137
3909 | Southdowns Environmental Consultants Ltd | 3909
3982 | Steer Davies Gleave | 3982
9652 | Sweett (UK) Ltd | 9652
588 | Tata Steel UK Ltd | 588
6876 | Temple Group Ltd | 6876
5795 | The Trevor Patrick Partnership | 5795
4414 | Tony Gee & Partners LLP | 4414
16501 | TPS Consult Ltd | 16501
4487 | Turner & Townsend LLP | 4487
7833 | URS Infrastructure & Environment UK Ltd | 7833
4601 | W A Fairhurst & Partners | 4601
4629 | Wardell Armstrong LLP | 4629
275 | Waterman Transport & Development Ltd | 275
4697 | WYG Engineering Ltd | 4697