## Plain Line CP5 remainder & CP6
Please Note that Amey Rail is delivering Carillion jobs following the purchase of Carillion contracts by Amey Rail
Project Manager | Delivery Function | Portfolio Code | Route | Contractor | Depot | Business Year | Engineering Week | Project ID | Activity ID | UID | Worksite | Work Category | Track ID | ELR | Part of Week | PPS Worksite No. | Start DateTime | Finish DateTime | Possession Duration | Activity Description | Planned Start Miles | Planned Start Yards | Planned Finish Miles | Planned Finish Yards | Planned Yards | Activity Notes | Change State
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 1 | 148273 | G4T335380 | 23301217 | Kensal Green South | 14 | 2100 | LEC1 | Weekend | W2018/5659689 | 2018-03-30 23:30 | 2018-04-03 05:30 | 3 day(s) 06:00 Hrs | CORE: 1st Core Kensal Green South 680 Yards of CAT14 TSR 50mph T137258 | 4 | 730 | 4 | 1410 | 680 | TQ required to change sleepers to EG47's - agreed and ordered | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 1 | 148309 | G2080 | 42200415 | New Cross Gate to Brockley (Dn) | 2 | 2200 | LBW | Weekend | W2018/5707694 | 2018-03-31 01:05 | 2018-04-02 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 4 | 0 | 4 | 21 | 21
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 1 | 148309 | G4T75570 | 42200415 | New Cross Gate to Brockley (Dn) | 11 | 2200 | LBW | Weekend | W2018/5707694 | 2018-03-31 01:05 | 2018-04-02 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 885 | 4 | 0 | 875
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 1 | 145803 | A353340 | 32201523DN | Cleghorn Dn | 14 | 2100 | WCM1 | Weekend | W2018/5686662 | 2018-04-01 00:01 | 2018-04-03 06:01 | 2 day(s) 06:00 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 330y) | 76 | 423 | 76 | 901 | 478
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 1 | 145803 | A371660 | 32201523UP | Cleghorn Up | 45A | 1100 | WCM1 | Weekend | W2018/5686662 | 2018-04-01 00:01 | 2018-04-03 06:01 | 2 day(s) 06:00 Hrs | CORE: 1st CW (45A - Renew Level Crossing Surface (Associated with Track Renewal) | 76 | 520 | 76 | 570 | 0
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 1 | 145803 | A373440 | 32201523UP | Cleghorn Up | 14 | 1100 | WCM1 | Weekend | W2018/5686662 | 2018-04-01 00:01 | 2018-04-03 06:01 | 2 day(s) 06:00 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 40y) | 76 | 480 | 76 | 520 | 90 | Production delays week 01 (-46 yds) | CR
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 1 | 145803 | A373450 | 32201523DN | Cleghorn Dn | 45A | 2100 | WCM1 | Weekend | W2018/5686662 | 2018-04-01 00:01 | 2018-04-03 06:01 | 2 day(s) 06:00 Hrs | CORE: 1st CW (45A - Renew Level Crossing Surface (Associated with Track Renewal) | 76 | 520 | 76 | 570 | 0
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 1 | 148316 | A2411230 | 121058 | Cannonburys | 2 | 1100 | CFP | Weekend | W2018/5721841 | 2018-04-01 00:01 | 2018-04-02 04:00 | 1 day(s) 03:59 Hrs | CORE: Cat 02 - Rerail - Both Rails - 2yds | 3 | 1351 | 3 | 1353 | 2 | AWCAP.
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 1 | 148316 | A6290 | 121058 | Cannonburys | 4 | 1100 | CFP | Weekend | W2018/5721841 | 2018-04-01 00:01 | 2018-04-02 04:00 | 1 day(s) 03:59 Hrs | CORE: Cat 04 - Rerail, Resleeper (Steel) - 643yds | 3 | 1353 | 4 | 236 | 643 | Work category amended from Cat 16 to Cat 4, C/C ref: PLS-1819-252. AWCAP. | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 1 | 148316 | A7150 | 121058 | Cannonburys | 2 | 1100 | CFP | Weekend | W2018/5721841 | 2018-04-01 00:01 | 2018-04-02 04:00 | 1 day(s) 03:59 Hrs | CORE: Cat 02 - Rerail - Both Rails - 114yds | 4 | 236 | 4 | 350 | 114 | AWCAP.
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 1 | 145803 | A2863980 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5793704 | 2018-04-01 00:25 | 2018-04-01 08:00 | 0 day(s) 07:35 Hrs | CORE: 1st CW | 36 | 6 | 36 | 102 | 96
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 1 | 148309 | G2070 | 42200415 | New Cross Gate to Brockley (Dn) | 2 | 2200 | LBW | Weekend | W2018/5707694 | 2018-04-01 01:05 | 2018-04-02 04:00 | 1 day(s) 02:55 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 3 | 866 | 3 | 885 | 19
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 1 | 145803 | A2861860 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5686662 | 2018-04-01 08:00 | 2018-04-05 12:00 | 4 day(s) 04:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 378
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 2 | 148817 | G4T101160 | 52200510 | St Annes | 11 | 1100 | MLN1 | Weekend | W2018/5701735 | 2018-04-07 01:00 | 2018-04-09 05:00 | 2 day(s) 04:00 Hrs | CORE: 1st CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 116 | 552 | 116 | 892 | 340 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 2 | 148309 | A935820 | 42100518 | Folkestone Viaduct (Down) | 2 | 2100 | XTD | Weekend | W2018/5698945 | 2018-04-07 01:40 | 2018-04-09 04:00 | 2 day(s) 02:20 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 70 | 554 | 70 | 578 | 24 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 2 | 148309 | A935830 | 42100518 | Folkestone Viaduct (Down) | 2 | 2100 | XTD | Weekend | W2018/5698945 | 2018-04-07 01:40 | 2018-04-09 04:00 | 2 day(s) 02:20 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 70 | 871 | 70 | 885 | 14 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 2 | 148309 | G4T120010 | 42100518 | Folkestone Viaduct (Down) | 11 | 2100 | XTD | Weekend | W2018/5698945 | 2018-04-07 01:40 | 2018-04-09 04:00 | 2 day(s) 02:20 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 70 | 578 | 70 | 871 | 293 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 2 | 145803 | A2876160 | 31500717 | Mondragon Burn Dn | 16 | 2100 | SCM5 | Weekend | W2018/5686836 | 2018-04-07 02:00 | 2018-04-09 05:30 | 2 day(s) 03:30 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 235y) | 5 | 1109 | 5 | 1344 | 0 | Plant issues week 02 - delivered part skim dig (Cat 16: +30 yds) | CR
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 2 | 145803 | A307660 | 31500617 | Mondragon Burn Up | 14 | 1100 | SCM5 | Weekend | W2018/5686916 | 2018-04-07 02:00 | 2018-04-09 05:30 | 2 day(s) 03:30 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 266y) | 5 | 1079 | 5 | 1345 | 266 | Plant failures week 02 - PCP invoked (Cat 14: -234 yds) | CR
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 2 | 145803 | G4T511780 | 31500717 | Mondragon Burn Dn | 14 | 2100 | SCM5 | Weekend | W2018/5686836 | 2018-04-07 02:00 | 2018-04-09 05:30 | 2 day(s) 03:30 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 235y) | 5 | 1109 | 5 | 1344 | 235 | Plant issues week 02 - delivered part skim dig (Cat 14: -30 yds) | CR
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 2 | 145803 | A309640 | 32201317 | Lamington Viaduct | 11 | 2100 | WCM1 | Weekend | W2018/5662261 | 2018-04-07 11:30 | 2018-04-08 14:30 | 1 day(s) 03:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 398y) | 62 | 1303 | 62 | 1701 | 581
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 2 | 157791 | A401490 | 23502818 | Kilsby South Drain | 15aa | 1100 | LEC1 | Weekend | W2018/5665307 | 2018-04-07 22:10 | 2018-04-08 12:00 | 0 day(s) 13:50 Hrs | CORE: 1st CW Kilsby South Drain - Track Drainage Associated Renewal - CAT15aa - 160yds | 0 | 0 | 0 | 0 | 160
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 3 | 154530 | A10200 | 53430218 | Holywell Junction Up 1 | 2 | 1100 | CNH3 | Weekend | W2018/0000000 | 2018-04-14 00:01 | 2018-04-16 05:01 | 2 day(s) 05:00 Hrs | CORE: 1st CW (insert description) | 195 | 1077 | 195 | 1105 | 28 |  | APC
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 3 | 154530 | A10210 | 53430218 | Holywell Junction Up 1 | 16 | 1100 | CNH3 | Weekend | W2018/0000000 | 2018-04-14 00:01 | 2018-04-16 05:01 | 2 day(s) 05:00 Hrs | CORE: 1st CW (insert description) | 195 | 1105 | 195 | 1177 | 72 |  | APC
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 3 | 154530 | A11060 | 53430218 | Holywell Junction Up 1 | 2 | 1100 | CNH3 | Weekend | W2018/0000000 | 2018-04-14 00:01 | 2018-04-16 05:01 | 2 day(s) 05:00 Hrs | CORE: 1st CW (insert description) | 195 | 1177 | 195 | 1192 | 15 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 3 | 145803 | G4T388300 | 31500817 | Inchture Up | 13 | 1100 | SCM5 | Weekend | W2018/5687324 | 2018-04-14 01:00 | 2018-04-16 05:30 | 2 day(s) 04:30 Hrs | CORE: 1st CW (13 - Formation, Reballast, Resleeper - Trax (all non steel sleeper types) 236y) | 8 | 164 | 8 | 400 | 236
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 3 | 145803 | A371670 | 32201317 | Lamington Viaduct | 11 | 2100 | WCM1 | Weekend | W2018/5662352 | 2018-04-14 11:30 | 2018-04-15 14:30 | 1 day(s) 03:00 Hrs | CORE: 2nd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 398y) | 62 | 1701 | 63 | 339 | 215
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 3 | 157791 | A402350 | 23502818 | Kilsby South Drain | 15aa | 1100 | LEC1 | Weekend | W2018/5665308 | 2018-04-14 22:10 | 2018-04-15 12:00 | 0 day(s) 13:50 Hrs | CORE: 2nd CW kilsby South Drain - Track Drainage Associated Renewal - CAT15aa - 160yds | 0 | 0 | 0 | 0 | 160
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 3 | 145803 | A2864160 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5793768 | 2018-04-15 00:25 | 2018-04-15 08:00 | 0 day(s) 07:35 Hrs | CORE: 2nd CW | 36 | 102 | 36 | 198 | 96
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 4 | 148310 | G1000 | 43300314 | Hove Tunnel (Up) | 2 | 1100 | BLI1 | Weekend | W2018/5678348 | 2018-04-21 02:05 | 2018-04-23 04:00 | 2 day(s) 01:55 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 0 | 552 | 0 | 559 | 7 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 4 | 148310 | G1010 | 43300314 | Hove Tunnel (Up) | 2 | 1100 | BLI1 | Weekend | W2018/5678348 | 2018-04-21 02:05 | 2018-04-23 04:00 | 2 day(s) 01:55 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 0 | 901 | 0 | 912 | 11 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 4 | 148310 | G4T95170 | 43300314 | Hove Tunnel (Up) | 11 | 1100 | BLI1 | Weekend | W2018/5678348 | 2018-04-21 02:05 | 2018-04-23 04:00 | 2 day(s) 01:55 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 0 | 559 | 0 | 901 | 342 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 4 | 145803 | A2451270 | 32200217b | Kirkpatrick South | 14 | 2100 | WCM1 | Weekend | W2018/5686542 | 2018-04-21 11:30 | 2018-04-22 14:30 | 1 day(s) 03:00 Hrs | CORE: 1st CW (14 -Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 531y) | 12 | 649 | 12 | 1187 | 552 | Late hand back and ESR issues
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 4 | 148817 | A63050 | 51300214 | Bletchington North | 7 | 1100 | DCL | Weekend | W2018/5795028 | 2018-04-21 23:35 | 2018-04-23 04:45 | 1 day(s) 05:10 Hrs | CORE: 1/2 25yds | 71 | 550 | 71 | 575 | 25 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 4 | 148817 | A950160 | 51300214 | Bletchington North | 11 | 1100 | DCL | Weekend | W2018/5932732 | 2018-04-21 23:35 | 2018-04-23 04:45 | 1 day(s) 05:10 Hrs | CORE: 1/2 Reballast - Trax Cat:11 | 71 | 575 | 71 | 1611 | 643 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 4 | 145803 | A2864170 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5793769 | 2018-04-22 00:25 | 2018-04-22 08:00 | 0 day(s) 07:35 Hrs | CORE: 3rd CW | 36 | 198 | 36 | 294 | 96
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 4 | 145803 | A162130 | FD31100814A | Cowie 14/15 Shortfall | 11 | 2100 | SCM3 | Weekend | W2018/5680188 | 2018-04-22 00:30 | 2018-04-23 04:30 | 1 day(s) 04:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 376y) | 115 | 830 | 115 | 1206 | 376
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 5 | 154530 | A11240 | 53480517 | Holywell Junction Down | 2 | 2100 | CNH3 | Weekend | W2018/0000000 | 2018-04-27 23:00 | 2018-04-30 04:00 | 2 day(s) 05:00 Hrs | CORE: 1st CW (insert description) | 195 | 972 | 195 | 978 | 6 |  | APC
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 5 | 154530 | A11250 | 53480517 | Holywell Junction Down | 11 | 2100 | CNH3 | Weekend | W2018/0000000 | 2018-04-27 23:00 | 2018-04-30 04:00 | 2 day(s) 05:00 Hrs | CORE: 1st CW (insert description) | 195 | 978 | 196 | 75 | 857 |  | APC
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 5 | 154530 | A12100 | 53480517 | Holywell Junction Down | 16 | 2100 | CNH3 | Weekend | W2018/0000000 | 2018-04-27 23:00 | 2018-04-30 04:00 | 2 day(s) 05:00 Hrs | CORE: 1st CW (insert description) | 196 | 75 | 196 | 282 | 207 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 5 | 157792 | A2909970 | 21400716 | Hi Ho | 11 | 2100 | CGJ7 | Weekend | W2018/5840152 | 2018-04-28 21:25 | 2018-04-29 10:30 | 0 day(s) 13:05 Hrs | CORE: 1 of 2: Hi Ho - Rerail, Resleeper, Reballast - Trax - CAT11 - 197yds | 27 | 706 | 27 | 903 | 197
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 5 | 157791 | A375730 | 23507599 | Atherstone Station | 12 | 1100 | LEC2 | Weekend | W2018/5874749 | 2018-04-28 22:30 | 2018-04-29 09:00 | 0 day(s) 10:30 Hrs | CORE: 1 of 7 Reballast, Formation - Trax Cat12 - 150yds - 50mph TSR | 102 | 0 | 102 | 150 | 150
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 5 | 148817 | A63060 | 51300214 | Bletchington North | 11 | 1100 | DCL | Weekend | W2018/5932732 | 2018-04-28 23:35 | 2018-04-30 04:45 | 1 day(s) 05:10 Hrs | CORE: 2/2 Reballast - Trax Cat:11 | 71 | 575 | 71 | 1611 | 436 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 5 | 148817 | A950350 | 51300214 | Bletchington North | 7 | 1100 | DCL | Weekend | W2018/5932732 | 2018-04-28 23:35 | 2018-04-30 04:45 | 1 day(s) 05:10 Hrs | CORE: 2/2 25yds | 71 | 550 | 71 | 575 | 25 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 5 | 145803 | A2451260 | 32200217b | Kirkpatrick South | 14 | 2100 | WCM1 | Weekend | W2018/5686585 | 2018-04-29 00:01 | 2018-04-30 03:01 | 1 day(s) 03:00 Hrs | CORE: 2nd CW (14 -Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 531y) | 12 | 1187 | 12 | 1725 | 418 | Planned yardage cut due to week 04 issues
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 5 | 145803 | A2861980 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5686585 | 2018-04-29 00:01 | 2018-05-04 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 378
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 5 | 148310 | A1090 | 43400517df1 | Ifield | 14 | 1100 | TBH1 | Weekend | W2018/5716770 | 2018-04-29 00:01 | 2018-05-01 03:01 | 2 day(s) 03:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 31 | 673 | 31 | 1573 | 900 | SUS-1819-49 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 5 | 145803 | A2865820 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5793770 | 2018-04-29 00:25 | 2018-04-29 08:00 | 0 day(s) 07:35 Hrs | CORE: 4th CW | 36 | 294 | 36 | 390 | 96
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 5 | 148310 | G4T168500 | 43400517df1 | Ifield | 2 | 1100 | TBH1 | Weekend | W2018/5716770 | 2018-04-30 00:01 | 2018-05-01 03:01 | 1 day(s) 03:00 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 31 | 657 | 31 | 673 | 16 | SUS-1819-49 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 5 | 148310 | G4T168510 | 43400517df1 | Ifield | 2 | 1100 | TBH1 | Weekend | W2018/5716770 | 2018-04-30 00:01 | 2018-05-01 03:01 | 1 day(s) 03:00 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 31 | 1573 | 31 | 1588 | 15 | SUS-1819-49 | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 6 | 148273 | G4T158980 | 23100217 | Bletchley Station | 12 | 1100 | LEC1 | Weekend | W2018/5667201 | 2018-05-04 23:30 | 2018-05-08 06:00 | 3 day(s) 06:30 Hrs | CORE: 1st Core Bletchley Station 573 Yards of Cat 14 - TSR 50mph T137437 | 46 | 936 | 46 | 1509 | 573 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 6 | 148309 | A938240 | 42401912sf1 | Brockley to New Cross Gate | 11 | 1200 | LBW | Weekend | W2018/5725421 | 2018-05-05 01:05 | 2018-05-07 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 1652 | 4 | 874 | 982 | KENT-1819-59 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 6 | 148309 | G4T121610 | 42401912sf1 | Brockley to New Cross Gate | 2 | 1200 | LBW | Weekend | W2018/5725421 | 2018-05-05 01:05 | 2018-05-07 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 3 | 1642 | 3 | 1652 | 10 | KENT-1819-59 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 6 | 148309 | G4T121620 | 42401912sf1 | Brockley to New Cross Gate | 2 | 1200 | LBW | Weekend | W2018/5725421 | 2018-05-05 01:05 | 2018-05-07 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 4 | 874 | 4 | 890 | 16 | KENT-1819-59 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 6 | 148309 | G1070 | 42200811df4 | St Johns (18-19) | 11 | 1200 | XTD | Weekend | W2018/5716815 | 2018-05-05 01:20 | 2018-05-07 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 5 | 908 | 5 | 1190 | 282 | KENT-1718-31
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 6 | 148309 | G1910 | 42200811df4 | St Johns (18-19) | 2 | 1200 | XTD | Weekend | W2018/5716815 | 2018-05-05 01:20 | 2018-05-07 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 5 | 896 | 5 | 908 | 12 | KENT-1718-31
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 6 | 157792 | A2451300 | 21400716 | Hi Ho | 11 | 2100 | CGJ7 | Weekend | W2018/5840174 | 2018-05-05 21:25 | 2018-05-06 10:40 | 0 day(s) 13:15 Hrs | CORE: 2 of 2 CAT 11 - 197yds | 27 | 903 | 27 | 1100 | 197
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 6 | 145803 | A145300 | 32201218 | Braidwood North | 11 | 2100 | WCM1 | Weekend | W2018/5712838 | 2018-05-06 00:20 | 2018-05-07 04:20 | 1 day(s) 04:00 Hrs | CORE: 1st CW (Reballast, Resleeper, Rerail - Trax (11 - all non steel sleeper types) 571y) | 80 | 1614 | 81 | 435 | 581
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 6 | 145803 | A2865830 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5793771 | 2018-05-06 00:25 | 2018-05-06 08:00 | 0 day(s) 07:35 Hrs | CORE: 5th CW | 36 | 390 | 36 | 486 | 0 | Haulage cancelled week 06 - section proving | CR
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 6 | 148316 | A2411750 | 121016 | Royston | 11 | 2100 | SBR | Weekend | W2018/5762260 | 2018-05-06 01:40 | 2018-05-07 05:00 | 1 day(s) 03:20 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 365yds | 45 | 465 | 45 | 100 | 365 | AWCAP.
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 7 | 154530 | A12280 | 53430318 | Holywell Junction Up 2 | 2 | 1100 | CNH3 | Weekend | W2018/0000000 | 2018-05-11 23:01 | 2018-05-14 04:01 | 2 day(s) 05:00 Hrs | CORE: 1st CW (insert description) | 196 | 55 | 196 | 88 | 33
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 7 | 154530 | A12290 | 53430318 | Holywell Junction Up 2 | 2 | 1100 | CNH3 | Weekend | W2018/0000000 | 2018-05-11 23:01 | 2018-05-14 04:01 | 2 day(s) 05:00 Hrs | CORE: 3rd CW (insert description) | 196 | 185 | 196 | 201 | 16
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 7 | 154530 | A13140 | 53430318 | Holywell Junction Up 2 | 16 | 1100 | CNH3 | Weekend | W2018/0000000 | 2018-05-11 23:01 | 2018-05-14 04:01 | 2 day(s) 05:00 Hrs | CORE: 2nd CW (insert description) | 196 | 88 | 196 | 185 | 97
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 7 | 148813 | W2130 | BK0038df2 | Dorchester Jcn to Monkton & Came | 11 | 2100 | BML3 | Weekend | W2018/5740364 | 2018-05-12 00:30 | 2018-05-14 05:20 | 2 day(s) 04:50 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 Part 1 | 162 | 412 | 163 | 161 | 1511
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 7 | 148817 | A99480 | 51100811 | Acton Main Line Station DN | 14 | 2100 | MLN1 | Weekend | W2018/5755641 | 2018-05-12 01:00 | 2018-05-14 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/1 CW (Rerail, Resleeper, Reballast, Formation - Trax) Cat:14 | 4 | 293 | 4 | 616 | 323
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 7 | 148817 | G4T35500 | 51100811 | Acton Main Line Station DN | 11 | 2100 | MLN1 | Weekend | W2018/5755641 | 2018-05-12 01:00 | 2018-05-14 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/1 CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 4 | 198 | 4 | 293 | 95 | Site skimmed from half chord 860.Overrun track slues over 200mm NTC relay. 2m closure rail required.
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 7 | 148310 | A937630 | 43201210 | Norwood Jn - 1 Dn Slow | 11 | 2200 | LBW | Weekend | W2018/5728390 | 2018-05-12 01:15 | 2018-05-14 04:00 | 2 day(s) 02:45 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 9 | 580 | 9 | 761 | 181 | SUS-1819-34 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 7 | 148310 | G4T168520 | 43201210 | Norwood Jn - 1 Dn Slow | 2 | 2200 | LBW | Weekend | W2018/5728390 | 2018-05-12 01:15 | 2018-05-14 04:00 | 2 day(s) 02:45 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 9 | 569 | 9 | 580 | 11 | SUS-1819-34 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 7 | 148310 | G4T168530 | 43201210 | Norwood Jn - 1 Dn Slow | 2 | 2200 | LBW | Weekend | W2018/5728390 | 2018-05-12 01:15 | 2018-05-14 04:00 | 2 day(s) 02:45 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 9 | 761 | 9 | 762 | 1 | SUS-1819-34 | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 7 | 157792 | A28850 | 21400315OPs | Hi Ho Shortfall | 11 | 2100 | CGJ7 | Weekend | W2018/5840659 | 2018-05-12 21:25 | 2018-05-13 10:40 | 0 day(s) 13:15 Hrs | CORE: 1 of 2: Hi Ho Shortfall - Rerail, Resleeper, Reballast - Trax - CAT11 - 178yds | 26 | 1596 | 26 | 1774 | 178
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 7 | 157791 | A392280 | 23507599 | Atherstone Station | 12 | 1100 | LEC2 | Weekend | W2018/5874987 | 2018-05-12 22:30 | 2018-05-13 09:00 | 0 day(s) 10:30 Hrs | CORE: 2 of 7 Reballast, Formation - Trax Cat12 - 150yds - 50mph TSR | 102 | 150 | 102 | 300 | 150
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 7 | 145803 | A2865840 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5793772 | 2018-05-13 00:25 | 2018-05-13 08:00 | 0 day(s) 07:35 Hrs | CORE: 6th CW | 36 | 486 | 36 | 582 | 94
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 7 | 145803 | A305680 | 32201318 | Motherwell Platform 1 | 14 | 1100 | WCM2 | Weekend | W2018/5725760 | 2018-05-13 00:35 | 2018-05-14 05:00 | 1 day(s) 04:25 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 380y) | 89 | 287 | 89 | 667 | 320
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 7 | 148316 | A2412610 | 121016 | Royston | 11 | 2100 | SBR | Weekend | W2018/5762284 | 2018-05-13 01:40 | 2018-05-14 05:00 | 1 day(s) 03:20 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 365yds | 45 | 100 | 44 | 1495 | 365 | AWCAP.
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 8 | 157792 | A2451220 | 21400315OPs | Hi Ho Shortfall | 11 | 2100 | CGJ7 | Weekend | W2018/5840667 | 2018-05-19 21:25 | 2018-05-20 10:40 | 0 day(s) 13:15 Hrs | CORE: 2 Of 2 Hi Ho Shortfall - Rerail, Resleeper, Reballast - Trax - CAT11 - 175yds | 26 | 1774 | 27 | 191 | 177
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 8 | 157838 | A2484760 | 123021 | Sleaford East | 2 | 3100 | GRS2 | Weekend | W2018/5950488 | 2018-05-19 22:10 | 2018-05-21 06:20 | 1 day(s) 08:10 Hrs | CORE: CAT 02 - Rerail (Both rails) - 10yds | 120 | 1418 | 121 | 440 | 10 | AWCAP.
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 8 | 157838 | A46460 | 123021 | Sleaford East | 4 | 3100 | GRS2 | Weekend | W2018/5950488 | 2018-05-19 22:10 | 2018-05-21 06:20 | 1 day(s) 08:10 Hrs | CORE: CAT 4 - (Steel Sleeper Relay and Rerail) - 769yds | 120 | 1418 | 121 | 440 | 769 | AWCAP.
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 8 | 157791 | A401170 | 23507599 | Atherstone Station | 2 | 1100 | LEC2 | Weekend | W2018/5875147 | 2018-05-19 23:15 | 2018-05-20 09:00 | 0 day(s) 09:45 Hrs | CORE: 3 of 7 Re Rail - Trax Cat02 - 375yds - 50mph TSR | 102 | 0 | 102 | 375 | 375
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 8 | 148273 | A943530 | 23502618 | Crick Tunnel | 14 | 1100 | HNR | Weekend | W2018/5669118 | 2018-05-19 23:55 | 2018-05-21 05:00 | 1 day(s) 05:05 Hrs | CORE: 1 of 1 - Crick Tunnel -CAT14 - 370yds | 79 | 50 | 79 | 420 | 370 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 8 | 148273 | A944570 | 23502719 | Crick Tunnel-1 | 14 | 1100 | HNR | Weekend | W2018/5669118 | 2018-05-19 23:55 | 2018-05-21 05:00 | 1 day(s) 05:05 Hrs | CORE: 1 of 1 - Crick Tunnel -1 CAT14 - 213yds | 79 | 1025 | 79 | 1238 | 213 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 8 | 145803 | A2865850 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5793773 | 2018-05-20 00:25 | 2018-05-20 08:00 | 0 day(s) 07:35 Hrs | CORE: 7th CW | 36 | 582 | 36 | 678 | 87 | Late start due to points failure
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 8 | 145803 | A2447020 | 32201318 | Motherwell Platform 1 | 14 | 1100 | WCM2 | Weekend | W2018/5725880 | 2018-05-20 00:35 | 2018-05-21 05:00 | 1 day(s) 04:25 Hrs | CORE: 2nd CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 380y) | 89 | 667 | 89 | 1047 | 440
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 9 | 148817 | A937440 | 52101811df1 | Worcester Curve (18/19) | 11 | 3100 | WAH | Weekend | W2018/5783808 | 2018-05-26 00:55 | 2018-05-29 00:45 | 2 day(s) 23:50 Hrs | CORE: CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 120 | 1200 | 120 | 1406 | 206 | To remove CAT 02 and 44 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 9 | 148817 | A938480 | 52101611df1 | Worcester Foregate Street Dn (18/19) | 11 | 3101 | WAH | Weekend | W2018/5783808 | 2018-05-26 00:55 | 2018-05-29 00:45 | 2 day(s) 23:50 Hrs | CORE: 1/3 CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 120 | 1406 | 121 | 385 | 739
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 9 | 148817 | A949730 | 52101811df1 | Worcester Curve (18/19) | 2 | 3100 | WAH | Weekend | W2018/5783808 | 2018-05-26 00:55 | 2018-05-29 00:45 | 2 day(s) 23:50 Hrs | CORE: CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 120 | 1178 | 120 | 1200 | 22 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 9 | 148817 | A949740 | 52101811df1 | Worcester Curve (18/19) | 44A | 3100 | WAH | Weekend | W2018/5783808 | 2018-05-26 00:55 | 2018-05-29 00:45 | 2 day(s) 23:50 Hrs | CORE: CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 120 | 1178 | 120 | 1299 | 22 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 9 | 145831 | A2450640 | 21301413OPsf | Penrith South OP SF | 11 | 1100 | CGJ7 | Weekend | W2018/5719822 | 2018-05-26 11:50 | 2018-05-28 04:55 | 1 day(s) 17:05 Hrs | CORE: CAT 11 - 617yds, Install Guard Rail & Stress | 50 | 961 | 50 | 1578 | 617 | LNWNPL-1819-104 Item added to 1819 programme dated wk06
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 9 | 148287 | A2438770 | 133055 | Gooseholme | 11 | 1100 | NEC2 | Weekend | W2018/5763985 | 2018-05-26 22:20 | 2018-05-28 05:00 | 1 day(s) 06:40 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 646yds | 26 | 239 | 26 | 865 | 646 | AWCAP. PLN-1819-028.Approved Spec 1.104. GG 20/11/17 - Volumes phasing adjusted slightly to align with RF11 (Nov 2017) Business Plan Costing Tool. Totals are unchanged | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 9 | 145803 | A2861870 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5726242 | 2018-05-27 00:01 | 2018-06-01 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 378
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 9 | 145803 | A351160 | 110138a | Cobbinshaw | 14 | 2100 | ECA2 | Weekend | W2018/5726242 | 2018-05-27 00:01 | 2018-05-29 05:01 | 2 day(s) 05:00 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 1063y) | 83 | 274 | 83 | 1343 | 1069 | Change mileage to remove redundant welds (+6 yds) | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 9 | 148817 | W1050 | 51200716 | Taplow | 11 | 1100 | MLN1 | Weekend | W2018/5768720 | 2018-05-27 00:01 | 2018-05-28 06:16 | 1 day(s) 06:15 Hrs | CORE: 1/8 CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 22 | 697 | 23 | 462 | 223 | Cancelled resource sent to Worcester works | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 9 | 155890 | G5380 | 42600718 | Sevenoaks Tunnel Up - P2 (CORE 1) | 11 | 1100 | XTD | Weekend | W2018/5733715 | 2018-05-27 01:15 | 2018-05-28 05:14 | 1 day(s) 03:59 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 22 | 857 | 22 | 1500 | 643 | TON-K-1819-06 | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 9 | 155890 | G7460 | 42600818 | Sevenoaks Tunnel Up - P4 (CORE 1) | 11 | 1100 | XTD | Weekend | W2018/5733715 | 2018-05-27 02:29 | 2018-05-28 05:14 | 1 day(s) 02:45 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 22 | 1500 | 23 | 242 | 502 | TON-K-1819-06 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 10 | 153374 | A35770 | 114486LSI | Finedon-1 | 14 | 1100 | SPC3 | Weekend | W2018/5926620 | 2018-06-02 00:01 | 2018-06-04 04:40 | 2 day(s) 04:39 Hrs | CORE: Cat 14 - Rerail, Resleeper, Reballast, Formation - Trax - 446yds | 68 | 426 | 68 | 872 | 446 | Addition of 1718 shortfall site to 1819 workbank, C/C ref: PLS-1819-299. AWCAP. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 10 | 145803 | A186880 | 31200218 | Whitelaw | 11 | 2100 | ECA2 | Weekend | W2018/5726390 | 2018-06-02 00:05 | 2018-06-04 05:00 | 2 day(s) 04:55 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 1395y) | 95 | 1000 | 96 | 635 | 1395
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 10 | 148310 | G4T168460 | 43400910 | Dorking - Horsham Down Fast | 2 | 2100 | BTH3 | Weekend | W2018/5748847 | 2018-06-02 18:50 | 2018-06-04 05:45 | 1 day(s) 10:55 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 25 | 1638 | 25 | 1653 | 15 | SUS-1819-42 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 10 | 148310 | G4T168470 | 43400910 | Dorking - Horsham Down Fast | 2 | 2100 | BTH3 | Weekend | W2018/5748847 | 2018-06-02 18:50 | 2018-06-04 05:45 | 1 day(s) 10:55 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 26 | 291 | 26 | 307 | 16 | SUS-1819-42 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 10 | 148310 | G4T51070 | 43400910 | Dorking - Horsham Down Fast | 9 | 2100 | BTH3 | Weekend | W2018/5748847 | 2018-06-02 18:50 | 2018-06-04 05:45 | 1 day(s) 10:55 Hrs | CORE: 1/1 Reballast, Resleeper - Trax (all non steel sleeper types) Cat:09 | 25 | 1653 | 26 | 291 | 398 | SUS-1819-42 | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 10 | 148273 | G4T450040 | 23400714 | Harlesden | 15aa | 2100 | LEC1 | Weekend | W2018/5669555/5764522 | 2018-06-02 20:00 | 2018-06-04 05:25 | 1 day(s) 09:25 Hrs | CORE: 1st Core Harlesden 326 Yards of CAT15aa | 5 | 1303 | 5 | 1629 | 326
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 10 | 148287 | A2439630 | 133055 | Gooseholme | 11 | 1100 | NEC2 | Weekend | W2018/5765584 | 2018-06-02 22:20 | 2018-06-04 05:00 | 1 day(s) 06:40 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 605yds | 26 | 865 | 26 | 1490 | 605 | PLN-1819-028. AWCAP | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 10 | 148287 | A2484840 | 133055 | Gooseholme | 2 | 1100 | NEC2 | Weekend | W2018/5765584 | 2018-06-02 22:20 | 2018-06-04 05:00 | 1 day(s) 06:40 Hrs | CORE: CAT 02: Rerail (Both Rails) : 42yds | 26 | 1490 | 26 | 1532 | 42 | PLN-1819-028. AWCAP | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 10 | 148817 | W1060 | 51200716 | Taplow | 11 | 1100 | MLN1 | Weekend | W2018/5768815 | 2018-06-02 22:45 | 2018-06-04 05:00 | 1 day(s) 06:15 Hrs | CORE: 2/8 CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 22 | 697 | 23 | 462 | 223 | Cancelled late possession ammendments | APC
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 10 | 159264 | A1090 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980199 | 2018-06-02 23:50 | 2018-06-03 08:10 | 0 day(s) 08:20 Hrs | CORE: CW (Installation of Micropiles wk: 1 of 7 Sat/Sun) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 10 | 148309 | A937200 | 42600410df1sf1 | Church Settle | 9 | 1100 | TTH | Weekend | W2018/5781961 | 2018-06-03 01:15 | 2018-06-04 04:00 | 1 day(s) 02:45 Hrs | CORE: 1/1 Reballast, Resleeper - Trax (all non steel sleeper types) Cat:09 | 42 | 1692 | 43 | 202 | 270 | 17KEN Deferral | APC
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 10 | 159264 | A2160 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980236 | 2018-06-03 23:35 | 2018-06-04 05:10 | 0 day(s) 05:35 Hrs | CORE: CW (Installation of Micropiles wk: 1 of 7 Sun/Mon) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 10 | 148817 | A950560 | 51489811 | Pewsey Up | 11 | 1100 | BHL | Weekend | W2018/0000000 | 2018-06-04 04:30 | 2018-06-07 04:30 | 3 day(s) 00:00 Hrs | CORE: 1st CW (Rerail, Resleeper, Reballast-Trax | 75 | 803 | 75 | 1298 | 495
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 10 | 148817 | G4T432630 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5766019 | 2018-06-05 22:00 | 2018-06-06 06:00 | 0 day(s) 08:00 Hrs | CORE: 2nd CW (Rerail - Both Rails) Cat:02 T/F | 41 | 1044 | 43 | 683 | 236
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 10 | 148817 | G4T432610 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5766020 | 2018-06-06 22:00 | 2018-06-07 06:00 | 0 day(s) 08:00 Hrs | CORE: 2nd CW (Rerail - Both Rails) Cat:02 T/W | 41 | 1044 | 43 | 683 | 236
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 10 | 148817 | G4T432620 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5766021 | 2018-06-07 22:00 | 2018-06-08 06:00 | 0 day(s) 08:00 Hrs | CORE: 2nd CW (Rerail - Both Rails) Cat:02 W/T | 41 | 1044 | 43 | 683 | 236
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 11 | 145803 | A311620 | 31200118 | Ma Broons | 11 | 2100 | ECA2 | Weekend | W2018/5726438 | 2018-06-09 00:05 | 2018-06-11 05:00 | 2 day(s) 04:55 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 1061y) | 90 | 317 | 90 | 1378 | 1061
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 11 | 148309 | A2130 | 42500211sf2df1 | Cambria Spur | 16 | 2100 | LTC | Weekend | W2018/5760815 | 2018-06-09 01:00 | 2018-06-11 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Resleeper, Rerail, Scarify/Skim (all non steel sleeper types) Cat:16 | 3 | 788 | 3 | 1278 | 490 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 11 | 157792 | A2910880 | 21300117 | Plumpton | 2 | 1100 | CGJ7 | Weekend | W2018/5840997 | 2018-06-09 21:55 | 2018-06-11 07:29 | 1 day(s) 09:34 Hrs | CORE: 2 of 5: Plumpton - Rerail - Both Rails - CAT02 - 17yds | 56 | 193 | 56 | 206 | 13
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 11 | 157792 | A4210 | 21300117 | Plumpton | 11 | 1100 | CGJ7 | Weekend | W2018/5840997 | 2018-06-09 21:55 | 2018-06-10 23:35 | 1 day(s) 01:40 Hrs | CORE: 1 of 5: Plumpton - Rerail, Resleeper, Reballast - Trax - CAT11 - 163yds | 56 | 206 | 56 | 369 | 163
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 11 | 157791 | A401500 | 23502818 | Kilsby South Drain | 15aa | 1100 | LEC1 | Weekend | W2018/5670027 | 2018-06-09 22:10 | 2018-06-10 12:00 | 0 day(s) 13:50 Hrs | CORE: 3rd CW Kilsby South Drain - Track Drainage Associated Renewal - CAT15aa - 160yds | 0 | 0 | 0 | 0 | 160
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 11 | 148817 | W1070 | 51200716 | Taplow | 11 | 1100 | MLN1 | Weekend | W2018/5768816 | 2018-06-09 22:45 | 2018-06-11 05:00 | 1 day(s) 06:15 Hrs | CORE: 3/8 CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 22 | 697 | 23 | 462 | 223 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 11 | 148287 | A2240130 | 138005A | Warden AHB - Fourstones | 11 | 1100 | NEC2 | Weekend | W2018/5766980 | 2018-06-09 23:05 | 2018-06-11 05:00 | 1 day(s) 05:55 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 422yds, Weld x 6 & Uplift/Replace Fourstone Farm & Moss Cottages UWC | 23 | 1339 | 24 | 1 | 422 | AWCAP
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 11 | 159264 | A2040 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980325 | 2018-06-09 23:50 | 2018-06-10 08:10 | 0 day(s) 08:20 Hrs | CORE: CW (Installation of Micropiles Wk: 2 of 7 Sat/Sun) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 11 | 159264 | A2170 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980163 | 2018-06-10 23:35 | 2018-06-11 05:10 | 0 day(s) 05:35 Hrs | CORE: CW (Installation of Micropiles Wk: 2 of 7 Sun/Mon) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 12 | 148310 | G1550 | 43401718 | Crawley Up Shortfalls | 14 | 1100 | TBH1 | Weekend | W2018/5751148 | 2018-06-16 01:00 | 2018-06-18 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rearil - Trax (all non steel sleeper types) Cat:14 | 30 | 1716 | 31 | 673 | 717 | SUS-1819-60 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 12 | 148310 | G2520 | 43401718 | Crawley Up Shortfalls | 2 | 1100 | TBH1 | Weekend | W2018/5751148 | 2018-06-16 01:00 | 2018-06-18 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 30 | 1700 | 30 | 1716 | 16 | SUS-1819-60 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 12 | 148310 | G2530 | 43401718 | Crawley Up Shortfalls | 2 | 1100 | TBH1 | Weekend | W2018/5751148 | 2018-06-16 01:00 | 2018-06-18 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 31 | 673 | 31 | 689 | 16 | SUS-1819-60 | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 12 | 157792 | A2451350 | 21300117 | Plumpton | 11 | 1100 | CGJ7 | Weekend | W2018/5841046 | 2018-06-16 21:55 | 2018-06-17 10:45 | 0 day(s) 12:50 Hrs | CORE: 3 of 5: Plumpton - Rerail, Resleeper, Reballast - Trax - CAT11 - 180yds | 56 | 369 | 56 | 549 | 180
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 12 | 157791 | A402440 | 23502818 | Kilsby South Drain | 15aa | 1100 | LEC1 | Weekend | W2018/5670028 | 2018-06-16 22:10 | 2018-06-17 09:00 | 0 day(s) 10:50 Hrs | CORE: 4th CW Kilsby South Drain - Track Drainage Associated Renewal - CAT15aa - 160yds | 0 | 0 | 0 | 0 | 160
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 12 | 157791 | A392290 | 23507599 | Atherstone Station | 12 | 1100 | LEC2 | Weekend | W2018/5874988 | 2018-06-16 22:30 | 2018-06-17 09:00 | 0 day(s) 10:30 Hrs | CORE: 4 of 7 Reballast, Formation - Trax Cat12 - 150yds - 50mph TSR | 102 | 300 | 102 | 450 | 150
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 12 | 148817 | G4T80580 | 51200716 | Taplow | 11 | 1100 | MLN1 | Weekend | W2018/5768817 | 2018-06-16 22:45 | 2018-06-18 05:00 | 1 day(s) 06:15 Hrs | CORE: 4/8 CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 22 | 697 | 23 | 462 | 223 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 12 | 148287 | A2240990 | 138005A | Warden AHB - Fourstones | 11 | 1100 | NEC2 | Weekend | W2018/5767043 | 2018-06-16 23:05 | 2018-06-18 05:00 | 1 day(s) 05:55 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 422yds, Weld x 8, 50mph TSR Handback and stress | 24 | 1 | 24 | 423 | 422 | AWCAP
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 12 | 157838 | A2489250 | 123228 | Gainsborough 2 | 2 | N/A | SPD3 | Weekend | W2018/5936552 | 2018-06-16 23:15 | 2018-06-18 06:15 | 1 day(s) 07:00 Hrs | CORE: Cat 02 - Rerail (Both rails) - 394yds | 96 | 923 | 96 | 1317 | 394 | C/C ref: PLS-1819-299 to remove the 12yds island. AWCAP | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 12 | 157838 | A9510 | 123228 | Gainsborough 2 | 2 | N/A | SPD3 | Weekend | W2018/5936552 | 2018-06-16 23:15 | 2018-06-18 06:15 | 1 day(s) 07:00 Hrs | CORE: Cat 02 - Rerail (Both rails) - 985yds | 95 | 1498 | 96 | 723 | 985 | C/C ref: PLS-1819-299 to remove the 12yds island. AWCAP | APC
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 12 | 159264 | A2060 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980332 | 2018-06-16 23:50 | 2018-06-17 08:10 | 0 day(s) 08:20 Hrs | CORE: CW (Installation of Micropiles Wk: 3 of 7 Sat/Sun) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 12 | 145803 | A2872210 | FDNV32103117A | Kilwinning Up Cess Drain | 15ba | 1100 | LGS1 | Weekend | W2018/5796959 | 2018-06-17 00:01 | 2018-06-17 08:01 | 0 day(s) 08:00 Hrs | CORE: 1st CW | 26 | 1110 | 26 | 1210 | 103 | Pipe found in formation (-70 yds) | CR
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 12 | 145803 | A2452470 | FD120090 | Winchburgh Quarry | 11 | 1100 | EGM1 | Weekend | W2018/5735637 | 2018-06-17 00:15 | 2018-06-18 04:20 | 1 day(s) 04:05 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 581y) | 33 | 639 | 33 | 1220 | 581 | Core cancelled - Isolation issues (-581 yds) | CR
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 12 | 159264 | A2180 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980223 | 2018-06-17 23:35 | 2018-06-18 05:10 | 0 day(s) 05:35 Hrs | CORE: CW (Installation of Micropiles Wk: 3 of 7 Sun/Mon) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 13 | 157792 | A2909960 | 21300117 | Plumpton | 11 | 1100 | CGJ7 | Weekend | W2018/5841056 | 2018-06-23 21:55 | 2018-06-24 09:45 | 0 day(s) 11:50 Hrs | CORE: 4 of 5: Plumpton - Rerail, Resleeper, Reballast - Trax - CAT11 - 119yds | 56 | 549 | 56 | 668 | 119
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 13 | 157792 | A2910890 | 21300117 | Plumpton | 2 | 1100 | CGJ7 | Weekend | W2018/5841056 | 2018-06-23 21:55 | 2018-06-24 09:45 | 0 day(s) 11:50 Hrs | CORE: 5 of 5: Plumpton - Rerail - Both Rails - CAT02 - 20yds | 56 | 668 | 56 | 688 | 20
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 13 | 157791 | A392300 | 23507599 | Atherstone Station | 12 | 1100 | LEC2 | Weekend | W2018/5874989 | 2018-06-23 22:30 | 2018-06-24 09:00 | 0 day(s) 10:30 Hrs | CORE: 5 of 7 Reballast, Formation - Trax Cat12 - 150yds - 50mph TSR | 102 | 450 | 102 | 600 | 150
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 13 | 145803 | A2861880 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5735708 | 2018-06-24 00:01 | 2018-06-29 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 378
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 13 | 145803 | D4040 | FDNV32103117A | Kilwinning Up Cess Drain | 15ba | 1100 | LGS1 | Weekend | W2018/5796959 | 2018-06-24 00:01 | 2018-06-24 08:01 | 0 day(s) 08:00 Hrs | CORE: 2nd CW | 26 | 1110 | 26 | 1210 | 103
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 13 | 148309 | G4T10890 | 42200117 | Bexleyheath to Barnehurst | 11 | 2100 | BEX | Weekend | W2018/5760657 | 2018-06-24 00:01 | 2018-06-26 02:01 | 2 day(s) 02:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 13 | 760 | 14 | 0 | 1000 | TON-K-1819-02 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 13 | 148309 | G4T121520 | 42200117 | Bexleyheath to Barnehurst | 2 | 2100 | BEX | Weekend | W2018/5760657 | 2018-06-24 00:01 | 2018-06-26 02:01 | 2 day(s) 02:00 Hrs | CORE: 1/2 Re-Rail Both Rails types) Cat:02 | 14 | 0 | 14 | 18 | 18 | TON-K-1819-02 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 13 | 148817 | G4T432360 | 51200716 | Taplow | 11 | 1100 | MLN1 | Weekend | W2018/5768818 | 2018-06-24 00:01 | 2018-06-25 06:16 | 1 day(s) 06:15 Hrs | CORE: 5/8 CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 22 | 697 | 23 | 462 | 223 |  | APC
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 13 | 159264 | A2080 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980341 | 2018-06-24 00:01 | 2018-06-24 08:21 | 0 day(s) 08:20 Hrs | CORE: CW (Installation of Micropiles Wk: 4 of 7 Sat/Sun) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 13 | 153374 | A6290 | 114487LSI | Finedon | 12 | 1100 | SPC3 | Weekend | W2018/5809291 | 2018-06-24 00:01 | 2018-06-25 07:46 | 1 day(s) 07:45 Hrs | CORE: Cat 12 - Formation, Reballast - Traxcavate - 372yds | 69 | 64 | 69 | 436 | 372 | Possession times TBC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 13 | 145803 | A2453440 | FD120090 | Winchburgh Quarry | 11 | 1100 | EGM1 | Weekend | W2018/5735708 | 2018-06-24 00:15 | 2018-06-25 04:20 | 1 day(s) 04:05 Hrs | CORE: 2nd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 581y) | 33 | 1220 | 34 | 41 | 581
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 13 | 159264 | A2190 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980224 | 2018-06-24 23:35 | 2018-06-25 05:10 | 0 day(s) 05:35 Hrs | CORE: CW (Installation of Micropiles Wk: 4 of 7 Sun/Mon) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 14 | 148324 | A929090 | 41101310 | East Ham Up | 2 | 1100 | FSS1 | Weekend | W2018/5773273 | 2018-06-30 01:25 | 2018-07-02 04:00 | 2 day(s) 02:35 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 6 | 5 | 6 | 7 | 2 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 14 | 148324 | G4T377840 | 41101310 | East Ham Up | 11 | 1100 | FSS1 | Weekend | W2018/5773273 | 2018-06-30 01:25 | 2018-07-02 04:00 | 2 day(s) 02:35 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 5 | 1015 | 6 | 5 | 750 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 14 | 148324 | G4T387550 | 41101310 | East Ham Up | 2 | 1100 | FSS1 | Weekend | W2018/5773273 | 2018-06-30 01:25 | 2018-07-02 04:00 | 2 day(s) 02:35 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 5 | 943 | 5 | 1015 | 72 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 14 | 157791 | A392310 | 23507599 | Atherstone Station | 12 | 1100 | LEC2 | Weekend | W2018/5874990 | 2018-06-30 22:30 | 2018-07-01 09:00 | 0 day(s) 10:30 Hrs | CORE: 6 of 7 Reballast, Formation - Trax Cat12 - 150yds - 50mph TSR | 102 | 600 | 102 | 750 | 150
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 14 | 148817 | G4T432370 | 51200716 | Taplow | 11 | 1100 | MLN1 | Weekend | W2018/5768819 | 2018-06-30 22:45 | 2018-07-02 05:00 | 1 day(s) 06:15 Hrs | CORE: 6/8 CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 22 | 697 | 23 | 462 | 223 |  | APC
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 14 | 159264 | A2100 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980346 | 2018-06-30 23:50 | 2018-07-01 08:10 | 0 day(s) 08:20 Hrs | CORE: CW (Installation of Micropiles Wk: 5 of 7 Sat/Sun) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 14 | 145803 | D4050 | FDNV32103117A | Kilwinning Up Cess Drain | 15ba | 1100 | LGS1 | Weekend | W2018/5796959 | 2018-07-01 00:01 | 2018-07-01 08:01 | 0 day(s) 08:00 Hrs | CORE: 3rd CW | 26 | 1110 | 26 | 1210 | 105
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 18/19 | 14 | 145831 | A2465680 | COT22500617 | Deansgate Jn - Skelton Jn Up | 11 | 1100 | SJD | Weekend | W2018/6013027 | 2018-07-01 00:01 | 2018-07-02 04:05 | 1 day(s) 04:04 Hrs | CORE: 1 of 1: CAT11 Rerail, Resleeper, Reballast (Trax) - 661Yds | 0 | 9 | 0 | 670 | 661 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 14 | 145803 | A2451430 | 31100516b | Cockmuir | 11 | 2100 | EGM1 | Weekend | W2018/5735775 | 2018-07-01 00:25 | 2018-07-02 04:30 | 1 day(s) 04:05 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 308y) | 33 | 542 | 33 | 850 | 308
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 14 | 145803 | A2451440 | 31100516b | Cockmuir | 14 | 2100 | EGM1 | Weekend | W2018/5735775 | 2018-07-01 00:25 | 2018-07-02 05:25 | 1 day(s) 05:00 Hrs | CORE: 2nd CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 245y) | 33 | 850 | 33 | 1095 | 245
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 14 | 159264 | A2200 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980225 | 2018-07-01 23:35 | 2018-07-02 05:10 | 0 day(s) 05:35 Hrs | CORE: CW (Installation of Micropiles Wk: 5 of 7 Sun/Mon) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 14 | 148310 | G4T169560 | 43400517df1 | Ifield | 14 | 1100 | TBH1 | Weekend |  | 2018-07-06 03:01 | 2018-07-06 06:00 | 0 day(s) 02:59 Hrs | CORE: Contractor Variation | 31 | 673 | 31 | 1573 | 0 | SUS-1819-49 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 14 | 148309 | G4T122110 | 42401912sf1 | Brockley to New Cross Gate | 11 | 1200 | LBW | Weekend |  | 2018-07-06 04:00 | 2018-07-06 12:00 | 0 day(s) 08:00 Hrs | CORE: Contractor Variations | 3 | 1652 | 4 | 874 | 0 | KENT-1819-59 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 14 | 148310 | G4T169580 | 43401718 | Crawley Up Shortfalls | 14 | 1100 | TBH1 | Weekend |  | 2018-07-06 04:00 | 2018-07-06 08:00 | 0 day(s) 04:00 Hrs | CORE: Contractor Variances | 30 | 1716 | 31 | 673 | 0 | SUS-1819-60 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 14 | 148310 | G4T169570 | 43400910 | Dorking - Horsham Down Fast | 9 | 2100 | BTH3 | Weekend |  | 2018-07-06 05:45 | 2018-07-06 12:45 | 0 day(s) 07:00 Hrs | CORE: Contractor Variances | 0 | 0 | 0 | 0 | 0 | SUS-1819-42 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 15 | 148310 | G4T3050 | 43201218 | Streatham & Leigham Tunnels | 11 | 2100 | BTH1 | Weekend | W2018/5797724 | 2018-07-07 01:05 | 2018-07-09 05:00 | 2 day(s) 03:55 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 6 | 1365 | 7 | 457 | 852
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 15 | 148310 | S1000 | 43201218 | Streatham & Leigham Tunnels | 2 | 2100 | BTH1 | Weekend | W2018/5797724 | 2018-07-07 01:05 | 2018-07-09 05:00 | 2 day(s) 03:55 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 6 | 1352 | 6 | 1365 | 13
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 15 | 148310 | S1010 | 43201218 | Streatham & Leigham Tunnels | 2 | 2100 | BTH1 | Weekend | W2018/5797724 | 2018-07-07 01:05 | 2018-07-09 05:00 | 2 day(s) 03:55 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 7 | 457 | 7 | 468 | 11
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 15 | 157792 | A2852750 | 21301313 | Penrith Goods Loop | 11 | 2200 | CGJ7 | Weekend | W2018/5841518 | 2018-07-07 21:55 | 2018-07-08 09:45 | 0 day(s) 11:50 Hrs | CORE: 1 of 7: CAT 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 147yds | 50 | 591 | 50 | 738 | 147 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 15 | 157791 | A328930 | 23510499 | Bridge 18 | 14 | 1200 | LEC2 | Weekend | W2018/5842852 | 2018-07-07 22:15 | 2018-07-08 12:00 | 0 day(s) 13:45 Hrs | CORE: 1 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 127yds - 50mph TSR | 88 | 1480 | 88 | 1597 | 127
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 15 | 157791 | A403040 | 23507599 | Atherstone Station | 2 | 1100 | LEC2 | Weekend | W2018/5875148 | 2018-07-07 22:30 | 2018-07-08 09:00 | 0 day(s) 10:30 Hrs | CORE: 7 of 7 Re Rail - Trax Cat02 - 375yds - 50mph TSR | 102 | 375 | 102 | 750 | 375
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 15 | 148817 | G4T432380 | 51200716 | Taplow | 11 | 1100 | MLN1 | Weekend | W2018/5768820 | 2018-07-07 22:45 | 2018-07-09 05:00 | 1 day(s) 06:15 Hrs | CORE: 7/8 CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 22 | 697 | 23 | 462 | 231 |  | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 15 | 148320 | A33330 | 114455 | Cricklewood | 11 | 1100 | SPC1 | Weekend | W2018/5809317 | 2018-07-07 22:45 | 2018-07-09 06:00 | 1 day(s) 07:15 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 274yds | 4 | 1588 | 5 | 102 | 274 | PLS-1819-216 Spec Change - Original Spec mileage included removal of S&C timbers - not required & Addition 3yds of CAT 02. Possession times TBC. | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 15 | 148320 | A34350 | 114455 | Cricklewood | 2 | 1100 | SPC1 | Weekend | W2018/5809317 | 2018-07-07 22:45 | 2018-07-09 06:00 | 1 day(s) 07:15 Hrs | CORE: Cat 02 - Rerail - Both Rails - 3yds | 4 | 1585 | 5 | 1588 | 3 | PLS-1819-216 Spec Change - Original Spec mileage included removal of S&C timbers - not required & Addition 3yds of CAT 02. Possession times TBC. | APC
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 15 | 159264 | A2120 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980353 | 2018-07-07 23:50 | 2018-07-08 08:10 | 0 day(s) 08:20 Hrs | CORE: CW (Installation of Micropiles Wk: 6 of 7 Sat/Sun) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 15 | 145803 | A2452290 | 31100516b | Cockmuir | 14 | 2100 | EGM1 | Weekend | W2018/5735827 | 2018-07-08 00:25 | 2018-07-09 04:30 | 1 day(s) 04:05 Hrs | CORE: 3rd CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 245y) | 33 | 1095 | 33 | 1340 | 245
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 15 | 145803 | A2453500 | 31100516b | Cockmuir | 11 | 2100 | EGM1 | Weekend | W2018/5735827 | 2018-07-08 00:25 | 2018-07-09 05:25 | 1 day(s) 05:00 Hrs | CORE: 4th CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 364y) | 33 | 1340 | 33 | 1704 | 364
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 15 | 159264 | A2210 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980226 | 2018-07-08 23:35 | 2018-07-09 05:10 | 0 day(s) 05:35 Hrs | CORE: CW (Installation of Micropiles Wk: 6 of 7 Sun/Mon) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 16 | 145803 | A2447140 | 32101317 | Bank Junction Down | 14 | 2100 | GSW | Blockade | W2018/5807916 | 2018-07-14 01:00 | 2018-07-19 00:30 | 4 day(s) 23:30 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 1599y) | 53 | 161 | 54 | 0 | 1599
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 16 | 155890 | G4340 | 42600918 | Sevenoaks Tunnel Up - P5 (CORE 2) | 11 | 1100 | XTD | Weekend | W2018/5762247 | 2018-07-14 01:15 | 2018-07-16 04:00 | 2 day(s) 02:45 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 23 | 950 | 23 | 1122 | 172 | KENT-1819-41
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 16 | 157792 | A2903690 | 21301313 | Penrith Goods Loop | 11 | 2200 | CGJ7 | Weekend | W2018/5841538 | 2018-07-14 21:55 | 2018-07-15 09:45 | 0 day(s) 11:50 Hrs | CORE: 2 of 7: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 144yds | 50 | 738 | 50 | 882 | 144 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 16 | 157791 | A392340 | 23510499 | Bridge 18 | 14 | 1200 | LEC2 | Weekend | W2018/5842853 | 2018-07-14 22:15 | 2018-07-15 09:00 | 0 day(s) 10:45 Hrs | CORE: 2 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 127yds - 50mph TSR | 88 | 1597 | 88 | 1724 | 127
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 16 | 148817 | W1080 | 51200716 | Taplow | 7 | 1100 | MLN1 | Weekend | W2018/5768821 | 2018-07-14 22:45 | 2018-07-16 05:00 | 1 day(s) 06:15 Hrs | CORE: 8/8 CW (CAT 07 Reballast - Trax) | 22 | 439 | 22 | 697 | 258 |  | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 16 | 148320 | A34300 | 114455 | Cricklewood | 11 | 1100 | SPC1 | Weekend | W2018/5809320 | 2018-07-14 22:45 | 2018-07-16 05:50 | 1 day(s) 07:05 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 274yds | 5 | 102 | 5 | 376 | 274 | PLS-1819-216 Spec Change - Original Spec mileage included removal of S&C timbers - not required & Addition 3yds of CAT 02. Possession times TBC. | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 16 | 157838 | A10550 | 123221 | Cowdale Dn | 2 | 2100 | SPD3 | Weekend | W2018/6045284 | 2018-07-14 23:10 | 2018-07-15 09:25 | 0 day(s) 10:15 Hrs | CORE: Cat 02 (Rerail - Both rails) - 219yds | 91 | 667 | 91 | 886 | 219 | Possession times TBC
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 16 | 159264 | A2140 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980358 | 2018-07-14 23:50 | 2018-07-15 08:10 | 0 day(s) 08:20 Hrs | CORE: CW (Installation of Micropiles Wk: 7 of 7 Sat/Sun) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 16 | 148309 | G4T121510 | 42200117 | Bexleyheath to Barnehurst | 2 | 2100 | BEX | Weekend | W2018/5791338 | 2018-07-15 01:15 | 2018-07-16 02:55 | 1 day(s) 01:40 Hrs | CORE: 2/2 Re-Rail Both Rails types) Cat:02 | 13 | 427 | 13 | 440 | 13 | TON-K-1819-02 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 16 | 148309 | K7400 | 42200117 | Bexleyheath to Barnehurst | 11 | 2100 | BEX | Weekend | W2018/5791338 | 2018-07-15 01:15 | 2018-07-16 02:55 | 1 day(s) 01:40 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 13 | 440 | 13 | 760 | 320 | TON-K-1819-02 | APC
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 16 | 159264 | A2220 | BES | Brind Embankment Stability | EM001 | 1100 | HUL1 | Weekend | W2018/5980227 | 2018-07-15 23:35 | 2018-07-16 05:10 | 0 day(s) 05:35 Hrs | CORE: CW (Installation of Micropiles Wk: 7 of 7 Sun/Mon) | 0 | 0 | 0 | 0 | 0 | Proposed in PPS
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 17 | 145803 | A308650 | FD32101615 | Old Cumnock | 11 | 1100 | GSW | Blockade | W2018/5810588 | 2018-07-17 23:00 | 2018-07-21 18:00 | 3 day(s) 19:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 950y) | 48 | 1560 | 49 | 750 | 0 | Defer due to weak viaduct (-950 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 17 | 145803 | A351230 | FD32101615 | Old Cumnock | 14 | 1100 | GSW | Blockade | W2018/5810588 | 2018-07-17 23:00 | 2018-07-21 18:00 | 3 day(s) 19:00 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 100y) | 49 | 750 | 49 | 850 | 0
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 17 | 145803 | A352240 | FD32101615 | Old Cumnock | 11 | 1100 | GSW | Blockade | W2018/5810588 | 2018-07-17 23:00 | 2018-07-21 18:00 | 3 day(s) 19:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 366y) | 49 | 869 | 50 | 52 | 943
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 17 | 145803 | A166090 | 32101418 | Darnlaw | 11 | 2100 | GSW | Weekend | W2018/5820812 | 2018-07-21 00:01 | 2018-07-23 05:00 | 2 day(s) 04:59 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 738y) | 44 | 1737 | 45 | 715 | 738
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 17 | 148309 | G2110 | 42201702df1 | West Wickham | 2 | 1100 | LCH | Weekend | W2018/5803295 | 2018-07-21 01:20 | 2018-07-23 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 13 | 127 | 13 | 146 | 19 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 17 | 148309 | K5280 | 42201702df1 | West Wickham | 11 | 1100 | LCH | Weekend | W2018/5803295 | 2018-07-21 01:20 | 2018-07-23 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 13 | 146 | 13 | 620 | 474 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 17 | 148273 | G4T491300 | 23400714 | Harlesden | 15aa | 2100 | LEC1 | Weekend | W2018/5741182 | 2018-07-21 20:00 | 2018-07-23 04:00 | 1 day(s) 08:00 Hrs | CORE: 2nd Core Harlesden 217 Yards of CAT15aa - Contingency Core | 5 | 1303 | 6 | 1629 | 0
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 17 | 157792 | A2903700 | 21301313 | Penrith Goods Loop | 11 | 2200 | CGJ7 | Weekend | W2018/5841543 | 2018-07-21 21:55 | 2018-07-22 09:45 | 0 day(s) 11:50 Hrs | CORE: 3 of 7: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 140yds | 50 | 882 | 50 | 1022 | 140 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 17 | 157839 | A5350 | 135093 | Knottingley Depot to Stn | 11 | 1100 | WAG1 | Weekend | W2018/5897765 | 2018-07-21 23:45 | 2018-07-22 20:45 | 0 day(s) 21:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 353yds | 58 | 762 | 58 | 1115 | 353
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 17 | 145803 | A2861890 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5820812 | 2018-07-22 00:01 | 2018-07-27 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 378
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 17 | 148817 | A943190 | 51400419 | Bedwyn | 14 | 1100 | BHL | Blockade | W2018/6071072 | 2018-07-22 22:00 | 2018-07-27 23:00 | 5 day(s) 01:00 Hrs | CORE: 1st CW (CAT 14 Rerail, Resleeper, Reballast, Formation-Trax) | 65 | 748 | 65 | 1177 | 429 | MC-P03-05 Schedule change | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 18 | 148309 | G2120 | 42201702df1 | West Wickham | 11 | 1100 | LCH | Weekend | W2018/5803306 | 2018-07-28 01:20 | 2018-07-30 04:00 | 2 day(s) 02:40 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 13 | 1094 | 13 | 1105 | 11 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 18 | 148309 | K6140 | 42201702df1 | West Wickham | 11 | 1100 | LCH | Weekend | W2018/5803306 | 2018-07-28 01:20 | 2018-07-30 04:00 | 2 day(s) 02:40 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 13 | 620 | 13 | 1094 | 474 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 18 | 148324 | A224820 | 41600112df1 | Bethnal Green - Cambridge Heath (shortfall) | 9 | 1100 | BGK | Weekend | W2018/5790886 | 2018-07-28 02:35 | 2018-07-30 03:15 | 2 day(s) 00:40 Hrs | CORE: 1/1 Reballast, Resleeper - Trax (all non steel sleeper types) Cat:09 | 1 | 1049 | 1 | 1060 | 11
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 18 | 148324 | G4T20830 | 41600112df1 | Bethnal Green - Cambridge Heath (shortfall) | 11 | 1100 | BGK | Weekend | W2018/5790886 | 2018-07-28 02:35 | 2018-07-30 03:15 | 2 day(s) 00:40 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 1 | 1060 | 1 | 1615 | 555
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 18 | 157792 | A2903710 | 21301313 | Penrith Goods Loop | 11 | 2200 | CGJ7 | Weekend | W2018/5841554 | 2018-07-28 21:55 | 2018-07-29 10:45 | 0 day(s) 12:50 Hrs | CORE: 4 of 7: Cat 11 - 140yds includeS Weld & Stressing and S&T Testing | 50 | 1022 | 50 | 1162 | 140 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 18 | 148287 | A2450560 | 133047 | Bebside LC | 11 | 1100 | EJM | Weekend | W2018/5818632 | 2018-07-28 22:00 | 2018-07-30 05:30 | 1 day(s) 07:30 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 694yds, Weld x 10 & uplift/reinstate Bebside LC | 13 | 1758 | 14 | 692 | 694
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 18 | 148287 | A2455670 | 133047 | Bebside LC | 2 | 1100 | EJM | Weekend | W2018/5818632 | 2018-07-28 22:00 | 2018-07-30 05:30 | 1 day(s) 07:30 Hrs | CORE: CAT02: Rerail (Both Rails) : 58yds | 14 | 1386 | 14 | 1444 | 58
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 18 | 157791 | A392350 | 23510499 | Bridge 18 | 14 | 1200 | LEC2 | Weekend | W2018/5842854 | 2018-07-28 22:15 | 2018-07-29 09:00 | 0 day(s) 10:45 Hrs | CORE: 3 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 128yds - 50mph TSR | 88 | 1724 | 89 | 102 | 128
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 18 | 157838 | A5350 | 123227 | Saxilby Up 3 | 2 | 1100 | SPD3 | Weekend | W2018/6045285 | 2018-07-28 23:25 | 2018-07-29 09:25 | 0 day(s) 10:00 Hrs | CORE: Cat 02 - Rerail (Both rails) - 415yds | 88 | 1549 | 89 | 204 | 415 | Possession times TBC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 18 | 145803 | A180940 | 32201017 | Kirkconnel Station | 14 | 1100 | GSW | Weekend | W2018/5766892 | 2018-07-29 00:01 | 2018-07-30 05:00 | 1 day(s) 04:59 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 462y) | 62 | 458 | 62 | 920 | 462
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 18 | 145803 | A2865860 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5827824 | 2018-07-29 00:25 | 2018-07-29 08:00 | 0 day(s) 07:35 Hrs | CORE: 8th CW | 36 | 678 | 36 | 774 | 96
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 19 | 148817 | A944050 | 51400419 | Bedwyn | 14 | 1100 | BHL | Blockade | W2018/6071072 | 2018-08-03 23:00 | 2018-08-09 | 5 day(s) 01:00 Hrs | CORE: 2nd CW (CAT 14 Rerail, Resleeper, Reballast, Formation-Trax) | 66 | 374 | 66 | 849 | 475 | MC-P03-05 Schedule change | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 19 | 148324 | K7440 | 41400311 | Saxmundham Dn | 16 | 2100 | ESK | Weekend | W2018/5806015 | 2018-08-03 23:15 | 2018-08-06 05:00 | 2 day(s) 05:45 Hrs | CORE: Resleeper, Rerail - Scarify/Skim (all non steel sleeper types) Cat:16 | 91 | 419 | 91 | 446 | 27
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 19 | 148324 | K7450 | 41400311 | Saxmundham Dn | 4 | 2100 | ESK | Weekend | W2018/5806015 | 2018-08-03 23:15 | 2018-08-06 05:00 | 2 day(s) 05:45 Hrs | CORE: Rerail, Resleeper (Steel) Cat:04 | 91 | 446 | 92 | 474 | 1788
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 19 | 148324 | K7460 | 41400311 | Saxmundham Dn | 16 | 2100 | ESK | Weekend | W2018/5806015 | 2018-08-03 23:15 | 2018-08-06 05:00 | 2 day(s) 05:45 Hrs | CORE: Resleeper, Rerail, Scarify/Skim (all non steel sleeper types) Cat:16 | 92 | 474 | 92 | 488 | 14
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 19 | 148324 | K7470 | 41400311 | Saxmundham Dn | 2 | 2100 | ESK | Weekend | W2018/5806015 | 2018-08-03 23:15 | 2018-08-06 05:00 | 2 day(s) 05:45 Hrs | CORE: Rerail - Both Rails Cat:02 | 92 | 488 | 92 | 490 | 2
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 19 | 157792 | A2903720 | 21301313 | Penrith Goods Loop | 11 | 2200 | CGJ7 | Weekend | W2018/5841559 | 2018-08-04 21:55 | 2018-08-05 10:45 | 0 day(s) 12:50 Hrs | CORE: 5 of 7: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 140yds | 50 | 1162 | 50 | 1302 | 140 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 19 | 148287 | A2451420 | 133047 | Bebside LC | 11 | 1100 | EJM | Weekend | W2018/5818687 | 2018-08-04 22:00 | 2018-08-06 05:30 | 1 day(s) 07:30 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 694yds, 10yds Transition Rails, Weld x 10 & uplift/reinstate CM FC | 14 | 692 | 14 | 1386 | 694
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 19 | 148273 | G4T335520 | 23500518 | Kilsby Tunnel Down Refurb | 16 | 2100 | LEC1 | Weekend | W2018/5740006 | 2018-08-04 22:10 | 2018-08-05 12:00 | 0 day(s) 13:50 Hrs | CORE: 1st Core Kilsby Tunnel Down Refurb 200 Yards of CAT16 | 77 | 0 | 77 | 200 | 200 | Approved Change Control D63 - Remove from 18/19 and Add to unassigned. LP 02.06.16. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 19 | 145803 | A176980 | 32101218 | Hurlford Down | 11 | 2100 | GSW | Weekend | W2018/5766931 | 2018-08-04 23:05 | 2018-08-06 06:30 | 1 day(s) 07:25 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 460y) | 35 | 1003 | 35 | 1513 | 510 | Remove island of timber sleepers (S&C plain lined) (+36 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 19 | 145803 | A2865870 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5827825 | 2018-08-05 00:25 | 2018-08-05 08:00 | 0 day(s) 07:35 Hrs | CORE: 9th CW | 36 | 774 | 36 | 870 | 96
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 20 | 157166 | A3390 | A18DN | A18 Althorpe Bridge Dn | 31 | 2100 | DOW | Weekend | W2018/0000000 | 2018-08-11 20:45 | 2018-08-12 12:45 | 0 day(s) 16:00 Hrs | CORE: CAT31: Ballast - Track Lift : 548yds | 19 | 590 | 19 | 42 | 548 | Not in PPS
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 20 | 157792 | A2903730 | 21301313 | Penrith Goods Loop | 11 | 2200 | CGJ7 | Weekend | W2018/5841592 | 2018-08-11 21:55 | 2018-08-12 10:45 | 0 day(s) 12:50 Hrs | CORE: 6 of 7: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 259yds | 50 | 1302 | 50 | 1561 | 259 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 20 | 157791 | A392360 | 23510499 | Bridge 18 | 14 | 1200 | LEC2 | Weekend | W2018/5842855 | 2018-08-11 22:15 | 2018-08-12 12:00 | 0 day(s) 13:45 Hrs | CORE: 4 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 128yds - 50mph TSR | 89 | 102 | 89 | 230 | 128
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 20 | 145803 | A169060 | 32202819 | Gateside | 12 | 1100 | GSW | Weekend | W2018/5767000 | 2018-08-12 00:01 | 2018-08-13 06:00 | 1 day(s) 05:59 Hrs | CORE: 1st CW (12 - Formation, Reballast - Traxcavate 324y) | 64 | 300 | 64 | 624 | 324
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 20 | 145803 | A2457500 | 32202819 | Gateside | 14 | 1100 | GSW | Weekend | W2018/5767000 | 2018-08-12 00:01 | 2018-08-13 06:01 | 1 day(s) 06:00 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 76y) | 64 | 624 | 64 | 700 | 76
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 20 | 145803 | A2865880 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5828040 | 2018-08-12 00:25 | 2018-08-12 08:00 | 0 day(s) 07:35 Hrs | CORE: 10th CW | 36 | 870 | 36 | 966 | 96
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 21 | 148817 | A943200 | 51400419 | Bedwyn | 14 | 1100 | BHL | Blockade | W2018/6071072 | 2018-08-16 | 2018-08-21 01:00 | 5 day(s) 01:00 Hrs | CORE: 3rd CW ((CAT 14 Rerail, Resleeper, Reballast, Formation-Trax) | 66 | 1122 | 67 | 18 | 818 | MC-P03-05 Schedule change | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 21 | 155890 | G8500 | 42601018 | Sevenoaks Tunnel Down - P1 (CORE 3 & 4) | 11 | 1100 | XTD | Weekend | W2018/5762254 | 2018-08-18 01:20 | 2018-08-20 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 22 | 780 | 22 | 1380 | 600 | TON-K-1819-03 | APC
N/A | Plain Line | ENHANCE | London North East | Carillion Rail | Doncaster | 18/19 | 21 | 157166 | A4430 | A18UP | A18 Althorpe Bridge Up | 31 | 1100 | DOW | Weekend | W2018/0000000 | 2018-08-18 20:45 | 2018-08-19 12:45 | 0 day(s) 16:00 Hrs | CORE: CAT31: Ballast - Track Lift : 548yds | 19 | 590 | 19 | 42 | 548 | Not in PPS
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 21 | 157792 | A2909930 | 21301313 | Penrith Goods Loop | 11 | 2200 | CGJ7 | Weekend | W2018/5868713 | 2018-08-18 21:55 | 2018-08-19 10:45 | 0 day(s) 12:50 Hrs | CORE: 7 of 7: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 271yds | 50 | 1561 | 51 | 72 | 271 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 21 | 157791 | A324770 | 23501319 | COT High Oaks Junction | 14 | 1200 | LEC2 | Weekend | W2018/5853594 | 2018-08-18 22:15 | 2018-08-19 12:00 | 0 day(s) 13:45 Hrs | CORE: 1 of 6 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 124yds - 50mph TSR | 85 | 583 | 85 | 707 | 124
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 21 | 145803 | A211630 | 32200220 | Longbank | 11 | 1100 | GSW | Weekend | W2018/5766962 | 2018-08-19 00:01 | 2018-08-20 06:00 | 1 day(s) 05:59 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 518y) | 102 | 1270 | 103 | 28 | 518
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 21 | 145803 | A2861900 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5766962 | 2018-08-19 00:01 | 2018-08-24 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 378
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 21 | 145803 | A2865890 | DVN31103319 | Broxburn Cottages Drain | 15ba | 1100 | EGM1 | Weekend | W2018/5828041 | 2018-08-19 00:25 | 2018-08-19 08:00 | 0 day(s) 07:35 Hrs | CORE: 11th CW | 36 | 966 | 36 | 1035 | 165 | Core cancelled week 06, shortfall included here - additional shifts?
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 22 | 145803 | A213610 | 31500316 | Rothiemay | 4 | 3400 | ANI1 | Weekend | W2018/5747795 | 2018-08-24 23:10 | 2018-08-27 05:50 | 2 day(s) 06:40 Hrs | CORE: 1st CW (4 - Steel Sleeper Relay and Rerail 1498y) | 45 | 973 | 46 | 711 | 1498
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 22 | 155890 | G4T3840 | 42601018 | Sevenoaks Tunnel Down - P1 (CORE 3 & 4) | 11 | 1100 | XTD | Weekend | W2018/5762270 | 2018-08-25 01:15 | 2018-08-28 04:00 | 3 day(s) 02:45 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 22 | 1380 | 23 | 0 | 380 | TON-K-1819-08 | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 22 | 155890 | G6420 | 42601118 | Sevenoaks Tunnel Down - P3 (CORE 4 & 5) | 11 | 1100 | XTD | Weekend | W2018/5762270 | 2018-08-25 01:15 | 2018-08-28 04:00 | 3 day(s) 02:45 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 23 | 0 | 23 | 470 | 470 | TON-K-1819-43
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 22 | 148273 | A937090 | 24300719 | COT Canley Station North | 12 | 2100 | RBS1 | Weekend | W2018/5740090 | 2018-08-25 01:30 | 2018-08-28 04:00 | 3 day(s) 02:30 Hrs | CORE: 1st Core COT Canley Station North 440 Yards of CAT12 | 95 | 500 | 95 | 940 | 440
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 22 | 148817 | A947350 | 51400119 | Kintbury | 14 | 1100 | BHL | Blockade | W2018/w20186074929 | 2018-08-27 22:00 | 2018-08-30 22:00 | 3 day(s) 00:00 Hrs | CORE: 1st CW (Rerail, Resleeper, Reballast, Formation-Trax) Cat 11 | 58 | 77 | 58 | 12 | 430
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 23 | 145803 | A371590 | 31500316 | Rothiemay | 4 | 3400 | ANI1 | Weekend | W2018/5747818 | 2018-08-31 23:10 | 2018-09-03 05:50 | 2 day(s) 06:40 Hrs | CORE: 2nd CW (4 - Steel Sleeper Relay and Rerail 1499y) | 46 | 711 | 47 | 466 | 1515 | Mileage amended (+16 yds) to remove adj sws | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 23 | 155890 | G4T3850 | 42601118 | Sevenoaks Tunnel Down - P3 (CORE 4 & 5) | 11 | 1100 | XTD | Weekend | W2018/5762291 | 2018-09-01 01:15 | 2018-09-03 04:00 | 2 day(s) 02:45 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 23 | 470 | 23 | 924 | 454 | TON-K-1819-07
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 23 | 157791 | A392430 | 23501319 | COT High Oaks Junction | 14 | 1200 | LEC2 | Weekend | W2018/5853596 | 2018-09-01 22:15 | 2018-09-02 12:00 | 0 day(s) 13:45 Hrs | CORE: 2 of 6 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 124yds - 50mph TSR | 85 | 707 | 85 | 831 | 124
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 23 | 157839 | A3270 | 125052 16 | Hexthorpe Jnc | 11 | 1100 | PED5 | Weekend | W2018/5897795 | 2018-09-02 00:05 | 2018-09-03 04:45 | 1 day(s) 04:40 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 637yds | 20 | 192 | 20 | 829 | 637
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 24 | 157792 | A29870 | 21380816 | Penrith Auction Mart | 11 | 2100 | CGJ7 | Weekend | W2018/5840772 | 2018-09-08 21:55 | 2018-09-09 09:45 | 0 day(s) 11:50 Hrs | CORE: 1 of 3: Penrith Auction Mart - Rerail, Resleeper, Reballast - Trax - CAT11 - 133yds | 50 | 533 | 50 | 930 | 133
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 24 | 157791 | A392440 | 23501319 | COT High Oaks Junction | 14 | 1200 | LEC2 | Weekend | W2018/5853597 | 2018-09-08 22:15 | 2018-09-09 12:00 | 0 day(s) 13:45 Hrs | CORE: 3 of 6 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 124yds - 50mph TSR | 85 | 831 | 85 | 955 | 124
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 24 | 145803 | A173020 | 32202618 | Heatherbell South | 2 | 2100 | SCM3 | Weekend | W2018/5765229 | 2018-09-09 00:01 | 2018-09-10 05:00 | 1 day(s) 04:59 Hrs | CORE: 1st CW (02 - Rerail - Both Rails 221y) | 96 | 352 | 96 | 573 | 471
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 24 | 145803 | A2450210 | 32202618 | Heatherbell South | 11 | 2100 | SCM3 | Weekend | W2018/5765229 | 2018-09-09 00:01 | 2018-09-10 05:00 | 1 day(s) 04:59 Hrs | CORE: 3rd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 295y) | 95 | 1654 | 96 | 70 | 413 | Reduce yardage by 132 yds - to be done as S&C refurb | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 24 | 157839 | A4130 | 125052 16 | Hexthorpe Jnc | 11 | 1100 | PED5 | Weekend | W2018/5897886 | 2018-09-09 00:05 | 2018-09-10 04:45 | 1 day(s) 04:40 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 638yds | 20 | 829 | 20 | 1467 | 638
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 24 | 148309 | A4160 | 42201016df2 | Old Dover Road (Down) | 11 | 2100 | HDR | Weekend | W2018/5821738 | 2018-09-09 01:50 | 2018-09-10 02:50 | 1 day(s) 01:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 23 | 80 | 23 | 331 | 251 | KENT-1819-49 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 24 | 148309 | A4180 | 42201016df2 | Old Dover Road (Down) | 2 | 2100 | HDR | Weekend | W2018/5821738 | 2018-09-09 01:50 | 2018-09-10 02:50 | 1 day(s) 01:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 67 | 23 | 80 | 13 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 24 | 148309 | K3180 | 42201016df2 | Old Dover Road (Down) | 2 | 2100 | HDR | Weekend | W2018/5821738 | 2018-09-09 01:50 | 2018-09-10 02:50 | 1 day(s) 01:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 331 | 23 | 344 | 13 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 25 | 148310 | G1060 | 43400513sf1 | Crawley Dn | 2 | 2100 | TBH1 | Weekend | W2018/5824067 | 2018-09-15 01:00 | 2018-09-17 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 31 | 1573 | 31 | 1599 | 26 | SUS-1819-39 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 25 | 148310 | S1110 | 43400513sf1 | Crawley Dn | 14 | 2100 | TBH1 | Weekend | W2018/5824067 | 2018-09-15 01:00 | 2018-09-17 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 31 | 900 | 31 | 1573 | 673 | SUS-1819-39 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 25 | 148310 | S2060 | 43400513sf1 | Crawley Dn | 2 | 2100 | TBH1 | Weekend | W2018/5824067 | 2018-09-15 01:00 | 2018-09-17 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 31 | 885 | 31 | 900 | 15 | SUS-1819-39 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 25 | 148817 | G4T196220 | 51138917 | Long Field Avenue | 11 | 1100 | MLN1 | Weekend | W2018/5801585 | 2018-09-15 21:30 | 2018-09-17 05:00 | 1 day(s) 07:30 Hrs | CORE: 1/3 CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 6 | 400 | 6 | 1056 | 219
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 25 | 157792 | A2903780 | 21380816 | Penrith Auction Mart | 11 | 2100 | CGJ7 | Weekend | W2018/5840782 | 2018-09-15 21:55 | 2018-09-16 09:45 | 0 day(s) 11:50 Hrs | CORE: 2 of 3: Penrith Auction Mart - Rerail, Resleeper, Reballast - Trax - CAT11 - 133yds | 50 | 533 | 50 | 930 | 133
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 25 | 148320 | A2130 | 113034 11 | Ashwell | 14 | 1100 | GSM2 | Weekend | W2018/5902492 | 2018-09-15 22:00 | 2018-09-17 05:00 | 1 day(s) 07:00 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 295yds | 96 | 1427 | 96 | 1722 | 295 | PLS-1819-205 - mileage changed from 96m1427y-97m360y to 96m 427y-97m0257y (590yds). Possession times TBC. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 25 | 145803 | A2447040 | 32202618 | Heatherbell South | 2 | 2100 | SCM3 | Weekend | W2018/5765361 | 2018-09-16 00:01 | 2018-09-17 05:00 | 1 day(s) 04:59 Hrs | CORE: 2nd CW (02 - Rerail - Both Rails 0y) | 96 | 573 | 96 | 794 | 0
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 25 | 145803 | A2450220 | 32202618 | Heatherbell South | 11 | 2100 | SCM3 | Weekend | W2018/5765361 | 2018-09-16 00:01 | 2018-09-17 05:00 | 1 day(s) 04:59 Hrs | CORE: 4th CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 0y) | 96 | 70 | 96 | 365 | 0
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 25 | 145803 | A2861910 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5765361 | 2018-09-16 00:01 | 2018-09-21 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 377
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 26 | 145803 | A2867610 | NV31200417 | Milton Road Drain | 15ba | 1100 | ECM8 | Weekend | W2018/5751905 | 2018-09-22 00:25 | 2018-09-23 09:00 | 1 day(s) 08:35 Hrs | CORE: 1st CW | 3 | 1369 | 3 | 1674 | 329
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 26 | 145803 | A345280 | 31205118 | Strawberry Brig | 14 | 2100 | ECM8 | Weekend | W2018/5764437 | 2018-09-22 00:25 | 2018-09-23 09:00 | 1 day(s) 08:35 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 638y) | 7 | 1160 | 8 | 40 | 641
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 26 | 145803 | A346270 | 31201018 | The Moss | 14 | 2100 | ECM8 | Weekend | W2018/5751905 | 2018-09-22 00:25 | 2018-09-23 09:00 | 1 day(s) 08:35 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types396y) | 40 | 1157 | 40 | 1553 | 396
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 26 | 148309 | A936030 | 42200517 | Eltham to Falconwood | 2 | 2100 | BEX | Weekend | W2018/5822887 | 2018-09-22 01:25 | 2018-09-24 04:00 | 2 day(s) 02:35 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 10 | 322 | 10 | 334 | 12 | TON-K-1819-01 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 26 | 148309 | G4T21670 | 42200517 | Eltham to Falconwood | 11 | 2100 | BEX | Weekend | W2018/5822887 | 2018-09-22 01:25 | 2018-09-24 04:00 | 2 day(s) 02:35 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 9 | 1082 | 10 | 322 | 1000 | TON-K-1819-01 | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 26 | 157792 | A2903790 | 21380816 | Penrith Auction Mart | 11 | 2100 | CGJ7 | Weekend | W2018/5840793 | 2018-09-22 21:55 | 2018-09-23 09:45 | 0 day(s) 11:50 Hrs | CORE: 3 of 3: Penrith Auction Mart - Rerail, Resleeper, Reballast - Trax - CAT11 - 132yds | 50 | 533 | 50 | 930 | 131
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 26 | 148817 | G4T432760 | 51138917 | Long Field Avenue | 11 | 1100 | MLN1 | Weekend | W2018/5801730 | 2018-09-22 22:00 | 2018-09-24 01:00 | 1 day(s) 03:00 Hrs | CORE: 2/3 CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 6 | 400 | 6 | 1056 | 219
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 26 | 148320 | A2990 | 113034 11 | Ashwell | 14 | 1100 | GSM2 | Weekend | W2018/5902618 | 2018-09-22 22:00 | 2018-09-24 05:00 | 1 day(s) 07:00 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 295yds | 96 | 1722 | 97 | 257 | 295 | PLS-1819-205 - mileage changed from 96m1427y-97m360y to 96m 427y-97m0257y (590yds). Possession times TBC. | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 26 | 148273 | A305040 | 23101818 | Kilsby Tunnel Down | 14 | 1100 | LEC1 | Weekend | W2018/5953767 | 2018-09-22 22:10 | 2018-09-23 12:00 | 0 day(s) 13:50 Hrs | CORE: 1st Core Kilsby Tunnel Down 146 Yards of CAT14 - TSR 50mph T137422 | 76 | 1320 | 76 | 467 | 146
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 26 | 157843 | A2190 | 44205415 | Brockenhurst Dn Loop | 11 | 3503 | BML2 | Weekend | W2019/5947161 | 2018-09-23 00:15 | 2018-09-24 04:00 | 1 day(s) 03:45 Hrs | CORE: 1st CW 170yds | 92 | 1307 | 92 | 1477 | 170
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 27 | 145803 | A2867780 | NV31200417 | Milton Road Drain | 15ba | 1100 | ECM8 | Weekend | W2018/5751998 | 2018-09-29 00:25 | 2018-09-30 09:00 | 1 day(s) 08:35 Hrs | CORE: 2nd CW | 3 | 1674 | 4 | 219 | 330
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 27 | 145803 | A351240 | 31205118 | Strawberry Brig | 14 | 2100 | ECM8 | Weekend | W2018/5764494 | 2018-09-29 00:25 | 2018-09-30 09:00 | 1 day(s) 08:35 Hrs | CORE: 2nd CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 637y) | 8 | 40 | 8 | 681 | 641
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 27 | 145803 | A371610 | 31201018 | The Moss | 14 | 2100 | ECM8 | Weekend | W2018/5751998 | 2018-09-29 00:25 | 2018-09-30 09:00 | 1 day(s) 08:35 Hrs | CORE: 2nd CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types397y) | 40 | 1553 | 41 | 190 | 397
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 27 | 157839 | A2467090 | 131020 SF2 | Ulgham Grange | 11 | 2100 | ECM7 | Weekend | W2018/5955123 | 2018-09-29 00:25 | 2018-09-30 08:50 | 1 day(s) 08:25 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 375yds + 20y RAMP | 22 | 440 | 22 | 815 | 375 | PLN-1920-030. PLN-1819-110 | APC
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 27 | 154530 | A3920 | 53100411 | Morton On Lugg | 11 | 1100 | SHL | Weekend | W2018/5940584 | 2018-09-29 01:00 | 2018-10-01 04:00 | 2 day(s) 03:00 Hrs | CORE: (1 of 2) Cat 11 628y - 1255y tot | 46 | 1400 | 47 | 268 | 628
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 27 | 148309 | A4200 | 42200517 | Eltham to Falconwood | 2 | 2100 | BEX | Weekend | W2018/5822940 | 2018-09-29 01:25 | 2018-10-01 04:00 | 2 day(s) 02:35 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 9 | 415 | 9 | 432 | 17 | TON-K-1819-01 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 27 | 148309 | A4220 | 42200517 | Eltham to Falconwood | 11 | 2100 | BEX | Weekend | W2018/5822940 | 2018-09-29 01:25 | 2018-10-01 04:00 | 2 day(s) 02:35 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 9 | 432 | 9 | 1082 | 650 | TON-K-1819-01 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 27 | 148817 | A940860 | 51138917 | Long Field Avenue | 2 | 1100 | MLN1 | Weekend | W2018/5801731 | 2018-09-29 22:00 | 2018-10-01 01:00 | 1 day(s) 03:00 Hrs | CORE: 3/3 CW (Rerail)Cat: 02 | 6 | 400 | 6 | 1056 | 26
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 27 | 148817 | G4T432770 | 51138917 | Long Field Avenue | 11 | 1100 | MLN1 | Weekend | W2018/5801731 | 2018-09-29 22:00 | 2018-10-01 01:00 | 1 day(s) 03:00 Hrs | CORE: 3/3 CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 6 | 400 | 6 | 1056 | 218
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 27 | 148316 | A2414170 | 122025 14 | St.Neots | 11 | 1200 | ECM1 | Weekend | W2018/5898004 | 2018-09-29 22:00 | 2018-10-01 04:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 438yds | 51 | 98 | 51 | 974 | 438 | Possession times TBC.
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 27 | 148316 | A30280 | 122025 14 | St.Neots | 2 | 1200 | ECM1 | Weekend | W2018/5898004 | 2018-09-29 22:00 | 2018-10-01 04:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail (Both Rails) - 18yds | 51 | 73 | 51 | 98 | 18 | Possession times TBC.
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 27 | 148273 | A935890 | 23101818 | Kilsby Tunnel Down | 14 | 1100 | LEC1 | Weekend | W2018/5961672 | 2018-09-29 22:10 | 2018-09-30 12:00 | 0 day(s) 13:50 Hrs | CORE: 2nd Core Kilsby Tunnel Down 147 Yards of CAT14 - TSR 50mph T137423 | 76 | 467 | 76 | 614 | 147
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 28 | 145803 | A306670 | FD80018a | Monktonhall South Falldown 12/13 | 2 | 1100 | ECM8 | Weekend | W2018/5783181 | 2018-10-06 00:25 | 2018-10-07 09:00 | 1 day(s) 08:35 Hrs | CORE: 1st CW (2 - Rerail - Both Rails 79y) | 5 | 1705 | 5 | 1744 | 0
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 28 | 145803 | A351200 | FD80018a | Monktonhall South Falldown 12/13 | 11 | 1100 | ECM8 | Weekend | W2018/5783181 | 2018-10-06 00:25 | 2018-10-07 09:00 | 1 day(s) 08:35 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 581y) | 5 | 1744 | 6 | 565 | 581
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 28 | 157839 | A2484780 | 131020 SF2 | Ulgham Grange | 11 | 2100 | ECM7 | Weekend | W2018/5955217 | 2018-10-06 00:25 | 2018-10-07 08:50 | 1 day(s) 08:25 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 334yds + 20y RAMP | 22 | 815 | 22 | 1149 | 334 | PLN-1920-030. PLN-1819-110 | APC
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 28 | 154530 | A9450 | 53100411 | Morton On Lugg | 11 | 1100 | SHL | Weekend | W2018/5940862 | 2018-10-06 03:20 | 2018-10-08 04:20 | 2 day(s) 01:00 Hrs | CORE: (2 of 2) Cat 11 628y - 1255y tot - Spate wk27 work OTM? | 47 | 268 | 47 | 895 | 627
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 28 | 145803 | A2858330 | FD31501018 | Hanover/Waterloo | 11 | 3400 | WRO | Weekend | W2018/5761715 | 2018-10-06 19:00 | 2018-10-10 09:00 | 3 day(s) 14:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 0m-0m 175y Line F 175y) | 0 | 0 | 0 | 175 | 47
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 28 | 145803 | A2858340 | FD31501018 | Hanover/Waterloo | 11 | 3400 | WRO | Weekend | W2018/5761715 | 2018-10-06 19:00 | 2018-10-10 09:00 | 3 day(s) 14:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 0m-0m 0085y Line A 85y) | 0 | 0 | 0 | 56 | 56
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 28 | 145803 | A2869930 | NV31501018 | Hanover/Waterloo Track Drain | 15ba | 3400 | WRO | Weekend | W2018/5796959 | 2018-10-06 19:00 | 2018-10-10 09:00 | 3 day(s) 14:00 Hrs | CORE: 1st CW | 0 | 0 | 0 | 404 | 404
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 28 | 148316 | A2411240 | 122025 14 | St.Neots | 2 | 1200 | ECM1 | Weekend | W2018/5898092 | 2018-10-06 22:00 | 2018-10-08 04:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail (Both Rails) - 17yds | 51 | 974 | 51 | 984 | 17 | Possession times TBC.
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 28 | 148316 | A31140 | 122025 14 | St.Neots | 11 | 1200 | ECM1 | Weekend | W2018/5898092 | 2018-10-06 22:00 | 2018-10-08 04:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 438yds | 51 | 98 | 51 | 974 | 438 | Possession times TBC.
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 28 | 148817 | A945270 | 51401319 | Enbourne-Bonemill Lane | 11 | 2100 | BHL | Weekend | W2018/0000000 | 2018-10-08 00:01 | 2018-10-10 00:01 | 2 day(s) 00:00 Hrs | CORE: 1st CW (Rerail, Resleeper, Reballast-Trax | 54 | 1661 | 54 | 66 | 759
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 29 | 153374 | A31250 | 114508LSI | Kettering North | 14 | 1100 | SPC3 | Weekend | W2018/5923588 | 2018-10-13 00:15 | 2018-10-15 04:40 | 2 day(s) 04:25 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 368yds | 73 | 1114 | 73 | 1482 | 368 | Possession times TBC.
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 29 | 145803 | A351210 | FD80018a | Monktonhall South Falldown 12/13 | 14 | 1100 | ECM8 | Weekend | W2018/5783204 | 2018-10-13 00:25 | 2018-10-14 09:00 | 1 day(s) 08:35 Hrs | CORE: 2nd CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 280y) | 6 | 565 | 6 | 845 | 280
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 29 | 145803 | A351220 | FD80018a | Monktonhall South Falldown 12/13 | 12 | 1100 | ECM8 | Weekend | W2018/5783204 | 2018-10-13 00:25 | 2018-10-14 09:00 | 1 day(s) 08:35 Hrs | CORE: 2nd CW (12 - Formation, Reballast - Traxcavate 121y) | 6 | 845 | 6 | 966 | 121
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 29 | 145803 | A351170 | FD31501018 | Hanover/Waterloo | 11 | 3400 | WRO | Weekend | W2018/5761899 | 2018-10-13 19:00 | 2018-10-17 09:00 | 3 day(s) 14:00 Hrs | CORE: 2nd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 596y) | 0 | 56 | 0 | 652 | 596
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 29 | 145803 | D4000 | NV31501018 | Hanover/Waterloo Track Drain | 15ba | 3400 | WRO | Weekend | W2018/5796959 | 2018-10-13 19:00 | 2018-10-17 09:00 | 3 day(s) 14:00 Hrs | CORE: 2nd CW | 0 | 404 | 0 | 808 | 404
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 29 | 145803 | A2861920 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5783204 | 2018-10-14 00:01 | 2018-10-19 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 377
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 29 | 157839 | A12540 | 125034 16 | Hexthorpe to St. James | 14 | 1100 | PED5 | Weekend | W2018/5904393 | 2018-10-14 00:05 | 2018-10-15 04:45 | 1 day(s) 04:40 Hrs | CORE: CAT14: Rerail, Resleeper, Reballast, Formation - Trax) : 495yds | 21 | 916 | 21 | 1411 | 495 | As per revised staging Peter Hoult (08/06/18)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 29 | 157839 | A12550 | 125034 16 | Hexthorpe to St. James | 2 | 1100 | PED5 | Weekend | W2018/5904393 | 2018-10-14 00:05 | 2018-10-15 04:45 | 1 day(s) 04:40 Hrs | CORE: CAT02: Rerail - both Rails: 7yds | 21 | 909 | 21 | 916 | 7 | As per revised staging Peter Hoult (08/06/18)
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 29 | 157843 | A3090 | 44205415 | Brockenhurst Dn Loop | 11 | 3503 | BML2 | Weekend | W2019/5947224 | 2018-10-14 00:45 | 2018-10-15 04:20 | 1 day(s) 03:35 Hrs | CORE: 2nd CW 364yds | 93 | 48 | 93 | 412 | 364
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 30 | 155890 | A10770 | 43400813df1 | Clayton Tunnel Dn | 11 | 2100 | VTB3 | Weekend | W2018/5883754 | 2018-10-20 01:20 | 2018-10-22 04:00 | 2 day(s) 02:40 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 44 | 660 | 44 | 1700 | 1040 | SUS-1819-69 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 30 | 145803 | A351180 | FD31501018 | Hanover/Waterloo | 11 | 3400 | WRO | Weekend | W2018/5761901 | 2018-10-20 19:00 | 2018-10-24 09:00 | 3 day(s) 14:00 Hrs | CORE: 3rd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 596y) | 0 | 652 | 0 | 1248 | 596
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 30 | 145803 | D4010 | NV31501018 | Hanover/Waterloo Track Drain | 15ba | 3400 | WRO | Weekend | W2018/5796959 | 2018-10-20 19:00 | 2018-10-24 09:00 | 3 day(s) 14:00 Hrs | CORE: 3rd CW | 0 | 808 | 0 | 1212 | 404
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 30 | 148273 | A941920 | 23101818 | Kilsby Tunnel Down | 14 | 1100 | LEC1 | Weekend | W2018/5961673 | 2018-10-20 22:10 | 2018-10-21 12:00 | 0 day(s) 13:50 Hrs | CORE: 3rd Core Kilsby Tunnel Down 147 Yards of CAT14 - TSR 50mph T138480 | 76 | 614 | 77 | 0 | 147
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 30 | 148817 | G4T378500 | 51130113 | West Drayton Combined | 11 | 1100 | MLN1 | Weekend | W2018/5809132 | 2018-10-20 23:00 | 2018-10-22 04:25 | 1 day(s) 05:25 Hrs | CORE: 1/5 CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 13 | 884 | 14 | 251 | 225
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 30 | 153374 | A34370 | 114510LSI | Kettering North-1 | 7 | 1100 | SPC3 | Weekend | W2018/5923593 | 2018-10-20 23:55 | 2018-10-22 05:25 | 1 day(s) 05:30 Hrs | CORE: Cat 7 - Reballast - Trax - 321yds | 74 | 209 | 74 | 530 | 321 | Possession times TBC. Changed from Cat 14 to Cat 7 C/C ref: PLS-1819-279 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 30 | 145803 | A2868790 | NV31400217 | Ardullie Drain | 15ba | 3400 | WCK | Weekend | W2018/5796959 | 2018-10-21 00:01 | 2018-10-22 04:01 | 1 day(s) 04:00 Hrs | CORE: 1st CW | 26 | 1110 | 26 | 1210 | 473
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 30 | 157839 | A5170 | 125034 16 | Hexthorpe to St. James | 14 | 1100 | PED5 | Weekend | W2018/5380275 | 2018-10-21 00:05 | 2018-10-22 04:45 | 1 day(s) 04:40 Hrs | CORE: CAT14: Rerail, Resleeper, Reballast, Formation - Trax) : 495yds | 21 | 1411 | 22 | 146 | 495 | As per revised staging Peter Hoult (08/06/18)
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 30 | 145803 | A371620 | 31202519 | Brunstane Station | 9 | 3400 | NDE1 | Weekend | W2018/5790955 | 2018-10-21 00:20 | 2018-10-22 05:00 | 1 day(s) 04:40 Hrs | CORE: 2nd CW (7 - Reballast - Traxcavation 218y) | 4 | 659 | 4 | 877 | 0 | Site deferred - to be done as an S&C refurb | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 30 | 148324 | G4T392500 | 41620312sf1 | Great Chesterford Dn | 2 | 2100 | BGK | Weekend | W2018/5945337 | 2018-10-21 00:50 | 2018-10-22 04:00 | 1 day(s) 03:10 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 45 | 1724 | 46 | 932 | 968
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 30 | 148324 | G4T393440 | 41620312sf1 | Great Chesterford Dn | 2 | 2100 | BGK | Weekend | W2018/5945337 | 2018-10-21 00:50 | 2018-10-22 04:00 | 1 day(s) 03:10 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 47 | 150 | 47 | 326 | 176
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 30 | 148324 | G4T393450 | 41620312sf1 | Great Chesterford Dn | 2 | 2100 | BGK | Weekend | W2018/5945337 | 2018-10-21 00:50 | 2018-10-22 04:00 | 1 day(s) 03:10 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 47 | 1260 | 47 | 1397 | 137
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 30 | 155890 | G4T3440 | 43400813df1 | Clayton Tunnel Dn | 11 | 2100 | VTB3 | Weekend | W2018/5885300 | 2018-10-22 04:00 | 2018-10-26 22:00 | 4 day(s) 18:00 Hrs | CORE: BLOCKADE - Shifts to be supplied. Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 44 | 660 | 44 | 1700 | 0 | SUS-1819-69 | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 31 | 155890 | G4T3450 | 43400813df1 | Clayton Tunnel Dn | 11 | 2100 | VTB3 | Weekend | W2018/5885302 | 2018-10-26 22:00 | 2018-10-29 04:00 | 2 day(s) 06:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 44 | 660 | 44 | 1700 | 0 | SUS-1819-69 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 31 | 157838 | A2190 | 123252 | Stones Sidings | 4 | 1100 | GRS2 | Weekend | W2018/0000000 | 2018-10-27 01:00 | 2018-10-28 08:00 | 1 day(s) 07:00 Hrs | CORE: Cat 04 - (Rerail, Resleeper - Steel) - 896yds | 127 | 1320 | 128 | 456 | 896 | Volume amended as per agreed C/C ref: PLS-1819-297
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 31 | 145803 | A2858310 | FD31501018 | Hanover/Waterloo | 11 | 3400 | WRO | Weekend | W2018/5761902 | 2018-10-27 19:00 | 2018-10-31 09:00 | 3 day(s) 14:00 Hrs | CORE: 4th CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 596y) | 0 | 1248 | 1 | 84 | 596
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 31 | 145803 | D4020 | NV31501018 | Hanover/Waterloo Track Drain | 15ba | 3400 | WRO | Weekend | W2018/5796959 | 2018-10-27 19:00 | 2018-10-31 09:00 | 3 day(s) 14:00 Hrs | CORE: 4th CW | 0 | 1212 | 0 | 1616 | 404
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 31 | 148320 | A13570 | 113228 | Barrow on Soar | 11 | 2200 | SPC5 | Weekend | W2018/5931323 | 2018-10-27 22:00 | 2018-10-29 05:00 | 1 day(s) 07:00 Hrs | CORE: Cat 11 - Rerail, Resleeper, Reballast - Trax - 220yds | 109 | 0 | 109 | 220 | 220 | Possession times TBC. Work category amended to Cat 11 vice Cat 14 as per c/c ref: PLS-1819-228 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 31 | 148817 | G4T432780 | 51130113 | West Drayton Combined | 11 | 1100 | MLN1 | Weekend | W2018/0000000 | 2018-10-27 23:00 | 2018-10-29 05:00 | 1 day(s) 06:00 Hrs | CORE: 2/5 CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 13 | 884 | 14 | 251 | 225
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 31 | 145803 | D3960 | NV31400217 | Ardullie Drain | 15ba | 3400 | WCK | Weekend | W2018/5796959 | 2018-10-28 00:01 | 2018-10-28 08:01 | 0 day(s) 08:00 Hrs | CORE: 2nd CW | 26 | 1110 | 26 | 1210 | 100
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 31 | 157839 | A4310 | 125034 16 | Hexthorpe to St. James | 11 | 1100 | PED5 | Weekend | W2018/5380281 | 2018-10-28 00:05 | 2018-10-29 04:45 | 1 day(s) 04:40 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 409yds | 22 | 232 | 22 | 641 | 409 | As per revised staging Peter Hoult (08/06/18)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 31 | 157839 | A4320 | 125034 16 | Hexthorpe to St. James | 14 | 1100 | PED5 | Weekend | W2018/5380281 | 2018-10-28 00:05 | 2018-10-29 04:45 | 1 day(s) 04:40 Hrs | CORE: CAT14: Rerail, Resleeper, Reballast, Formation - Trax) : 86yds | 22 | 146 | 22 | 232 | 86 | As per revised staging Peter Hoult (08/06/18)
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 18/19 | 31 | 145831 | A2452780 | 22200511 | Crewe Station Platform 1 | 15aa | 3201 | LEC5 | Weekend | W2018/000000 | 2018-10-28 00:45 | 2018-10-29 04:40 | 1 day(s) 03:55 Hrs | CORE: Core 1 of 4 (Associated Drainage) Cat:15aa | 157 | 1456 | 158 | 18 | 322
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 18/19 | 31 | 145831 | A2466970 | 22200511 | Crewe Station Platform 1 | 15aa | 3201 | LEC5 | Weekend | W2018/000000 | 2018-10-28 00:45 | 2018-10-29 04:40 | 1 day(s) 03:55 Hrs | CORE: Core 1 of 4 (Associated Drainage) Cat:15aa | 158 | 160 | 158 | 231 | 71
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 32 | 148817 | A940850 | 51130113 | West Drayton Combined | 2 | 1100 | MLN1 | Weekend | W2018/0000000 | 2018-11-03 01:00 | 2018-11-05 05:00 | 2 day(s) 04:00 Hrs | CORE: 3/5CW (Rerail) Cat: 02 | 13 | 884 | 14 | 251 | 35
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 32 | 157838 | A2489810 | 123252 | Stones Sidings | 2 | 1100 | GRS2 | Weekend | W2018/0000000 | 2018-11-03 01:00 | 2018-11-04 08:00 | 1 day(s) 07:00 Hrs | CORE: Cat 02 - Rerail (Both rails) - 20yds | 128 | 1351 | 128 | 1371 | 20 | Volume amended as per agreed C/C ref: PLS-1819-297
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 32 | 157838 | A3090 | 123252 | Stones Sidings | 4 | 1100 | GRS2 | Weekend | W2018/0000000 | 2018-11-03 01:00 | 2018-11-04 08:00 | 1 day(s) 07:00 Hrs | CORE: Cat 04 - (Rerail, Resleeper - Steel) - 895yds | 128 | 456 | 128 | 1351 | 895 | Volume amended as per agreed C/C ref: PLS-1819-297
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 32 | 148310 | G4T168480 | 43401118 | Dorking to Holmwood | 2 | 1100 | BTH3 | Weekend | W2018/5787295 | 2018-11-03 18:50 | 2018-11-05 05:45 | 1 day(s) 10:55 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 26 | 1613 | 26 | 128 | 15 | SUS-1819-44 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 32 | 148310 | G4T168490 | 43401118 | Dorking to Holmwood | 2 | 1100 | BTH3 | Weekend | W2018/5787295 | 2018-11-03 18:50 | 2018-11-05 05:45 | 1 day(s) 10:55 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 27 | 308 | 27 | 321 | 13 | SUS-1819-44 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 32 | 148310 | G4T59890 | 43401118 | Dorking to Holmwood | 11 | 1100 | BTH3 | Weekend | W2018/5787295 | 2018-11-03 18:50 | 2018-11-05 05:45 | 1 day(s) 10:55 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 26 | 1628 | 27 | 308 | 440 | SUS-1819-44 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 32 | 145803 | A2858320 | FD31501018 | Hanover/Waterloo | 11 | 3400 | WRO | Weekend | W2018/5761903 | 2018-11-03 19:00 | 2018-11-07 09:00 | 3 day(s) 14:00 Hrs | CORE: 5th CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 596y) | 1 | 84 | 1 | 680 | 596
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 32 | 145803 | D4030 | NV31501018 | Hanover/Waterloo Track Drain | 15ba | 3400 | WRO | Weekend | W2018/5796959 | 2018-11-03 19:00 | 2018-11-07 09:00 | 3 day(s) 14:00 Hrs | CORE: 5th CW | 0 | 1616 | 1 | 1210 | 404
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 32 | 148273 | A940630 | 23300715 | Anthony Close Drain | 15aa | 1100 | LEC1 | Weekend | W2018/5849896 | 2018-11-03 20:00 | 2018-11-04 12:00 | 0 day(s) 16:00 Hrs | CORE: 1st Core 1/2 Anthony Close Drain 153yards CAT of 15aa | 15 | 574 | 15 | 727 | 153 | Late Addition into the Programme - Requires an EPA or TT-84 and TT-65
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 32 | 148320 | A14430 | 113228 | Barrow on Soar | 11 | 2200 | SPC5 | Weekend | W2018/5931611 | 2018-11-03 22:00 | 2018-11-05 05:00 | 1 day(s) 07:00 Hrs | CORE: Cat 11 - Rerail, Resleeper, Reballast - Trax - 220yds | 109 | 220 | 109 | 440 | 220 | Possession times TBC. Work category amended to Cat 11 vice Cat 14 as per c/c ref: PLS-1819-228 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 32 | 148817 | G4T432790 | 51130113 | West Drayton Combined | 11 | 1100 | MLN1 | Weekend | W2018/0000000 | 2018-11-03 23:00 | 2018-11-05 05:00 | 1 day(s) 06:00 Hrs | CORE: 3/5CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 13 | 884 | 14 | 251 | 225
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 32 | 145803 | D3970 | NV31400217 | Ardullie Drain | 15ba | 3400 | WCK | Weekend | W2018/5796959 | 2018-11-04 00:01 | 2018-11-04 08:01 | 0 day(s) 08:00 Hrs | CORE: 3rd CW | 26 | 1110 | 26 | 1210 | 100
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 32 | 157839 | A2490740 | 125034 16 | Hexthorpe to St. James | 11 | 1100 | PED5 | Weekend | W2018/5904619 | 2018-11-04 00:05 | 2018-11-05 04:45 | 1 day(s) 04:40 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 154yds | 22 | 641 | 22 | 795 | 154 | As per revised staging Peter Hoult (08/06/18)
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 18/19 | 32 | 145831 | A2452620 | 22200511 | Crewe Station Platform 1 | 7 | 3201 | LEC5 | Weekend | W2018/000000 | 2018-11-04 00:45 | 2018-11-05 04:40 | 1 day(s) 03:55 Hrs | CORE: Core 2 of 4 (Reballast, Formation - Trax) Cat:07 | 157 | 1456 | 157 | 1617 | 161
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 33 | 148309 | G4T117930 | 42100618 | Margate to Broadstairs (Up) | 11 | 1100 | VIR | Weekend | W2018/5923688 | 2018-11-10 00:30 | 2018-11-12 04:30 | 2 day(s) 04:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 75 | 1496 | 76 | 924 | 1188 | KENT1819-54 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 33 | 148309 | G4T121130 | 42100618 | Margate to Broadstairs (Up) | 2 | 1100 | VIR | Weekend | W2018/5923688 | 2018-11-10 00:30 | 2018-11-12 04:30 | 2 day(s) 04:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 75 | 1482 | 75 | 1496 | 14
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 33 | 148309 | G4T121140 | 42100618 | Margate to Broadstairs (Up) | 2 | 1100 | VIR | Weekend | W2018/5923688 | 2018-11-10 00:30 | 2018-11-12 04:30 | 2 day(s) 04:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 76 | 924 | 76 | 938 | 14
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 33 | 148287 | A2181890 | 122011 15 | Maxey - Lolham | 2 | 1200 | ECM1 | Weekend | W2018/5939842 | 2018-11-10 01:20 | 2018-11-11 09:00 | 1 day(s) 07:40 Hrs | CORE: CAT 02: Rerail - Both Rails: 16yds | 82 | 765 | 82 | 781 | 16
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 33 | 148287 | A2452640 | 125226 | Peascliffe - Manthorpe DN | 14 | 2100 | ECM1 | Weekend | W2018/5947911 | 2018-11-10 01:20 | 2018-11-11 12:00 | 1 day(s) 10:40 Hrs | CORE: CAT14: Formation, Reballast, Resleeper, Rerail - Trax: 296yds | 107 | 838 | 107 | 1134 | 296
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 33 | 148287 | A2485220 | 122011 15 | Maxey - Lolham | 11 | 1200 | ECM1 | Weekend | W2018/5939842 | 2018-11-10 01:20 | 2018-11-11 09:00 | 1 day(s) 07:40 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 583yds | 82 | 781 | 82 | 1656 | 583 | GG 20/11/19 - Activity added to align with RF11 (Nov 2017) Business Plan Costing Tool
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 33 | 148813 | A935930 | 44201218 | Southampton Airport Parkway Up | 11 | 1100 | BML1 | Weekend | W2018/5900708 | 2018-11-10 01:25 | 2018-11-12 04:00 | 2 day(s) 02:35 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 74 | 1224 | 75 | 74 | 610 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 33 | 145803 | A367350 | FD31502613 SF1 | Cradlehall | 4 | 1100 | HGL2 | Weekend | W2018/5822748 | 2018-11-10 22:50 | 2018-11-12 04:45 | 1 day(s) 05:55 Hrs | CORE: 1st CW (4 - Steel Sleeper Relay and Rerail 758y) | 115 | 418 | 115 | 1176 | 758
Andrew Derry | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 33 | 157842 | A4310 | 52200112 SF | Alderton Tunnel | 11 | 1100 | SWB | Weekend | W2018/5965155 | 2018-11-10 23:30 | 2018-11-13 05:00 | 2 day(s) 05:30 Hrs | CORE: Cat 11 418y - OTM? - (Work can't start until 0800 Sat) | 97 | 1452 | 97 | 1452 | 418 | Change reuired to remove from program | CR
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 33 | 145803 | A2861930 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5822748 | 2018-11-11 00:01 | 2018-11-16 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 377
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 33 | 145803 | A2871070 | FDNV32201418 | Cambuslang Cutting Up Cess Drain | 15ba | 1100 | WCM2 | Weekend | W2018/5796959 | 2018-11-11 00:01 | 2018-11-11 08:01 | 0 day(s) 08:00 Hrs | CORE: 1st CW | 96 | 1620 | 96 | 1700 | 80
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 18/19 | 33 | 145831 | A2451770 | 22200511 | Crewe Station Platform 1 | 7 | 3201 | LEC5 | Weekend | W2018/000000 | 2018-11-11 00:45 | 2018-11-12 04:40 | 1 day(s) 03:55 Hrs | CORE: Core 3 of 4 (Reballast, Formation - Trax) Cat:07 | 157 | 1617 | 158 | 18 | 161
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 34 | 148273 | A936050 | 24101112 | Beaconsfield Platform | 14 | 2100 | NAJ2 | Weekend | W2018/5850460 | 2018-11-17 01:15 | 2018-11-19 05:25 | 2 day(s) 04:10 Hrs | CORE: 1st Core Beaconsfield Platform 760 Yards of CAT14 | 11 | 406 | 11 | 1166 | 760
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 34 | 148310 | A3180 | 43100214 | Balham to Streatham Cmn | 14 | 2100 | VTB1 | Weekend | W2018/5863235 | 2018-11-17 01:20 | 2018-11-19 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 6 | 259 | 6 | 574 | 315 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 34 | 148310 | G4T168440 | 43100214 | Balham to Streatham Cmn | 2 | 2100 | VTB1 | Weekend | W2018/5863235 | 2018-11-17 01:20 | 2018-11-19 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 6 | 53 | 6 | 66 | 13 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 34 | 148310 | G4T168450 | 43100214 | Balham to Streatham Cmn | 2 | 2100 | VTB1 | Weekend | W2018/5863235 | 2018-11-17 01:20 | 2018-11-19 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Re-Rail Both Rails Cat:02 | 6 | 574 | 6 | 587 | 13 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 34 | 148310 | G4T24610 | 43100214 | Balham to Streatham Cmn | 14 | 2100 | VTB1 | Weekend | W2018/5863235 | 2018-11-17 01:20 | 2018-11-19 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 6 | 66 | 6 | 175 | 109 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 34 | 148287 | A2182750 | 122011 15 | Maxey - Lolham | 11 | 1200 | ECM1 | Weekend | W2018/5939998 | 2018-11-17 01:20 | 2018-11-18 12:00 | 1 day(s) 10:40 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 583yds | 82 | 781 | 82 | 1656 | 583 | GG 20/11/17 - Volumes adjusted to spread over 3 weeks vice 2, as per RF11 (nov 2017) Business Plan Costing Tool
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 34 | 148287 | A2453500 | 125226 | Peascliffe - Manthorpe DN | 14 | 2100 | ECM1 | Weekend | W2018/5947912 | 2018-11-17 01:20 | 2018-11-18 12:00 | 1 day(s) 10:40 Hrs | CORE: CAT14: Formation, Reballast, Resleeper, Rerail - Trax: 296yds | 107 | 1134 | 107 | 1430 | 296
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 34 | 148273 | G4T212040 | 23100515s | Courteenhall | 15aa | 1100 | LEC1 | Weekend | W2018/5952802 | 2018-11-17 22:10 | 2018-11-18 09:00 | 0 day(s) 10:50 Hrs | CORE: 1st Core Courteenhall 149 Yards of CAT15aa | 60 | 1320 | 60 | 1469 | 149 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 34 | 145803 | D3990 | FDNV32201418 | Cambuslang Cutting Up Cess Drain | 15ba | 1100 | WCM2 | Weekend | W2018/5796959 | 2018-11-18 00:01 | 2018-11-18 08:01 | 0 day(s) 08:00 Hrs | CORE: 2nd CW | 96 | 1700 | 97 | 20 | 80
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 18/19 | 34 | 145831 | A2452710 | 22200511 | Crewe Station Platform 1 | 7 | 3201 | LEC5 | Weekend | W2018/000000 | 2018-11-18 00:45 | 2018-11-19 04:40 | 1 day(s) 03:55 Hrs | CORE: Core 4 of 4 (Reballast, Formation - Trax) Cat:07 | 158 | 160 | 158 | 231 | 71
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 18/19 | 34 | 145831 | A2452950 | 22200511 | Crewe Station Platform 1 | 2 | 3201 | LEC5 | Weekend | W2018/000000 | 2018-11-18 00:45 | 2018-11-19 04:40 | 1 day(s) 03:55 Hrs | CORE: Core 1 of 1 (Rerail) Cat:02 | 158 | 153 | 158 | 160 | 7
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 35 | 145803 | A371630 | 31504418 | Stanley Joiners Shop Dn | 14 | 2100 | HGL1 | Weekend | W2018/5822704 | 2018-11-23 22:40 | 2018-11-27 04:45 | 3 day(s) 06:05 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 580y) | 158 | 93 | 158 | 700 | 607
Andrew Derry | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 35 | 157842 | A3270 | 51300120 | Hullavington | 14 | 2100 | SWB | Weekend | W2018/5965166 | 2018-11-24 00:01 | 2018-11-26 04:00 | 2 day(s) 03:59 Hrs | CORE: 1st CW (insert description) | 93 | 1584 | 94 | 264 | 440 | Change reuired to remove from program | CR
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 35 | 155890 | G4T1330 | 43402118 | Clayton Tunnel Up | 11 | 1100 | VTB3 | Weekend | W2018/6060658 | 2018-11-24 01:20 | 2018-11-26 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Core Re-Rail, Re-sleeper, Re-ballast Cat 11 | 44 | 880 | 44 | 1700 | 820 | TON-SUS-1819-02 | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 35 | 155890 | G4T4510 | 43402118 | Clayton Tunnel Up | 2 | 1100 | VTB3 | Weekend | W2018/6060658 | 2018-11-24 01:20 | 2018-11-26 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Core Re-rail Both Rails Cat 02 | 44 | 860 | 44 | 880 | 20 | TON-SUS-1819-02 | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 35 | 155890 | G4T4520 | 43402118 | Clayton Tunnel Up | 2 | 1100 | VTB3 | Weekend | W2018/6060658 | 2018-11-24 01:20 | 2018-11-26 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Core Re-rail Both Rails Cat 02 | 44 | 1700 | 44 | 1717 | 17 | TON-SUS-1819-02 | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 35 | 148287 | A2181900 | 122011 15 | Maxey - Lolham | 11 | 1200 | ECM1 | Weekend | W2018/5940125 | 2018-11-24 01:20 | 2018-11-25 12:00 | 1 day(s) 10:40 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 583yds | 82 | 1656 | 83 | 770 | 583 | GG 20/11/17 - Volumes adjusted to spread over 3 weeks vice 2, as per RF11 (nov 2017) Business Plan Costing Tool
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 35 | 148287 | A2451600 | 125227 | Peascliffe - Manthorpe UP | 14 | 1100 | ECM1 | Weekend | W2018/5947924 | 2018-11-24 01:20 | 2018-11-25 12:00 | 1 day(s) 10:40 Hrs | CORE: CAT14: Formation, Reballast, Resleeper, Rerail - Trax: 296yds | 107 | 838 | 107 | 1134 | 296
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 35 | 157792 | A27830 | 21400518 | Brock FC | 16 | 2100 | CGJ6 | Weekend | W2018/5859502 | 2018-11-24 21:30 | 2018-11-25 09:20 | 0 day(s) 11:50 Hrs | CORE: 1 of 3: Brock FC - Rerail, Resleeper (Concrete) - CAT16 180yrds | 6 | 825 | 6 | 1005 | 180
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 35 | 148273 | G4T361980 | 23500416 | Kilsby Tunnel North | 12 | 1100 | LEC1 | Weekend | W2018/5848665 | 2018-11-24 22:10 | 2018-11-25 09:00 | 0 day(s) 10:50 Hrs | CORE: 1st Core Kilsby Tunnel North 146 Yards of Cat12 | 78 | 220 | 78 | 380 | 160
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 35 | 148817 | A941110 | 51130113 | West Drayton Combined | 11 | 1100 | MLN1 | Weekend | W2018/0000000 | 2018-11-24 23:00 | 2018-11-26 05:00 | 1 day(s) 06:00 Hrs | CORE: 4/5 CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 13 | 884 | 14 | 251 | 225
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 35 | 145803 | D3980 | FDNV32201418 | Cambuslang Cutting Up Cess Drain | 15ba | 1100 | WCM2 | Weekend | W2018/5796959 | 2018-11-25 00:01 | 2018-11-25 08:01 | 0 day(s) 08:00 Hrs | CORE: 3rd CW | 97 | 20 | 97 | 102 | 82
Andrew Derry | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 35 | 157842 | A2190 | 51422213 | Midgham | 14 | 2100 | BHL | Weekend | W2018/0000000 | 2018-11-25 01:00 | 2018-11-26 05:00 | 1 day(s) 04:00 Hrs | CORE: 1st CW (insert description) | 46 | 1065 | 46 | 1230 | 185 | Change reuired to remove from program | CR
Andrew Derry | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 35 | 157842 | A8840 | 51422213 | Midgham | 7 | 2100 | BHL | Weekend | W2018/0000000 | 2018-11-25 01:00 | 2018-11-26 05:00 | 1 day(s) 04:00 Hrs | CORE: 1st CW (insert description) | 46 | 1230 | 46 | 1250 | 20 | Change reuired to remove from program | CR
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 36 | 148310 | G1020 | 43201118 | Merstham to Holmthorpe | 2 | 1100 | RED2 | Weekend | W2018/5878404 | 2018-12-01 00:55 | 2018-12-03 04:00 | 2 day(s) 03:05 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 20 | 1234 | 20 | 1250 | 16 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 36 | 148310 | G4T121630 | 43201118 | Merstham to Holmthorpe | 14 | 1100 | RED2 | Weekend | W2018/5878404 | 2018-12-01 00:55 | 2018-12-03 04:00 | 2 day(s) 03:05 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 20 | 1250 | 21 | 75 | 585 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 36 | 148287 | A2452460 | 125227 | Peascliffe - Manthorpe UP | 14 | 1100 | ECM1 | Weekend | W2018/5947925 | 2018-12-01 01:20 | 2018-12-02 12:00 | 1 day(s) 10:40 Hrs | CORE: CAT14: Formation, Reballast, Resleeper, Rerail - Trax: 296yds | 107 | 1134 | 107 | 1430 | 296
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 36 | 157792 | A2451240 | 21400518 | Brock FC | 16 | 2100 | CGJ6 | Weekend | W2018/5859534 | 2018-12-01 21:30 | 2018-12-02 09:20 | 0 day(s) 11:50 Hrs | CORE: 2 of 3: Brock FC - Rerail, Resleeper (Concrete) - CAT16 180yrds | 6 | 1005 | 6 | 1185 | 180
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 36 | 148273 | G4T491480 | 23500416 | Kilsby Tunnel North | 12 | 1100 | LEC1 | Weekend | W2018/5848666 | 2018-12-01 22:10 | 2018-12-02 09:00 | 0 day(s) 10:50 Hrs | CORE: 2nd Core Kilsby Tunnel North 146 Yards of CAT12 | 78 | 380 | 78 | 540 | 160
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 36 | 153374 | A14610 | 114496LSI | Elstree | 12 | 1100 | SPC1 | Weekend | W2018/5948229 | 2018-12-01 22:45 | 2018-12-03 06:00 | 1 day(s) 07:15 Hrs | CORE: Cat 12 - Reballast, Formation - Trax - 219yds | 12 | 1540 | 12 | 1759 | 219 | Possession times TBC. Changed from Cat 14 to Cat 12 C/C ref: PLS-1819-278 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 36 | 148817 | A941120 | 51130113 | West Drayton Combined | 11 | 1100 | MLN1 | Weekend | W2018/0000000 | 2018-12-01 23:00 | 2018-12-03 05:00 | 1 day(s) 06:00 Hrs | CORE:5/5 CW (Rerail, Resleeper, Reballast - Trax) Cat: 11 | 13 | 884 | 14 | 251 | 227
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 36 | 145803 | A158170 | 32201718 | Coatbridge Central Station | 11 | 2100 | SCM3 | Weekend | W2018/5826035 | 2018-12-02 00:01 | 2018-12-03 04:15 | 1 day(s) 04:14 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 430y) | 94 | 1292 | 94 | 1637 | 345 | Mileage previously renewed by S&C project (-79 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 36 | 145803 | A2875720 | FDNV32200514 | Portland 2A Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2018-12-02 00:01 | 2018-12-02 08:01 | 0 day(s) 08:00 Hrs | CORE: 1st CW | 26 | 1110 | 26 | 1210 | 0 | Work site removed - Drain not required (-561 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 36 | 145803 | A2878500 | NV32201017 | Kirkconnel Station Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2018-12-02 00:01 | 2018-12-02 08:01 | 0 day(s) 08:00 Hrs | CORE: 1st CW | 26 | 1110 | 26 | 1210 | 160 | Drain renewal to replace Portland 2 drain (+640 yds) | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 37 | 148310 | G1040 | 43201118 | Merstham to Holmthorpe | 14 | 1100 | RED2 | Weekend | W2018/5878452 | 2018-12-08 00:55 | 2018-12-10 04:00 | 2 day(s) 03:05 Hrs | CORE: 2/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 21 | 75 | 21 | 660 | 585 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 37 | 148310 | G1050 | 43201118 | Merstham to Holmthorpe | 2 | 1100 | RED2 | Weekend | W2018/5878452 | 2018-12-08 00:55 | 2018-12-11 04:00 | 3 day(s) 03:05 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 21 | 660 | 21 | 676 | 16 |  | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 37 | 157843 | A4310 | 44100510 | Motspur Park Plt | 11 | 2100 | RPE | Weekend | W2018/ | 2018-12-08 01:00 | 2018-12-10 03:55 | 2 day(s) 02:55 Hrs | CORE: 1st CW (insert description) | 9 | 1098 | 9 | 1390 | 292
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 37 | 157792 | A2451270 | 21400518 | Brock FC | 16 | 2100 | CGJ6 | Weekend | W2018/5859547 | 2018-12-08 21:30 | 2018-12-09 09:20 | 0 day(s) 11:50 Hrs | CORE: 3 of 3: Brock FC - Rerail, Resleeper (Concrete) - CAT16 115yrda | 6 | 1185 | 6 | 1300 | 115
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 37 | 157791 | A327890 | 23509799 | Brinklow Yard | 12 | 1100 | LEC2 | Weekend | W2018/5953508 | 2018-12-08 22:15 | 2018-12-09 09:15 | 0 day(s) 11:00 Hrs | CORE: 1 of 2 Reballast, Formation - Trax - Cat12 - 137yds | 87 | 1695 | 88 | 72 | 137
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 37 | 157838 | A14450 | 114084 | Hendon | 11 | 1200 | SPC1 | Weekend | W2018/5998621 | 2018-12-08 22:45 | 2018-12-10 05:45 | 1 day(s) 07:00 Hrs | CORE: CAT 11 Reballast, Resleeper, Rerail - Trax - 280yds | 7 | 25 | 7 | 305 | 280 | CC 02.03.17 - PLS-1920-015 mileage changed from 7m0y-7m280y (280yds) to 7m45y-7m325y (280yds). LP
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 37 | 145803 | A2861940 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2018/5286267 | 2018-12-09 00:01 | 2018-12-14 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 377
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 37 | 145803 | A2875940 | FDNV32200514 | Portland 2A Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2018-12-09 00:01 | 2018-12-09 08:01 | 0 day(s) 08:00 Hrs | CORE: 2nd CW | 26 | 1110 | 26 | 1210 | 0 | Work site removed - Drain not required (-561 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 37 | 145803 | A2878660 | NV32201017 | Kirkconnel Station Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2018-12-09 00:01 | 2018-12-09 08:01 | 0 day(s) 08:00 Hrs | CORE: 2nd CW | 26 | 1110 | 26 | 1210 | 160 | Drain renewal to replace Portland 2 drain (+640 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 37 | 145803 | A371640 | 32201718 | Coatbridge Central Station | 11 | 2100 | SCM3 | Weekend | W2018/5286267 | 2018-12-09 00:01 | 2018-12-10 04:15 | 1 day(s) 04:14 Hrs | CORE: 2nd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 430y) | 94 | 1637 | 95 | 222 | 345 | Mileage previously renewed by S&C project (-79 yds) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 37 | 157839 | A2489650 | 124104SF | Whitting Moor Road Shortfall | 11 | 1100 | TJC1 | Weekend | W2018/5988728 | 2018-12-09 00:40 | 2018-12-09 10:00 | 0 day(s) 09:20 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 125yds | 149 | 313 | 149 | 438 | 125 | CC PLN-1819-087 Approved 18/01/18 | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 38 | 157843 | A6390 | 44200710df2 | Swanwick XJ | 11 | 2100 | SDP1 | Weekend | W2018/5995772 | 2018-12-15 01:00 | 2018-12-17 04:00 | 2 day(s) 03:00 Hrs | CORE: 1st CW Rerail, Resleeper, Reballast-Trax | 13 | 225 | 13 | 1330 | 1099
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 38 | 157843 | A8470 | 44301817 | Windsor & Eton Riverside Platform-2 | 11 | 3602 | SWE | Weekend | W2018/5995790 | 2018-12-15 01:00 | 2018-12-17 04:30 | 2 day(s) 03:30 Hrs | CORE: 1st CW 405yds | 25 | 627 | 25 | 1032 | 405
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 38 | 148273 | A303820 | 23500416 | Kilsby Tunnel North | 12 | 1100 | LEC1 | Weekend | W2018/5848664 | 2018-12-15 22:10 | 2018-12-16 09:00 | 0 day(s) 10:50 Hrs | CORE: 3rd Core Kilsby Tunnel North 147 Yards of CAT12 | 78 | 540 | 78 | 660 | 120
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 38 | 157791 | A392330 | 23509799 | Brinklow Yard | 12 | 1100 | LEC2 | Weekend | W2018/5953510 | 2018-12-15 22:15 | 2018-12-16 09:15 | 0 day(s) 11:00 Hrs | CORE: 2 of 2 Reballast, Formation - Trax - Cat12 - 138yds | 88 | 72 | 88 | 210 | 138
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 38 | 153374 | A30210 | 114484LSI | Radwell Viaduct | 12 | 2100 | SPC2 | Weekend | W2018/5988703 | 2018-12-15 23:10 | 2018-12-17 05:25 | 1 day(s) 06:15 Hrs | CORE: Cat 12 - Formation, Reballast - Traxcavate 270yds | 54 | 900 | 54 | 1170 | 270 | Possession times TBC.
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 38 | 145803 | A2875950 | FDNV32200514 | Portland 2A Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2018-12-16 00:01 | 2018-12-16 08:01 | 0 day(s) 08:00 Hrs | CORE: 3rd CW | 26 | 1110 | 26 | 1210 | 0 | Work site removed - Drain not required (-561 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 38 | 145803 | A2878670 | NV32201017 | Kirkconnel Station Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2018-12-16 00:01 | 2018-12-16 08:01 | 0 day(s) 08:00 Hrs | CORE: 3rd CW | 26 | 1110 | 26 | 1210 | 160 | Drain renewal to replace Portland 2 drain (+640 yds) | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 40 | 157791 | A389250 | 23102018 | Milton Keynes - Platform 6 CAT15a | 15aa | 2100 | LEC1 | Weekend | W2018/5948883 | 2018-12-24 20:00 | 2018-12-29 08:00 | 4 day(s) 12:00 Hrs | CORE: 1 of 1 PL drainage associated - CAT15a - 1090yds | 49 | 990 | 50 | 210 | 1090 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 40 | 157791 | A390290 | 23101918 | Milton Keynes - Platform 6 Cat14 | 14 | 2100 | LEC1 | Weekend | W2018/5948883 | 2018-12-24 20:00 | 2018-12-29 08:00 | 4 day(s) 12:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 820yds | 49 | 880 | 49 | 1700 | 820 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 39 | 145803 | A210640 | 31201118 | PSG West Dn | 11 | 2100 | ECN2 | Christmas | W2018/5844927 | 2018-12-24 23:00 | 2018-12-27 04:00 | 2 day(s) 05:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 197y) | 0 | 775 | 0 | 980 | 205 | Mileage amended (+8yds) to tie into welds | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 39 | 145803 | A212620 | 31201218 | PSG West Up | 11 | 1100 | ECN2 | Christmas | W2018/5845351 | 2018-12-24 23:00 | 2018-12-26 10:00 | 1 day(s) 11:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 180y) | 0 | 801 | 0 | 972 | 171 | Mileage amended (-6yds) to tie into welds | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 39 | 145803 | A343300 | 32300817 | Salkeld Street Line 2 | 11 | 2101 | WCM2 | Christmas | W2018/5842214 | 2018-12-24 23:00 | 2018-12-26 08:00 | 1 day(s) 09:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 155y) | 101 | 885 | 101 | 1040 | 155
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 40 | 148309 | G4T121420 | 42500213 | Factory Jcn to Stewarts lane | 2 | 2100 | BSF | Weekend | W2018/5963181 | 2018-12-29 01:00 | 2018-12-31 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 1 | 921 | 1 | 928 | 7 | KENT1819-55 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 40 | 148309 | G4T121430 | 42500213 | Factory Jcn to Stewarts lane | 2 | 2100 | BSF | Weekend | W2018/5963181 | 2018-12-29 01:00 | 2018-12-31 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 1 | 1288 | 1 | 1293 | 5 | KENT1819-55 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 40 | 148309 | G4T30490 | 42500213 | Factory Jcn to Stewarts lane | 11 | 2100 | BSF | Weekend | W2018/5963181 | 2018-12-29 01:00 | 2018-12-31 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 1 | 928 | 1 | 1288 | 360 | KENT1819-55 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 40 | 145803 | A2457620 | 32300717 | Salkeld Street Line 1 | 11 | 1101 | WCM2 | Christmas | W2018/5842148 | 2018-12-31 23:00 | 2019-01-02 05:00 | 1 day(s) 06:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 150y) | 101 | 1086 | 101 | 1206 | 150
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 40 | 145803 | A348250 | 32300717 | Salkeld Street Line 1 | 11 | 1101 | WCM2 | Christmas | W2018/5842148 | 2018-12-31 23:00 | 2019-01-02 05:00 | 1 day(s) 06:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 158y) | 101 | 887 | 101 | 1045 | 158
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 41 | 145803 | A174010 | 32300217 | Hillington East Up Gourock | 11 | 1200 | AYR1 | Weekend | W2019/5849843 | 2019-01-05 00:45 | 2019-01-07 05:30 | 2 day(s) 04:45 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 1108y) | 3 | 728 | 4 | 76 | 900
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 41 | 148309 | A3170 | 42501310df3 | Elmstead Woods Platform 4 | 11 | 2200 | XTD | Weekend | W2018/5988546 | 2019-01-05 01:25 | 2019-01-07 02:50 | 2 day(s) 01:25 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 10 | 262 | 10 | 1324 | 1062 | KENT-1819-60 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 41 | 148309 | A4120 | 42501310df3 | Elmstead Woods Platform 4 | 2 | 2200 | XTD | Weekend | W2018/5988546 | 2019-01-05 01:25 | 2019-01-07 02:50 | 2 day(s) 01:25 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 10 | 241 | 10 | 262 | 21 | KENT-1819-60 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 41 | 148309 | A4130 | 42501310df3 | Elmstead Woods Platform 4 | 2 | 2200 | XTD | Weekend | W2018/5988546 | 2019-01-05 01:25 | 2019-01-07 02:50 | 2 day(s) 01:25 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 10 | 1324 | 10 | 1334 | 10 | KENT-1819-60 | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 41 | 148273 | A938130 | 23400514sb | Queens Park | 15aa | 2100 | LEC1 | Weekend | W2018/5816555 | 2019-01-05 20:00 | 2019-01-06 12:00 | 0 day(s) 16:00 Hrs | CORE: 1st Core Queens Park B 170 Yards of CAT15aa | 3 | 1414 | 4 | 1584 | 170
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 41 | 157792 | A2190 | 21101219 | Whitbeck/Bootle Beck | 4 | 2100 | CBC1 | Weekend | W2018/000000 | 2019-01-05 21:10 | 2019-01-06 06:25 | 0 day(s) 09:15 Hrs | CORE: 1 of 4: Whitbeck/Bootle Beck - Rerail, Resleeper (Steel) - CAT04 - 1043yds | 50 | 860 | 52 | 0 | 1176
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 41 | 157792 | A2910900 | 21101219 | Whitbeck/Bootle Beck | 2 | 2100 | CBC1 | Weekend | W2018/000000 | 2019-01-05 21:10 | 2019-01-06 06:25 | 0 day(s) 09:15 Hrs | CORE: 1 of 4: Whitbeck/Bootle Beck - Rerail, Both Rails- CAT02 - 5yds | 50 | 1009 | 50 | 1014 | 5
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 41 | 145803 | A2861950 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2019/5849843 | 2019-01-06 00:01 | 2019-01-11 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 377
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 41 | 145803 | A2875960 | FDNV32200514 | Portland 2A Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2019-01-06 00:01 | 2019-01-06 08:01 | 0 day(s) 08:00 Hrs | CORE: 4th CW | 26 | 1110 | 26 | 1210 | 0 | Work site removed - Drain not required (-561 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 41 | 145803 | A2878680 | NV32201017 | Kirkconnel Station Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2019-01-06 00:01 | 2019-01-06 08:01 | 0 day(s) 08:00 Hrs | CORE: 4th CW | 26 | 1110 | 26 | 1210 | 160 | Drain renewal to replace Portland 2 drain (+640 yds) | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 41 | 148817 | G4T10020 | 51300711 | Bourton | 11 | 1100 | MLN1 | Weekend | W2018/5865789 | 2019-01-06 00:55 | 2019-01-07 05:20 | 1 day(s) 04:25 Hrs | CORE: 1st CW (Rerail, Resleeper, Reballast - Trax) Cat:11 | 72 | 757 | 72 | 1001 | 244
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 42 | 145803 | A372220 | 32300217 | Hillington East Up Gourock | 11 | 1200 | AYR1 | Weekend | W2019/5849936 | 2019-01-12 00:45 | 2019-01-14 05:30 | 2 day(s) 04:45 Hrs | CORE: 2nd CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 1108y) | 4 | 76 | 4 | 1184 | 900
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 42 | 148324 | A938360 | 41600812sf1 | Roydon Up (Shortfall) | 2 | 1100 | BGK | Weekend | W2018/000000 | 2019-01-12 01:55 | 2019-01-14 04:00 | 2 day(s) 02:05 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 18 | 802 | 18 | 805 | 3
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 42 | 148324 | A938370 | 41600812sf1 | Roydon Up (Shortfall) | 11 | 1100 | BGK | Weekend | W2018/000000 | 2019-01-12 01:55 | 2019-01-14 04:00 | 2 day(s) 02:05 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 18 | 805 | 18 | 1429 | 624
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 42 | 148324 | A938390 | 41600812sf1 | Roydon Up (Shortfall) | 2 | 1100 | BGK | Weekend | W2018/000000 | 2019-01-12 01:55 | 2019-01-14 04:00 | 2 day(s) 02:05 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 18 | 1429 | 18 | 1432 | 3
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 42 | 148273 | A938990 | 23400514sb | Queens Park | 15aa | 2100 | LEC1 | Weekend | W2018/5816557 | 2019-01-12 20:00 | 2019-01-13 12:00 | 0 day(s) 16:00 Hrs | CORE: 2nd Core Queens Park B 170 Yards of CAT15aa | 3 | 1584 | 4 | 1754 | 170
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 42 | 157792 | A31840 | 21101219 | Whitbeck/Bootle Beck | 4 | 2100 | CBC1 | Weekend | W2018/000000 | 2019-01-12 21:10 | 2019-01-13 06:25 | 0 day(s) 09:15 Hrs | CORE: 2 of 4: Whitbeck/Bootle Beck - Rerail, Resleeper (Steel) - CAT04 - 1043yds | 52 | 280 | 52 | 845 | 1176
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 42 | 157839 | A6390 | 124168SF1 | Meadowhall Station Platform 3 | 7 | 1100 | SHB | Weekend | W2018/5723579 | 2019-01-12 23:35 | 2019-01-14 04:45 | 1 day(s) 05:10 Hrs | CORE: CAT07: Reballast - Trax: 321yds (See notes) | 161 | 1418 | 161 | 1739 | 321 | Now week 44? Wincobank access
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 42 | 145803 | A150250 | 31300118A | Burntisland Platform A&B | 11 | 1100 | ECN2 | Weekend | W2019/5852060 | 2019-01-13 00:01 | 2019-01-14 04:45 | 1 day(s) 04:44 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 300y) | 20 | 50 | 20 | 350 | 300
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 42 | 145803 | A2874580 | FDNV31100116 | Polmont Station Down Drain | 15ba | 2100 | EGM1 | Weekend | W2018/5796959 | 2019-01-13 00:01 | 2019-01-13 08:01 | 0 day(s) 08:00 Hrs | CORE: 1st CW | 24 | 1330 | 24 | 1416 | 86 | Mileage reduced to tie into existing drain (-30 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 42 | 145803 | A352350 | 31300118A | Burntisland Platform A&B | 2 | 1100 | ECN2 | Weekend | W2019/5852060 | 2019-01-13 00:01 | 2019-01-14 04:45 | 1 day(s) 04:44 Hrs | CORE: 1st CW (2 - Rerail - Both Rails 158y) | 19 | 1652 | 20 | 50 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 42 | 148817 | G4T415650 | 51122113 | Ealing UM (Shortfall) | 14 | 1100 | MLN1 | Weekend | W2018/5818958 | 2019-01-13 01:00 | 2019-01-14 04:00 | 1 day(s) 03:00 Hrs | CORE: 1st CW (CAT 14 Rerail, Resleeper, Reballast,Formation - Trax) | 6 | 50 | 6 | 110 | 20 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 42 | 148817 | G4T415660 | 51122113 | Ealing UM (Shortfall) | 12 | 1100 | MLN1 | Weekend | W2018/5818958 | 2019-01-13 01:00 | 2019-01-14 04:00 | 1 day(s) 03:00 Hrs | CORE: 1st CW (CAT 12 Reballast - Trax) | 5 | 1557 | 6 | 50 | 85 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 42 | 148817 | G4T81560 | 51122113 | Ealing UM (Shortfall) | 11 | 1100 | MLN1 | Weekend | W2018/5818958 | 2019-01-13 01:00 | 2019-01-14 04:00 | 1 day(s) 03:00 Hrs | CORE: 1st CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 6 | 110 | 6 | 400 | 97 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 43 | 145803 | A2875900 | 32300217 | Hillington East Up Gourock | 11 | 1200 | AYR1 | Weekend | W2019/5849937 | 2019-01-19 00:45 | 2019-01-21 05:30 | 2 day(s) 04:45 Hrs | CORE: 2nd CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 1108y) | 4 | 76 | 4 | 1184 | 416
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 43 | 157843 | A9510 | 44201418 | Southampton Parkway 6ft Drainage | 15ba | 2100 | BML1 | Weekend | W2018/6021071 | 2019-01-19 01:25 | 2019-01-21 04:00 | 2 day(s) 02:35 Hrs | CORE: 1st CW 836yds | 74 | 121 | 75 | 286 | 836
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 43 | 148310 | G1260 | 43400614 | Horse Crossing | 11 | 2100 | WJB | Weekend | W2018/6058961 | 2019-01-19 01:45 | 2019-01-21 04:00 | 2 day(s) 02:15 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 20 | 1405 | 21 | 321 | 676 | TON-SUS-1819-01 | CR
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 43 | 148310 | G4T167150 | 43400614 | Horse Crossing | 2 | 2100 | WJB | Weekend | W2018/6058961 | 2019-01-19 01:45 | 2019-01-21 04:00 | 2 day(s) 02:15 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 20 | 1391 | 20 | 1405 | 14 | TON-SUS-1819-01 | CR
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 43 | 148310 | G4T167160 | 43400614 | Horse Crossing | 2 | 2100 | WJB | Weekend | W2018/6058961 | 2019-01-19 01:45 | 2019-01-21 04:00 | 2 day(s) 02:15 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 21 | 321 | 21 | 334 | 13 | TON-SUS-1819-01 | CR
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 43 | 148324 | A937420 | 41600812sf1 | Roydon Up (Shortfall) | 11 | 1100 | BGK | Weekend | W2018/000000 | 2019-01-19 01:55 | 2019-01-21 04:00 | 2 day(s) 02:05 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 18 | 1512 | 18 | 1706 | 194
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 43 | 148324 | A938380 | 41600812sf1 | Roydon Up (Shortfall) | 2 | 1100 | BGK | Weekend | W2018/000000 | 2019-01-19 01:55 | 2019-01-21 04:00 | 2 day(s) 02:05 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 18 | 1462 | 18 | 1512 | 50
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 43 | 148324 | G4T390470 | 41600812sf1 | Roydon Up (Shortfall) | 2 | 1100 | BGK | Weekend | W2018/000000 | 2019-01-19 01:55 | 2019-01-21 04:00 | 2 day(s) 02:05 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 18 | 1706 | 18 | 1722 | 16
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 43 | 148273 | A938140 | 23400514sb | Queens Park | 15aa | 2100 | LEC1 | Weekend | W2018/5816560 | 2019-01-19 20:00 | 2019-01-21 12:00 | 1 day(s) 16:00 Hrs | CORE: 3rd Core Queens Park B 170 Yards of CAT15aa | 3 | 1754 | 4 | 164 | 170
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 43 | 157792 | A31850 | 21101219 | Whitbeck/Bootle Beck | 4 | 2100 | CBC1 | Weekend | W2018/000000 | 2019-01-19 21:10 | 2019-01-20 06:25 | 0 day(s) 09:15 Hrs | CORE: 3 of 4: Whitbeck/Bootle Beck - Rerail, Resleeper (Steel) - CAT04 - 1044yds | 52 | 1340 | 53 | 860 | 1177
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 43 | 148273 | G4T344340 | 23500316 | Kilsby Tunnel Up | 14 | 1100 | LEC1 | Weekend | W2018/5939858 | 2019-01-19 22:10 | 2019-01-22 12:00 | 2 day(s) 13:50 Hrs | CORE: 1st Core Kilsby Tunnel Up 146 Yards of Cat14 | 76 | 1320 | 77 | 0 | 146
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 43 | 157838 | A2484450 | 123260 | Hough Lane | 4 | 1100 | GRS1 | Weekend | W2018/6020424 | 2019-01-19 22:30 | 2019-01-21 06:30 | 1 day(s) 08:00 Hrs | CORE: CAT 04: Rerail, Resleeper - Steel : 763yds | 111 | 639 | 111 | 1402 | 763 | Moved from Wk's 44 & 45 to Wk's 43 & 44 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 43 | 145803 | A151240 | 31300118A | Burntisland Platform A&B | 11 | 1100 | ECN2 | Weekend | W2019/5852074 | 2019-01-20 00:01 | 2019-01-21 04:45 | 1 day(s) 04:44 Hrs | CORE: 2nd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 539y) | 20 | 350 | 20 | 889 | 539
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 43 | 145803 | D4060 | FDNV31100116 | Polmont Station Down Drain | 15ba | 2100 | EGM1 | Weekend | W2018/5796959 | 2019-01-20 00:01 | 2019-01-20 08:01 | 0 day(s) 08:00 Hrs | CORE: 2nd CW | 24 | 1416 | 24 | 1502 | 86
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 43 | 157839 | A2190 | 137015 18 | Featherstone | 11 | 1100 | WAG1 | Weekend | W2018/5986369 | 2019-01-20 00:01 | 2019-01-21 04:30 | 1 day(s) 04:29 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 299yds | 54 | 142 | 54 | 441 | 299
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 43 | 148817 | G4T71760 | 51300911 | Swindon East Up | 11 | 1100 | MLN1 | Weekend | W2018/5865922 | 2019-01-20 00:55 | 2019-01-21 04:55 | 1 day(s) 04:00 Hrs | CORE: 1st CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 76 | 726 | 76 | 1584 | 458 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 43 | 148817 | G4T432510 | 51122113 | Ealing UM (Shortfall) | 11 | 1100 | MLN1 | Weekend | W2018/5818959 | 2019-01-20 01:00 | 2019-01-21 04:00 | 1 day(s) 03:00 Hrs | CORE: 2nd CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 6 | 110 | 6 | 400 | 97 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 43 | 148817 | G4T432520 | 51122113 | Ealing UM (Shortfall) | 14 | 1100 | MLN1 | Weekend | W2018/5818959 | 2019-01-20 01:00 | 2019-01-21 04:00 | 1 day(s) 03:00 Hrs | CORE: 2nd CW (CAT 14 Rerail, Resleeper, Reballast,Formation - Trax) | 6 | 50 | 6 | 110 | 20 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 43 | 148817 | G4T432530 | 51122113 | Ealing UM (Shortfall) | 12 | 1100 | MLN1 | Weekend | W2018/5818959 | 2019-01-20 01:00 | 2019-01-21 04:00 | 1 day(s) 03:00 Hrs | CORE: 2nd CW (CAT 12 Reballast - Trax) | 5 | 1557 | 6 | 50 | 85 |  | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 44 | 157843 | A7430 | 44301717 | Windsor & Eton Riverside Platform-1 | 11 | 3601 | SWE | Weekend | W2018/6001475 | 2019-01-26 00:40 | 2019-01-28 04:00 | 2 day(s) 03:20 Hrs | CORE: 1st CW 380yds | 25 | 656 | 25 | 1036 | 380
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 44 | 145803 | A177970 | 32300316 | Ibrox Access West | 14 | 2100 | AYR1 | Weekend | W2019/5865661 | 2019-01-26 00:45 | 2019-01-28 05:30 | 2 day(s) 04:45 Hrs | CORE: 1st CW (14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 304y) | 2 | 322 | 2 | 626 | 304
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 44 | 148310 | G4T139270 | 43100318 | Reedham to Coulsdon Town | 2 | 1100 | TAT | Weekend | W2018/5881420 | 2019-01-26 01:00 | 2019-01-28 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 16 | 270 | 16 | 281 | 11 | SUS-1819-64 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 44 | 148310 | G4T167040 | 43100318 | Reedham to Coulsdon Town | 11 | 1100 | TAT | Weekend | W2018/5881420 | 2019-01-26 01:00 | 2019-01-28 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 16 | 281 | 16 | 659 | 378 | SUS-1819-64 | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 44 | 157791 | A320610 | 23300719 | COT Bullbeggars Lane | 12 | 2200 | LEC1 | Weekend | W2018/5853464 | 2019-01-26 20:00 | 2019-01-27 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3 Reballast, Formation - Trax - Cat12 - 130yds - 50mph TSR | 26 | 410 | 26 | 540 | 130
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 44 | 157792 | A2904870 | 21101219 | Whitbeck/Bootle Beck | 4 | 2100 | CBC1 | Weekend | W2018/000000 | 2019-01-26 21:10 | 2019-01-27 06:25 | 0 day(s) 09:15 Hrs | CORE: 4 of 4: Whitbeck/Bootle Beck - Rerail, Resleeper (Steel) - CAT04 - 1044yds | 52 | 1340 | 53 | 556 | 976
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 44 | 157792 | A2910910 | 21101219 | Whitbeck/Bootle Beck | 11 | 2100 | CBC1 | Weekend | W2018/000000 | 2019-01-26 21:10 | 2019-01-27 06:25 | 0 day(s) 09:15 Hrs | CORE: 4 of 4: Whitbeck/Bootle Beck - Rerail, Resleeper, Reballast - Trax - CAT11 - 196yds | 53 | 664 | 53 | 860 | 196
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 44 | 157791 | A392450 | 23501319 | COT High Oaks Junction | 14 | 1200 | LEC2 | Weekend | W2018/5856120 | 2019-01-26 22:15 | 2019-01-27 12:00 | 0 day(s) 13:45 Hrs | CORE: 4 of 6 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 124yds - 50mph TSR | 85 | 955 | 85 | 1079 | 124
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 44 | 157838 | A2483590 | 123260 | Hough Lane | 4 | 1100 | GRS1 | Weekend | W2018/6020432 | 2019-01-26 22:30 | 2019-01-28 06:30 | 1 day(s) 08:00 Hrs | CORE: CAT 04: Rerail, Resleeper - Steel : 763yds | 110 | 1636 | 111 | 639 | 763 | Volume amended as per agreed c/c ref: PLN-1920-061. Moved from Wk's 44 & 45 to Wk's 43 & 44. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 44 | 145803 | D4070 | FDNV31100116 | Polmont Station Down Drain | 15ba | 2100 | EGM1 | Weekend | W2018/5796959 | 2019-01-27 00:01 | 2019-01-27 08:01 | 0 day(s) 08:00 Hrs | CORE: 3rd CW | 24 | 1502 | 24 | 1588 | 86
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 44 | 157839 | A2241170 | 124050 16 | Wincobank | 11 | 2100 | TJC2 | Weekend | W2018/6020328 | 2019-01-27 00:01 | 2019-01-28 04:45 | 1 day(s) 04:44 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 440yds | 162 | 220 | 162 | 660 | 440 | PLN-1819-071. PLN-1819-096. (Access to Meadowhall?) | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 44 | 148817 | G4T432350 | 51300911 | Swindon East Up | 11 | 1100 | MLN1 | Weekend | W2018/5865923 | 2019-01-27 00:55 | 2019-01-28 04:55 | 1 day(s) 04:00 Hrs | CORE: 2nd CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 76 | 726 | 76 | 1584 | 400 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 44 | 148817 | G4T432540 | 51122113 | Ealing UM (Shortfall) | 11 | 1100 | MLN1 | Weekend | W2018/5818960 | 2019-01-27 01:00 | 2019-01-28 04:00 | 1 day(s) 03:00 Hrs | CORE: 3rd CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 6 | 110 | 6 | 400 | 96 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 44 | 148817 | G4T432550 | 51122113 | Ealing UM (Shortfall) | 14 | 1100 | MLN1 | Weekend | W2018/5818960 | 2019-01-27 01:00 | 2019-01-28 04:00 | 1 day(s) 03:00 Hrs | CORE: 3rd CW (CAT 14 Rerail, Resleeper, Reballast,Formation - Trax) | 6 | 50 | 6 | 110 | 20 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 44 | 148817 | G4T432560 | 51122113 | Ealing UM (Shortfall) | 12 | 1100 | MLN1 | Weekend | W2018/5818960 | 2019-01-27 01:00 | 2019-01-28 04:00 | 1 day(s) 03:00 Hrs | CORE: 3rd CW (CAT 12 Reballast - Trax) | 5 | 1557 | 6 | 50 | 83 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 44 | 145803 | A184900 | 100215 | Wormit | 11 | 1100 | ECN2 | Weekend | W2019/5854017 | 2019-01-27 01:05 | 2019-01-28 06:05 | 1 day(s) 05:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 671y) | 55 | 649 | 55 | 1320 | 671
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 45 | 157839 | A2242030 | 124050 16 | Wincobank | 11 | 2100 | TJC2 | Weekend | W2018/6020331 | 2019-02-02 00:01 | 2019-02-03 04:45 | 1 day(s) 04:44 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 440yds | 162 | 660 | 162 | 1100 | 440 | PLN-1819-071. PLN-1819-096. | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 45 | 148310 | A2130 | 43201010df1 | Limpsfield Tunnel Up | 11 | 1100 | SCU1 | Weekend | W2018/5955444 | 2019-02-02 00:50 | 2019-02-04 04:00 | 2 day(s) 03:10 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 20 | 1221 | 21 | 169 | 708 | SUS-1819-66 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 45 | 148310 | A3080 | 43201010df1 | Limpsfield Tunnel Up | 2 | 1100 | SCU1 | Weekend | W2018/5955444 | 2019-02-02 00:50 | 2019-02-04 04:00 | 2 day(s) 03:10 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 20 | 1207 | 20 | 1221 | 14 | Site added on 10/08/2016. CC Ref. SUS-1819-10
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 45 | 148310 | A3090 | 43201010df1 | Limpsfield Tunnel Up | 2 | 1100 | SCU1 | Weekend | W2018/5955444 | 2019-02-02 00:50 | 2019-02-04 04:00 | 2 day(s) 03:10 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 21 | 169 | 21 | 180 | 11 | Site added on 10/08/2016. CC Ref. SUS-1819-10
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 45 | 157843 | A5350 | 44201318 | Southampton Airport Parkway Dn | 11 | 2100 | BML1 | Weekend | W2018/5900708 | 2019-02-02 01:00 | 2019-02-04 04:00 | 2 day(s) 03:00 Hrs | CORE: 1st CW 645yds | 74 | 1225 | 75 | 110 | 645
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 45 | 148324 | A938420 | 41500118 | Up Temple Mills | 2 | 1152 | LTN1 | Weekend | W2018/000000 | 2019-02-02 01:30 | 2019-02-04 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 3 | 11 | 3 | 13 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 45 | 148324 | G4T381760 | 41500118 | Up Temple Mills | 11 | 1152 | LTN1 | Weekend | W2018/000000 | 2019-02-02 01:30 | 2019-02-04 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 13 | 3 | 238 | 225
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 45 | 157791 | A392410 | 23300719 | COT Bullbeggars Lane | 12 | 2200 | LEC1 | Weekend | W2018/5853465 | 2019-02-02 20:00 | 2019-02-03 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3 Reballast, Formation - Trax - Cat12 - 130yds - 50mph TSR | 26 | 540 | 26 | 670 | 130
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 45 | 157792 | A2903910 | TSR21101519 | Bootle Beck | 4 | 1100 | CBC1 | Weekend | W2018/000000 | 2019-02-02 21:10 | 2019-02-03 06:25 | 0 day(s) 09:15 Hrs | CORE: 1 of 2: Bootle Beck - Rerail, Resleeper (Steel) - CAT04 - 653yds | 50 | 452 | 52 | 60 | 653
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 45 | 157791 | A392460 | 23501319 | COT High Oaks Junction | 14 | 1200 | LEC2 | Weekend | W2018/5856121 | 2019-02-02 22:15 | 2019-02-03 12:00 | 0 day(s) 13:45 Hrs | CORE: 5 of 6 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 125yds - 50mph TSR | 85 | 1079 | 85 | 1204 | 125
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 45 | 157791 | A403500 | 23501319 | COT High Oaks Junction | 16 | 1200 | LEC2 | Weekend | W2018/5856121 | 2019-02-02 22:15 | 2019-02-03 12:00 | 0 day(s) 13:45 Hrs | CORE: 6 of 6 Rerail, Resleeper (Concrete) - CAT16 - 35yds | 85 | 548 | 85 | 583 | 35
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 45 | 145803 | A2861960 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2019/5871194 | 2019-02-03 00:01 | 2019-02-08 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 377
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 45 | 145803 | D4080 | FDNV31100116 | Polmont Station Down Drain | 15ba | 2100 | EGM1 | Weekend | W2018/5796959 | 2019-02-03 00:01 | 2019-02-03 08:01 | 0 day(s) 08:00 Hrs | CORE: 4th CW | 24 | 1588 | 24 | 1674 | 86
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 45 | 145803 | A144310 | 32100518 | Beith North | 11 | 1100 | AYR3 | Weekend | W2019/5871194 | 2019-02-03 00:15 | 2019-02-04 05:20 | 1 day(s) 05:05 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 605y) | 17 | 550 | 17 | 953 | 403
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 45 | 145803 | A371650 | 32100518 | Beith North | 11 | 1100 | AYR3 | Weekend | W2019/5871291 | 2019-02-03 00:15 | 2019-02-04 05:20 | 1 day(s) 05:05 Hrs | CORE: 2nd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 605y) | 17 | 953 | 18 | 1356 | 403
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 45 | 145803 | A371700 | 100215 | Wormit | 11 | 1100 | ECN2 | Weekend | W2019/5854092 | 2019-02-03 01:05 | 2019-02-04 05:20 | 1 day(s) 04:15 Hrs | CORE: 2nd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 671y) | 55 | 1320 | 56 | 231 | 671
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 46 | 157839 | A2241180 | 124050 16 | Wincobank | 11 | 2100 | TJC2 | Weekend | W2018/6020332 | 2019-02-09 00:01 | 2019-02-10 04:45 | 1 day(s) 04:44 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 440yds | 162 | 1100 | 162 | 1540 | 440 | PLN-1819-071. PLN-1819-096. | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 46 | 148324 | A934600 | 41500118 | Up Temple Mills | 2 | 1152 | LTN1 | Weekend | W2018/000000 | 2019-02-09 01:30 | 2019-02-11 04:00 | 2 day(s) 02:30 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 3 | 462 | 3 | 464 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 46 | 148324 | G4T390480 | 41500118 | Up Temple Mills | 11 | 1152 | LTN1 | Weekend | W2018/000000 | 2019-02-09 01:30 | 2019-02-11 04:00 | 2 day(s) 02:30 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 238 | 3 | 462 | 224
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 46 | 157791 | A392420 | 23300719 | COT Bullbeggars Lane | 12 | 2200 | LEC1 | Weekend | W2018/5853466 | 2019-02-09 20:00 | 2019-02-10 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3 Reballast, Formation - Trax - Cat12 - 130yds - 50mph TSR | 26 | 670 | 26 | 800 | 130
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 46 | 157792 | A2904850 | TSR21101519 | Bootle Beck | 14 | 1100 | CBC1 | Weekend | W2018/000000 | 2019-02-09 21:10 | 2019-02-10 06:25 | 0 day(s) 09:15 Hrs | CORE: 2 of 2: Bootle Beck - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 270yds | 53 | 610 | 53 | 771 | 270
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 46 | 148273 | A945870 | 23500316 | Kilsby Tunnel Up | 14 | 1100 | LEC1 | Weekend | W2018/5939860 | 2019-02-09 22:10 | 2019-02-12 12:00 | 2 day(s) 13:50 Hrs | CORE: 2nd Core Kilsby Tunnel Up 147 Yards of Cat14 | 76 | 1320 | 77 | 0 | 147
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 46 | 157838 | A2484650 | 123257 | Seweston Lane | 2 | 2100 | NOG1 | Weekend | W2018/6021692 | 2019-02-09 22:30 | 2019-02-11 05:30 | 1 day(s) 07:00 Hrs | CORE: CAT 02 -Rerail (Both rails) - 26yds **Moving to Week.41** | 110 | 1072 | 111 | 817 | 26 | CC 12.06.17 - PLS-1920-075 - Add job to 19/20 Plain Line Workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 46 | 157838 | A42300 | 123257 | Seweston Lane | 4 | 2100 | NOG1 | Weekend | W2018/6021692 | 2019-02-09 22:30 | 2019-02-11 05:30 | 1 day(s) 07:00 Hrs | CORE: CAT 4 - (Steel Sleeper Relay and Rerail) - 418yds **Moving to Week.41** | 110 | 1072 | 111 | 817 | 418 | CC 12.06.17 - PLS-1920-075 - Add job to 19/20 Plain Line Workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 46 | 157838 | A7430 | 114200 | Hendon DF SF | 11 | 2100 | SPC1 | Weekend | W2018/6037863 | 2019-02-09 22:45 | 2019-02-11 06:00 | 1 day(s) 07:15 Hrs | CORE: Cat 11 - Rerail, Resleeper, Reballast - Trax - 472yds | 6 | 660 | 6 | 1109 | 472
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 46 | 154530 | A2880 | TBC1HAWA | Hawarden Bridge Up | 11 | 2100 | WDB3 | Weekend | W2018/5932274 | 2019-02-09 23:55 | 2019-02-11 06:00 | 1 day(s) 06:05 Hrs | CORE: (1 of 2) Cat11 456y tot | 13 | 1631 | 14 | 341 | 470 | Instruction to be sent to babcock. Costing issues due to Spec Split and higher costs. | CR
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 46 | 145803 | D4090 | FDNV31100116 | Polmont Station Down Drain | 15ba | 2100 | EGM1 | Weekend | W2018/5796959 | 2019-02-10 00:01 | 2019-02-10 08:01 | 0 day(s) 08:00 Hrs | CORE: 5th CW | 24 | 1674 | 25 | 0 | 86
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 46 | 145803 | A2861990 | 32100518 | Beith North | 11 | 1100 | AYR3 | Weekend | W2019/5871292 | 2019-02-10 00:15 | 2019-02-11 05:20 | 1 day(s) 05:05 Hrs | CORE: 3rd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 404y) | 17 | 1356 | 18 | 0 | 404
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 46 | 145803 | A2862940 | 32100518 | Beith North | 15aa | 1100 | AYR3 | Weekend | W2019/5871292 | 2019-02-10 00:15 | 2019-02-11 05:20 | 1 day(s) 05:05 Hrs | CORE: 3rd CW (15aa drainage) | 17 | 1356 | 18 | 0 | 146
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 46 | 145803 | A2875980 | 32100518 | Beith North | 15aa | 1100 | AYR3 | Weekend | W2019/5871292 | 2019-02-10 00:15 | 2019-02-11 05:20 | 1 day(s) 05:05 Hrs | CORE: 3rd CW (15aa drainage) | 17 | 1356 | 18 | 0 | 5
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 46 | 145803 | A161140 | 31500819 | Cove Bay North | 11 | 1100 | ECN5 | Weekend | W2019/5873864 | 2019-02-10 00:30 | 2019-02-11 05:05 | 1 day(s) 04:35 Hrs | CORE: 1st CW (7 - Reballast - Traxcavation 439y) | 236 | 8 | 236 | 447 | 439
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 47 | 157791 | A373650 | TSB1100000s2 | Tyseley | 14 | 1100 | TSB | Weekend | W2018/5988202 | 2019-02-16 01:30 | 2019-02-19 05:30 | 3 day(s) 04:00 Hrs | CORE: 1 of 1 Reballast, Resleeper, Rerail, Formation - Trax (all non-steel sleeper types) - Cat11 - 395yds | 0 | 70 | 0 | 465 | 395 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 47 | 157792 | A23750 | 21501118 | Euxton | 14 | 1100 | CGJ5 | Weekend | W2018/000000 | 2019-02-16 21:50 | 2019-02-17 09:00 | 0 day(s) 11:10 Hrs | CORE: 1 of 2: Euxton - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 145yds | 15 | 1230 | 15 | 1520 | 145
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 47 | 157838 | A2484640 | 123257 | Seweston Lane | 4 | 2100 | NOG1 | Weekend | W2018/6021768 | 2019-02-16 22:30 | 2019-02-18 05:30 | 1 day(s) 07:00 Hrs | CORE: CAT 4 - (Steel Sleeper Relay and Rerail) - 1048yds **Moving to Week.42** | 110 | 1072 | 111 | 817 | 1048 | CC 12.06.17 - PLS-1920-075 - Add job to 19/20 Plain Line Workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 47 | 157841 | A2190 | 121022 13 | Barnet Tunnel South | 11 | 1200 | ECM1 | Weekend | W2018/6052852 | 2019-02-16 23:50 | 2019-02-18 04:05 | 1 day(s) 04:15 Hrs | CORE: Cat:11 - Rerail, Resleeper, Reballast - Trax - 180yds | 7 | 1350 | 7 | 1600 | 180
N/A | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 18/19 | 47 | 154530 | A9960 | TBC1HAWA | Hawarden Bridge Up | 11 | 2100 | WDB3 | Weekend | W2018/5932317 | 2019-02-16 23:55 | 2019-02-18 06:00 | 1 day(s) 06:05 Hrs | CORE: (2 of 2) Cat11 456y tot | 13 | 1631 | 14 | 341 | 470
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 47 | 145803 | D4100 | FDNV31100116 | Polmont Station Down Drain | 15ba | 2100 | EGM1 | Weekend | W2018/5796959 | 2019-02-17 00:01 | 2019-02-17 08:01 | 0 day(s) 08:00 Hrs | CORE: 6th CW | 25 | 0 | 25 | 86 | 86
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 47 | 145803 | A371710 | 31500819 | Cove Bay North | 11 | 1100 | ECN5 | Weekend | W2019/5873867 | 2019-02-17 00:30 | 2019-02-18 05:05 | 1 day(s) 04:35 Hrs | CORE: 2nd CW (7 - Reballast - Traxcavation 439y) | 236 | 447 | 236 | 886 | 439
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 48 | 157792 | A2451320 | 21501118 | Euxton | 14 | 1100 | CGJ5 | Weekend | W2018/000000 | 2019-02-23 21:50 | 2019-02-24 09:00 | 0 day(s) 11:10 Hrs | CORE: 2 of 2: Euxton - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 145yds | 15 | 1230 | 15 | 1520 | 145
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 48 | 157791 | A318530 | 23101118 | Milton Keynes North | 12 | 2100 | LEC1 | Weekend | W2018/5993445 | 2019-02-23 22:20 | 2019-02-24 14:20 | 0 day(s) 16:00 Hrs | CORE: 1 of 2 Reballast, Formation - Trax - Cat12 - 128yds | 50 | 824 | 50 | 981 | 128
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 48 | 148273 | A941490 | 23300715 | Anthony Close Drain | 15aa | 1100 | LEC1 | Weekend | W2018/5904923/5915270 | 2019-02-23 23:00 | 2019-02-24 15:00 | 0 day(s) 16:00 Hrs | CORE: 2nd Core 2/2 Anthony Close Drain 153yards of CAT 15aa | 15 | 727 | 15 | 880 | 153 | Late Addition into the Programme - Requires an EPA or TT-84 and TT-65
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 48 | 148320 | A34280 | 114086 11 | Mill Hill | 11 | 1100 | SPC1 | Weekend | W2018/6052849 | 2019-02-23 23:05 | 2019-02-25 06:00 | 1 day(s) 06:55 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax- 303yds **Moving to Wk.45** | 9 | 506 | 9 | 809 | 303 | Possession times TBC. | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 48 | 148320 | A34290 | 114086 11 | Mill Hill | 2 | 1100 | SPC1 | Weekend | W2018/6052849 | 2019-02-23 23:05 | 2019-02-25 06:00 | 1 day(s) 06:55 Hrs | CORE: Cat 02 - Rerail - Both Rails - 12yds **Moving to Wk.45** | 9 | 809 | 9 | 821 | 12 | Possession times TBC. | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 48 | 148320 | A5250 | 114086 11 | Mill Hill | 2 | 1100 | SPC1 | Weekend | W2018/6052849 | 2019-02-23 23:05 | 2019-02-25 06:00 | 1 day(s) 06:55 Hrs | CORE: Cat 02 - Rerail - Both Rails - 14yds **Awaiting C/C approval to move to Wk.45** | 9 | 492 | 9 | 506 | 14 | Possession times TBC. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 48 | 145803 | A148270 | 31500616c | Buckiehilloch Level Crossing South | 11 | 2100 | ECN3 | Weekend | W2019/5889769 | 2019-02-23 23:50 | 2019-02-25 04:50 | 1 day(s) 05:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 412y) | 10 | 908 | 10 | 1320 | 412
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 48 | 148316 | A29240 | 26438 12 | Barnet Tunnel | 14 | 1100 | ECM1 | Weekend | W2018/6052867 | 2019-02-23 23:50 | 2019-02-25 04:05 | 1 day(s) 04:15 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 152yds | 7 | 1433 | 7 | 1585 | 152 | Possession times TBC. Job to move to Week.48 (subject to c/c approval).
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 48 | 148316 | A30100 | 26438 12 | Barnet Tunnel | 11 | 1100 | ECM1 | Weekend | W2018/6052867 | 2019-02-23 23:50 | 2019-02-25 04:05 | 1 day(s) 04:15 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 161yds | 7 | 1585 | 7 | 1746 | 161 | Possession times TBC. Job to move to Week.48 (subject to c/c approval).
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 18/19 | 48 | 153374 | A15650 | 114513LSI | East Langton | 7 | 1100 | SPC3 | Weekend | W2018/6052876 | 2019-02-23 23:55 | 2019-02-25 05:25 | 1 day(s) 05:30 Hrs | CORE: Cat 07 - Reballast - Traxcavation 230yds | 86 | 490 | 86 | 720 | 230 | Possession times TBC. Works being carried out by Doncaster. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 48 | 145803 | D4110 | FDNV31100116 | Polmont Station Down Drain | 15ba | 2100 | EGM1 | Weekend | W2018/5796959 | 2019-02-24 00:01 | 2019-02-24 08:01 | 0 day(s) 08:00 Hrs | CORE: 7th CW | 25 | 86 | 25 | 170 | 84
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 48 | 145803 | A175990 | 32100118 | Howwood Station Up | 11 | 1100 | AYR3 | Weekend | W2019/5889848 | 2019-02-24 00:35 | 2019-02-25 05:30 | 1 day(s) 04:55 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 1034y) | 12 | 946 | 12 | 1463 | 517
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 49 | 148310 | G4T167400 | 43200117df1 | Hurst Green Jn to Lingfield | 11 | 2100 | HGG1 | Weekend | W2018/6006264 | 2019-03-02 00:50 | 2019-03-04 04:00 | 2 day(s) 03:10 Hrs | CORE: 1/1 Re-rail, Re-sleeper, Re-ballast - Trax - Cat11 | 22 | 879 | 22 | 1527 | 648 | SUS-1819-73 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 49 | 148310 | G4T168350 | 43200117df1 | Hurst Green Jn to Lingfield | 2 | 2100 | HGG1 | Weekend | W2018/6006264 | 2019-03-02 00:50 | 2019-03-04 04:00 | 2 day(s) 03:10 Hrs | CORE: 1/1 Re-rail Both Rails - Cat02 | 22 | 863 | 22 | 879 | 16 | SUS-1819-73 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 18/19 | 49 | 148310 | G4T168360 | 43200117df1 | Hurst Green Jn to Lingfield | 2 | 2100 | HGG1 | Weekend | W2018/6006264 | 2019-03-02 00:50 | 2019-03-04 04:00 | 2 day(s) 03:10 Hrs | CORE: 1/1 Re-rail Both Rails - Cat02 | 22 | 1527 | 22 | 1547 | 20 | SUS-1819-73 | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 49 | 148324 | A923920 | 41500613df1 | Ilford - 1 Up Main | 11 | 1100 | LTN1 | Weekend | W2018/5897323 | 2019-03-02 02:00 | 2019-03-04 04:00 | 2 day(s) 02:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 7 | 395 | 7 | 1033 | 638
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 49 | 157792 | A22730 | 21501218 | Blainscough DN Main | 14 | 2100 | CGJ5 | Weekend | W2018/000000 | 2019-03-02 21:50 | 2019-03-03 09:00 | 0 day(s) 11:10 Hrs | CORE: 1 of 2: Blainscough - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 130yds | 11 | 620 | 11 | 880 | 130
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 49 | 157839 | A2457090 | 134028B 17 | Willey Moor Bridge Pt 2 | 2 | 3100 | HBS | Weekend | W2018/6003411 | 2019-03-02 22:05 | 2019-03-04 06:00 | 1 day(s) 07:55 Hrs | CORE: CAT02: Rerail - both Rails: 19yds | 40 | 762 | 40 | 781 | 19 | PLN-1920-027 | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 49 | 157839 | A2473020 | 134028B 17 | Willey Moor Bridge Pt 2 | 16 | 3100 | HBS | Weekend | W2018/6003411 | 2019-03-02 22:05 | 2019-03-04 06:00 | 1 day(s) 07:55 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify (all non steel sleeper types) : 930yds | 40 | 781 | 41 | 880 | 930 | PLN-1920-027 | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 49 | 157791 | A326850 | 23503299 | Long Buckby Station | 14 | 2100 | HNR | Weekend | W2018/5917840 | 2019-03-02 22:10 | 2019-03-04 12:00 | 1 day(s) 13:50 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 350yds | 75 | 694 | 75 | 1044 | 350 | CC LNWSPL-1920-002 received 12/04/17. Change to mileages from 75m 694y-75m 973 to 75m 694y-75m 1044y. EA
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 49 | 148316 | A20850 | 121012 14 | Knebworth Stn Back Platform-1 | 14 | 2200 | ECM1 | Weekend | W2018/0000000 | 2019-03-02 23:00 | 2019-03-04 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 - Rerail, Resleeper, Reballast, Formation - Trax - 172yds | 24 | 1706 | 25 | 118 | 172 | PLS-1819-213 - Changed from Cat 11 to Cat 14 and Milesage Changed from 24m1694y-25m290y to 24m1706y-25m290y. Possession times TBC. This job is now happening over 2 week's - Wk's 49 & 50 (subject to c/c approval). 30/08/17 GGannon reversed this back
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 49 | 145803 | A349240 | 31500516 | Balmossie Up | 11 | 1100 | ECN3 | Weekend | W2019/5889696 | 2019-03-02 23:50 | 2019-03-04 04:50 | 1 day(s) 05:00 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 436y) | 4 | 1642 | 5 | 318 | 436
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 49 | 145803 | A2861970 | MED REFURB | Medium Refurb | 3 | 2100 | SCM3 | Weekend | W2019/5890109 | 2019-03-03 00:01 | 2019-03-08 20:01 | 5 day(s) 20:00 Hrs | Medium Refurb | 120 | 1402 | 121 | 234 | 377
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 49 | 145803 | A2879940 | NV31195020 | Greenhill Lower Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2019-03-03 00:01 | 2019-03-03 08:01 | 0 day(s) 08:00 Hrs | CORE: 1st CW | 106 | 866 | 106 | 966 | 100 | Falldown recovery from 17/18 (+400 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 49 | 145803 | A2858400 | 32100118 | Howwood Station Up | 11 | 1100 | AYR3 | Weekend | W2019/5890109 | 2019-03-03 00:35 | 2019-03-04 05:30 | 1 day(s) 04:55 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 1034y) | 12 | 1463 | 13 | 220 | 517
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 50 | 157839 | A2473030 | 134028B 17 | Willey Moor Bridge Pt 2 | 11 | 3100 | HBS | Weekend | W2018/6003408 | 2019-03-08 22:05 | 2019-03-11 06:00 | 2 day(s) 07:55 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 131yds | 41 | 880 | 41 | 1011 | 131 | PLN-1920-027 | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 50 | 157839 | A2484840 | 134028B 17 | Willey Moor Bridge Pt 2 | 16 | 3100 | HBS | Weekend | W2018/6003408 | 2019-03-08 22:05 | 2019-03-11 06:00 | 2 day(s) 07:55 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify (all non steel sleeper types) : 929yds | 40 | 781 | 41 | 880 | 929 | PLN-1920-027 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | A950700 | 51220313 | Scours to Tilehurst | 2 | 2200 | MLN1 | Weekend | W2018/5802443 | 2019-03-09 00:01 | 2019-03-11 00:01 | 2 day(s) 00:00 Hrs | CORE: 1st CW (Rerail - Both Rails) Cat:02 | 37 | 1540 | 38 | 560 | 780
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 50 | 145803 | A164110 | 32100718A | Dalry South A | 11 | 1100 | AYR3 | Weekend | W2019/5893255 | 2019-03-09 00:45 | 2019-03-11 05:30 | 2 day(s) 04:45 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 660y) | 22 | 1100 | 23 | 0 | 660
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 50 | 145803 | A165100 | 32100618B | Dalry South B | 11 | 1100 | AYR4 | Weekend | W2019/5893255 | 2019-03-09 00:45 | 2019-03-11 05:30 | 2 day(s) 04:45 Hrs | CORE: 1st CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 220y) | 23 | 0 | 23 | 220 | 220
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | A940400 | 51220612 | Tilehurst 2 | 2 | 1200 | MLN1 | Weekend | W2018/0000000 | 2019-03-09 01:00 | 2019-03-10 04:00 | 1 day(s) 03:00 Hrs | CORE: 2/2 CW (Rerail - Both Rails) Cat:02 | 38 | 595 | 39 | 1320 | 1106
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T413780 | 51220612 | Tilehurst 2 | 2 | 1200 | MLN1 | Weekend | W2018/0000000 | 2019-03-09 01:00 | 2019-03-10 01:00 | 1 day(s) 00:00 Hrs | CORE: 1/2 CW (Rerail - Both Rails) Cat:02 | 38 | 595 | 39 | 1320 | 1379
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432590 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Weekend | W2018/0000000 | 2019-03-09 01:00 | 2019-03-10 01:00 | 1 day(s) 00:00 Hrs | CORE: Cat 2: 158y (3159 tot) | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432640 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5849585 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 3rd CW (Rerail - Both Rails) Cat:02 M/T | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432650 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5849587 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 3rd CW (Rerail - Both Rails) Cat:02 T/W | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432660 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5849588 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 3rd CW (Rerail - Both Rails) Cat:02 W/T | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432670 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5849586 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 3rd CW (Rerail - Both Rails) Cat:02 T/F | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432680 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5849591 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 4th CW (Rerail - Both Rails) Cat:02 M/T | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432690 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5849593 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 4th CW (Rerail - Both Rails) Cat:02 T/W | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432700 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5849594 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 4th CW (Rerail - Both Rails) Cat:02 W/T | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432710 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/5849592 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 4th CW (Rerail - Both Rails) Cat:02 T/F | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432720 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 5th CW (Rerail - Both Rails) Cat:02 M/T | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432730 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 5th CW (Rerail - Both Rails) Cat:02 T/W | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432740 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 5th CW (Rerail - Both Rails) Cat:02 W/T | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432750 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 01:00 | 2019-03-09 09:00 | 0 day(s) 08:00 Hrs | CORE: 5th CW (Rerail - Both Rails) Cat:02 T/F | 41 | 1044 | 43 | 683 | 157
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T407900 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 01:30 | 2019-03-10 01:30 | 1 day(s) 00:00 Hrs | CORE: 1st CW (Rerail - Both Rails) Cat:02 M/T | 41 | 1044 | 43 | 683 | 158
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432570 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 01:30 | 2019-03-10 01:30 | 1 day(s) 00:00 Hrs | CORE: 1st CW (Rerail - Both Rails) Cat:02 T/W | 41 | 1044 | 43 | 683 | 158
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 50 | 148324 | A931380 | 41500218 | Ilford Flyover | 2 | 1152 | LTN1 | Weekend | W2018/5901045 | 2019-03-09 02:00 | 2019-03-11 04:00 | 2 day(s) 02:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 6 | 1351 | 6 | 1353 | 2 | CC ref: EA-1819-35 | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 50 | 148324 | A931390 | 41500218 | Ilford Flyover | 2 | 1152 | LTN1 | Weekend | W2018/5901045 | 2019-03-09 02:00 | 2019-03-11 04:00 | 2 day(s) 02:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 6 | 1573 | 6 | 1730 | 157 | CC ref: EA-1819-35 | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 50 | 148324 | A931400 | 41500218 | Ilford Flyover | 1 | 1152 | LTN1 | Weekend | W2018/5901045 | 2019-03-09 02:00 | 2019-03-11 04:00 | 2 day(s) 02:00 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 6 | 1730 | 7 | 139 | 169 | CC ref: EA-1819-35 | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 50 | 148324 | G4T378820 | 41500218 | Ilford Flyover | 11 | 1152 | LTN1 | Weekend | W2018/5901045 | 2019-03-09 02:00 | 2019-03-11 04:00 | 2 day(s) 02:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 6 | 1353 | 6 | 1573 | 220 | CC ref: EA-1819-35 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432580 | 51222213 | Pangbourne to Goring | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 06:00 | 2019-03-09 06:00 | 0 day(s) 00:00 Hrs | CORE: 1st CW (Rerail - Both Rails) Cat:02 W/T | 41 | 1044 | 43 | 683 | 158
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 50 | 157792 | A2903810 | 21501218 | Blainscough DN Main | 14 | 2100 | CGJ5 | Weekend | W2018/000000 | 2019-03-09 21:50 | 2019-03-10 09:00 | 0 day(s) 11:10 Hrs | CORE: 2 of 2: Blainscough - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 130yds | 11 | 620 | 11 | 880 | 130
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T412800 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 1/3 (Rerail - Both Rails) Cat:02 M/T | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432390 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 1/3 (Rerail - Both Rails) Cat:02 T/W | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432400 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 1/3 (Rerail - Both Rails) Cat:02 W/T | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432410 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 1/3 (Rerail - Both Rails) Cat:02 T/F | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432420 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 2/3 (Rerail - Both Rails) Cat:02 M/T | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432430 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 2/3 (Rerail - Both Rails) Cat:02 T/W | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432440 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 2/3 (Rerail - Both Rails) Cat:02 W/T | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432450 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 2/3 (Rerail - Both Rails) Cat:02 T/F | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432460 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 3/3 (Rerail - Both Rails) Cat:02 M/T | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432470 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 3/3 (Rerail - Both Rails) Cat:02 T/W | 39 | 1278 | 41 | 220 | 205
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432480 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 3/3 (Rerail - Both Rails) Cat:02 W/T | 39 | 1278 | 41 | 220 | 206
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 50 | 148817 | G4T432490 | 51220413 | Tilehurst to Pangbourne | 2 | 2200 | MLN1 | Midweek Nights | W2018/0000000 | 2019-03-09 22:00 | 2019-03-10 06:00 | 0 day(s) 08:00 Hrs | CORE: 3/3 (Rerail - Both Rails) Cat:02 T/F | 39 | 1278 | 41 | 220 | 206
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 50 | 148273 | A945880 | 23500316 | Kilsby Tunnel Up | 14 | 1100 | LEC1 | Weekend | W2018/5939862 | 2019-03-09 22:10 | 2019-03-12 12:00 | 2 day(s) 13:50 Hrs | CORE: 3rd Core Kilsby Tunnel Up 147 Yards of Cat14 | 76 | 1320 | 77 | 0 | 147
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 50 | 157791 | A392650 | 23101118 | Milton Keynes North | 12 | 2100 | LEC1 | Weekend | W2018/5993448 | 2019-03-09 22:20 | 2019-03-10 14:20 | 0 day(s) 16:00 Hrs | CORE: 2 of 2 Reballast, Formation - Trax - Cat12 - 129yds | 50 | 981 | 50 | 1081 | 129
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 50 | 148316 | A2414360 | 121012 14 | Knebworth Stn Back Platform-1 | 14 | 2200 | ECM1 | Weekend | W2018/0000000 | 2019-03-09 23:00 | 2019-03-11 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 - Rerail, Resleeper, Reballast, Formation - Trax - 172yds | 25 | 118 | 25 | 290 | 172 | PLS-1819-213 - Changed from Cat 11 to Cat 14 and Milesage Changed from 24m1694y-25m290y to 24m1706y-25m290y. Possession times TBC. This job is now happening over 2 week's - Wk's 49 & 50 (subject to c/c approval). 30/08/17 GGannon reversed this back
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 50 | 145803 | A371600 | 31500516 | Balmossie Up | 11 | 1100 | ECN3 | Weekend | W2019/5889765 | 2019-03-09 23:50 | 2019-03-11 05:25 | 1 day(s) 05:35 Hrs | CORE: 2nd CW (11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types 436y) | 5 | 318 | 5 | 754 | 436
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 50 | 145803 | A2880100 | NV31195020 | Greenhill Lower Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2019-03-10 00:01 | 2019-03-10 08:01 | 0 day(s) 08:00 Hrs | CORE: 2nd CW | 106 | 966 | 106 | 1066 | 100 | Falldown recovery from 17/18 (+400 yds) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 51 | 157839 | A2484850 | 23070A | Nafferton | 2 | 2100 | HBS | Weekend | W2018/6004618 | 2019-03-15 23:55 | 2019-03-18 05:30 | 2 day(s) 05:35 Hrs | CORE: CAT02: Rerail - both Rails: 25yds | 20 | 427 | 20 | 452 | 25 | Volume phasing TBC.
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 51 | 157839 | A7430 | 23070A | Nafferton | 14 | 2100 | HBS | Weekend | W2018/6004618 | 2019-03-15 23:55 | 2019-03-18 05:30 | 2 day(s) 05:35 Hrs | CORE: CAT14: Rerail, Resleeper, Reballast, Formation - Trax) : 390yds | 21 | 900 | 21 | 1290 | 390 | Volume phasing TBC.
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 51 | 157839 | A7440 | 23070A | Nafferton | 16 | 2100 | HBS | Weekend | W2018/6004618 | 2019-03-15 23:55 | 2019-03-18 05:30 | 2 day(s) 05:35 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify (all non steel sleeper types) : 736yds | 21 | 1290 | 22 | 266 | 736 | Volume phasing TBC.
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 51 | 148324 | G4T391460 | 41505810 | Bishopsgate Tunnel Dn Suburban 1819 | 14 | 2154 | LTN1 | Weekend | W2018/000000 | 2019-03-16 00:01 | 2019-03-18 04:01 | 2 day(s) 04:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax Cat:14 | 0 | 531 | 0 | 600 | 69
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 51 | 148324 | G4T393410 | 41505810 | Bishopsgate Tunnel Dn Suburban 1819 | 2 | 2154 | LTN1 | Weekend | W2018/000000 | 2019-03-16 00:01 | 2019-03-18 04:01 | 2 day(s) 04:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 0 | 600 | 0 | 611 | 11
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 51 | 148324 | G4T393420 | 41505810 | Bishopsgate Tunnel Dn Suburban 1819 | 44A | 2154 | LTN1 | Weekend | W2018/000000 | 2019-03-16 00:01 | 2019-03-18 04:01 | 2 day(s) 04:00 Hrs | CORE: 1/1 Baseplate Changing Cat:44A | 0 | 600 | 0 | 611 | 11
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 51 | 148324 | G4T393430 | 41505810 | Bishopsgate Tunnel Dn Suburban 1819 | 14 | 2154 | LTN1 | Weekend | W2018/000000 | 2019-03-16 00:01 | 2019-03-18 04:01 | 2 day(s) 04:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax Cat:14 | 0 | 611 | 0 | 815 | 204
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 51 | 148324 | A922880 | 41501713sf1 | Forest Gate Dn | 11 | 2100 | LTN1 | Weekend | W2018/0000000 | 2019-03-16 01:00 | 2019-03-18 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 5 | 1424 | 6 | 206 | 542
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 18/19 | 51 | 148324 | G4T387900 | 41501713sf1 | Forest Gate Dn | 2 | 2100 | LTN1 | Weekend | W2018/0000000 | 2019-03-16 01:00 | 2019-03-18 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 6 | 206 | 6 | 222 | 16
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 51 | 157791 | A340370 | 23352511 | Kings Langley | 11 | 2100 | LEC1 | Weekend | W2018/5931018 | 2019-03-16 20:00 | 2019-03-17 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat11 - 155yds - 50mph TSR | 21 | 290 | 21 | 445 | 155
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 51 | 157792 | A2454430 | COT21480114s | Blainscough Up Main | 14 | 1100 | CGJ5 | Weekend | W2018/000000 | 2019-03-16 21:50 | 2019-03-17 09:00 | 0 day(s) 11:10 Hrs | CORE: 1 of 2: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 150yds | 14 | 500 | 14 | 650 | 150 | CC Ref LNWPL-1920-045
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 51 | 148273 | G4T414900 | 23501918 | Kilsby Tunnel Up Refurb | 16 | 1100 | LEC1 | Weekend | W2018/5989319 | 2019-03-16 22:10 | 2019-03-17 08:05 | 0 day(s) 09:55 Hrs | CORE: 1st Core Kilsby Tunnel Tunnel Up Refurb 200 Yards of CAT16 | 77 | 0 | 77 | 200 | 200 | Approved Change Control D63 - Remove from 18/19 and Add to unassigned. LP 02.06.16. | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 51 | 148817 | G4T160940 | 51100214 | Hayes & Harlington Station | 14 | 2100 | MLN1 | Weekend | W2018/5830819 | 2019-03-16 23:00 | 2019-03-18 03:00 | 1 day(s) 04:00 Hrs | CORE: 1/4 CW (CAT 14 Rerail, Resleeper, Reballast,Formation - Trax) | 10 | 1510 | 11 | 300 | 550
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 51 | 148817 | G4T415670 | 51100214 | Hayes & Harlington Station | 14 | 2100 | MLN1 | Weekend | W2018/5830819 | 2019-03-16 23:00 | 2019-03-18 05:00 | 1 day(s) 06:00 Hrs | CORE: 1/4 CW (CAT 14 Rerail, Resleeper, Reballast,Formation - Trax) | 10 | 1100 | 10 | 1320 | 220
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 51 | 148316 | A2409170 | 121042 | Stanborough | 2 | 1100 | ECM1 | Weekend | W2018/0000000 | 2019-03-16 23:00 | 2019-03-18 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 2 - Rerail - Both Rails 10yds | 19 | 1102 | 19 | 1112 | 10 | Approved Change Control PLS-1819-206. Bring Job into work bank from 17/18. Possession times TBC. Job to move to Wk's 51 & 52 (subject to c/c approval). | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 51 | 148316 | A2410030 | 121042 | Stanborough | 2 | 1100 | ECM1 | Weekend | W2018/0000000 | 2019-03-16 23:00 | 2019-03-18 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 2 - Rerail - Both Rails 6yds | 20 | 280 | 20 | 286 | 6 | Approved Change Control PLS-1819-206. Bring Job into work bank from 17/18. Possession times TBC. Job to move to Wk's 51 & 52 (subject to c/c approval). | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 51 | 148316 | A2411210 | 121042 | Stanborough | 11 | 1100 | ECM1 | Weekend | W2018/0000000 | 2019-03-16 23:00 | 2019-03-18 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 464yds | 19 | 1576 | 20 | 280 | 464 | Approved Change Control PLS-1819-206. Bring Job into work bank from 17/18. Possession times TBC. Job to move to Wk's 51 & 52 (subject to c/c approval). | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 51 | 145803 | A2880110 | NV31195020 | Greenhill Lower Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2019-03-17 00:01 | 2019-03-17 08:01 | 0 day(s) 08:00 Hrs | CORE: 3rd CW | 106 | 1066 | 106 | 1166 | 100 | Falldown recovery from 17/18 (+400 yds) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 51 | 145803 | A2448180 | 31500317 | Blackhills Up | 14 | 1100 | ECN5 | Weekend | W2019/5889436 | 2019-03-17 00:20 | 2019-03-18 05:15 | 1 day(s) 04:55 Hrs | CORE: 1st CW (13 - Formation, Reballast, Resleeper - Trax (all non steel sleeper types) 171y) | 228 | 160 | 228 | 651 | 491
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 52 | 157839 | A12570 | 23070A | Nafferton | 16 | 2100 | HBS | Weekend | W2018/6004625 | 2019-03-22 23:55 | 2019-03-25 05:30 | 2 day(s) 05:35 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify (all non steel sleeper types) : 736yds | 22 | 1002 | 22 | 1738 | 736 | Volume phasing TBC.
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 52 | 157839 | A8290 | 23070A | Nafferton | 16 | 2100 | HBS | Weekend | W2018/6004625 | 2019-03-22 23:55 | 2019-03-25 05:30 | 2 day(s) 05:35 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify (all non steel sleeper types) : 736yds | 22 | 266 | 22 | 1002 | 736 | Volume phasing TBC.
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10450 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 1042 | 23 | 1062 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10680 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 1 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 23 | 1673 | 23 | 1683 | 10
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10690 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 1 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 24 | 210 | 24 | 229 | 19
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10700 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 1 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 24 | 664 | 24 | 683 | 19
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10710 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 1062 | 23 | 1072 | 10
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10720 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 1251 | 23 | 1271 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10730 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 1445 | 23 | 1465 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10740 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 1465 | 23 | 1475 | 10
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10750 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 442 | 24 | 462 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10760 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 462 | 24 | 482 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10770 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 683 | 24 | 703 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10780 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 703 | 24 | 713 | 10
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10790 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 767 | 24 | 787 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10800 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 2 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 943 | 24 | 963 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G9590 | SVOAKSRR002 (Down) | Sevenoaks Re-Railing (Down) | 1 | 2100 | XTD | Weekend | W2019/000000 | 2019-03-23 00:01 | 2019-03-25 09:01 | 2 day(s) 09:00 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 23 | 1653 | 23 | 1673 | 20
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 18/19 | 52 | 157839 | A2484870 | 131020 SF2 | Ulgham Grange | 2 | 2100 | ECM7 | Weekend | W2018/5955217 | 2019-03-23 00:25 | 2019-03-23 00:25 | 0 day(s) 00:00 Hrs | CORE: CAT02: Rerail (Both Rails): 83yds - Removed as per CC (See Notes) | 22 | 896 | 22 | 979 | 0 | PLN-1920-030. PLN-1819-110 (Spec CAT11 - 709yds) - CAT02 removed | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 52 | 148817 | A946310 | 51200611 | Hungerford Common | 13 | 1100 | BHL | Weekend | W2018/6046052 | 2019-03-23 00:30 | 2019-03-27 04:45 | 4 day(s) 04:15 Hrs | CORE: 1st CW (Resleeper, Reballast, Formation-Trax | 60 | 374 | 60 | 11 | 726 |  | CR
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 52 | 145803 | A368390 | FD32101815 SF1 | Saltcoats High Flats 15/16 Shortfall | 11 | 1100 | LGS1 | Weekend | W2019/5885792 | 2019-03-23 01:00 | 2019-03-25 05:40 | 2 day(s) 04:40 Hrs | CORE: 1st CW (14 -Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) 676y) | 29 | 905 | 29 | 1571 | 666 | 02/05/18 - Redate week 52, from week 51 smoothing as EAS version 3 | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | A12850 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 1 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 23 | 1579 | 23 | 1599 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10540 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 1243 | 23 | 1253 | 10
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10550 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 1253 | 23 | 1273 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10560 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 1431 | 23 | 1450 | 19
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10570 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 23 | 1450 | 23 | 1470 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10580 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 215 | 24 | 235 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10590 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 443 | 24 | 463 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10600 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 463 | 24 | 483 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10610 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 682 | 24 | 692 | 10
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10620 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 692 | 24 | 712 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10630 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 712 | 24 | 732 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10640 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 2 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 934 | 24 | 954 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10650 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 1 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 23 | 1650 | 23 | 1660 | 10
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10660 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 1 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 23 | 1660 | 23 | 1680 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G10670 | SVOAKSRR001 (UP) | Sevenoaks Re-Railing (Up Road) | 1 | 1100 | XTD | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-23 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 24 | 530 | 24 | 550 | 20
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G4T2370 | 43300319 | Horley Up Fast | 11 | 1100 | VTB3 | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-25 04:00 | 2 day(s) 03:00 Hrs | CORE: Re-Rail, Re-Sleeper, Re-ballast - Trax | 25 | 1056 | 26 | 264 | 968 | SUS-1819-72 | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G4T3320 | 43300319 | Horley Up Fast | 2 | 1100 | VTB3 | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-25 04:00 | 2 day(s) 03:00 Hrs | CORE: Re-Rail Both Rails | 25 | 1040 | 25 | 1056 | 16 | SUS-1819-72 | APC
Bradfield, Ms Hailey | Plain Line | ENHANCE | South East Multi Route | Colas | Tonbridge | 18/19 | 52 | 155890 | G4T3330 | 43300319 | Horley Up Fast | 2 | 1100 | VTB3 | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-25 04:00 | 2 day(s) 03:00 Hrs | CORE: Re-Rail Both Rails | 26 | 264 | 26 | 267 | 3 | SUS-1819-72 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 52 | 148309 | A936160 | 42400318 | Honor Oak Park to Forest Hill Up Slow | 11 | 1200 | LBW | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-25 03:45 | 2 day(s) 02:45 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 866 | 5 | 0 | 894 | KENT-1819-61 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 52 | 148309 | G4T121530 | 42400318 | Honor Oak Park to Forest Hill Up Slow | 2 | 1200 | LBW | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-25 03:45 | 2 day(s) 02:45 Hrs | CORE: 1/1 Re-Rail both Rails Cat:02 | 4 | 855 | 4 | 866 | 11 | KENT-1819-61 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 18/19 | 52 | 148309 | G4T121540 | 42400318 | Honor Oak Park to Forest Hill Up Slow | 2 | 1200 | LBW | Weekend | W2019/000000 | 2019-03-23 01:00 | 2019-03-25 03:45 | 2 day(s) 02:45 Hrs | CORE: 1/1 Re-Rail both Rails Cat:02 | 5 | 0 | 5 | 11 | 11 | KENT-1819-61 | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 52 | 148817 | A944230 | 51401219 | Crofton-Savernake | 11 | 1100 | BHL | Weekend | W2018/0000000 | 2019-03-23 01:00 | 2019-03-24 04:00 | 1 day(s) 03:00 Hrs | CORE: 1st CW (Rerail, Resleeper, Reballast-Trax) CAT 11 | 70 | 94 | 70 | 55 | 456 |  | CR
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 52 | 157843 | A14250 | 44300312 | Fulwell Station Up Platform | 11 | 1100 | NMS2 | Weekend |  | 2019-03-23 01:00 | 2019-03-24 05:00 | 1 day(s) 04:00 Hrs | CORE: 2nd CW 187yds | 12 | 1293 | 12 | 1478 | 187
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 18/19 | 52 | 157843 | A3270 | 44300312 | Fulwell Station Up Platform | 14 | 1100 | NMS2 | Weekend |  | 2019-03-23 01:00 | 2019-03-24 05:00 | 1 day(s) 04:00 Hrs | CORE: 1st CW 333yds | 12 | 1478 | 13 | 51 | 333
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 18/19 | 52 | 157791 | A66120 | 23100319 | COT Bletchley Park | 12 | 1200 | LEC1 | Weekend | W2018/5989321 | 2019-03-23 20:00 | 2019-03-24 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Reballast, Formaion -Trax - CAT12 -140yds | 46 | 1650 | 47 | 30 | 140
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 18/19 | 52 | 157792 | A2903660 | COT21480114s | Blainscough Up Main | 14 | 1100 | CGJ5 | Weekend | W2018/000000 | 2019-03-23 21:50 | 2019-03-24 09:00 | 0 day(s) 11:10 Hrs | CORE: 2 of 2: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 150yds | 14 | 650 | 14 | 800 | 150 | CC Ref LNWPL-1920-045
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 18/19 | 52 | 148817 | G4T415680 | 51100214 | Hayes & Harlington Station | 11 | 2100 | MLN1 | Weekend | W2018/5830823 | 2019-03-23 23:00 | 2019-03-26 05:00 | 2 day(s) 06:00 Hrs | CORE:2/4 CW (CAT 11 Rerail, Resleeper, Reballast - Trax) | 10 | 1320 | 10 | 1510 | 190
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Carillion Rail | Peterborough | 18/19 | 52 | 148316 | A2409180 | 121042 | Stanborough | 11 | 1100 | ECM1 | Weekend | W2018/0000000 | 2019-03-23 23:00 | 2019-03-25 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax- 464yds | 19 | 1112 | 19 | 1576 | 464 | Approved Change Control PLS-1819-206. Bring Job into work bank from 17/18. Possession times TBC. Job to move to Wk's 51 & 52 (subject to c/c approval). | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 18/19 | 52 | 145803 | A2880120 | NV31195020 | Greenhill Lower Drain | 15ba | 1100 | GSW | Weekend | W2018/5796959 | 2019-03-24 00:01 | 2019-03-24 08:01 | 0 day(s) 08:00 Hrs | CORE: 4th CW | 106 | 1166 | 106 | 1266 | 100 | Falldown recovery from 17/18 (+400 yds) | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 1 | 154931 | A3150 | 43401418 | Burgess Hill to Hassocks (Dn) | 14 | 2100 | VTB3 | Weekend | W2019/6065890 | 2019-03-30 01:20 | 2019-04-01 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 42 | 22 | 42 | 440 | 418 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 1 | 154931 | G1370 | 43401418 | Burgess Hill to Hassocks (Dn) | 2 | 2100 | VTB3 | Weekend | W2019/6065890 | 2019-03-30 01:20 | 2019-04-01 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 41 | 1329 | 42 | 1346 | 17 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 1 | 154931 | G4T33430 | 43401418 | Burgess Hill to Hassocks (Dn) | 11 | 2100 | VTB3 | Weekend | W2019/6065890 | 2019-03-30 01:20 | 2019-04-01 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 42 | 1346 | 42 | 22 | 436 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 1 | 154931 | G1380 | 43401418 | Burgess Hill to Hassocks (Dn) | 2 | 2100 | VTB3 | Weekend | W2019/6065890 | 2019-03-30 01:30 | 2019-04-01 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 42 | 440 | 42 | 457 | 17 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 1 | 154929 | A933900 | 4150112df2 | Manor Park Dn (19/20) | 11 | 2100 | LTN1 | Weekend | W2019/0000000 | 2019-03-30 01:30 | 2019-04-01 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 6 | 587 | 6 | 880 | 293
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 1 | 154929 | A933910 | 4150112df2 | Manor Park Dn (19/20) | 11 | 2100 | LTN1 | Weekend | W2019/0000000 | 2019-03-30 01:30 | 2019-04-01 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 6 | 880 | 6 | 1017 | 137
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 1 | 154929 | A934760 | 4150112df2 | Manor Park Dn (19/20) | 2 | 2100 | LTN1 | Weekend | W2019/0000000 | 2019-03-30 01:30 | 2019-04-01 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 6 | 571 | 6 | 587 | 16
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 1 | 154334 | A36450 | 113180 | Gas House Curve | 11 | 2100 | TES | Weekend | W2019/5739386 | 2019-03-30 23:00 | 2019-04-01 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11 - Reballast, Resleeper, Rerail - Trax - 339yds | 0 | 144 | 0 | 483 | 339 | Volume amended as per agreed C/C ref: PLS-1920-106 (rerailing added) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 1 | 154343 | A271410 | 31103019 | Livingston North East | 13 | 2100 | NBE | Weekend |  | 2019-03-31 00:01 | 2019-04-01 05:01 | 1 day(s) 05:00 Hrs | CORE: Livingston North East [Week 01] Cat 13:337 yds | 29 | 1320 | 29 | 1657 | 337
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 1 | 154343 | A1410 | 32300218a | Rutherglen Coup South | 11 | 2100 | WCM2 | Weekend |  | 2019-04-01 00:01 | 2019-04-02 05:01 | 1 day(s) 05:00 Hrs | CORE: Rutherglen Coup South [Week 01] Cat 11:564 yds | 98 | 1382 | 99 | 186 | 564 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 1 | 154146 | WES491270 | 52202011 | Yatton Down Main | 14 | 2100 | MLN1 | Weekend | W2019/0000000 | 2019-04-01 01:00 | 2019-04-02 04:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 130 | 413 | 130 | 833 | 420
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 1 | 154146 | WES501580 | 52202011 | Yatton Down Main | 2 | 2100 | MLN1 | Weekend | W2019/0000000 | 2019-04-01 01:00 | 2019-04-02 04:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 130 | 833 | 130 | 873 | 40
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 2 | 154335 | A2450090 | 124191 | East Bank Tunnel | 14 | 1100 | TJC1 | Weekend | W2019/5739446 | 2019-04-06 01:00 | 2019-04-07 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 232yds | 157 | 1600 | 158 | 72 | 232
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 2 | 154931 | G1390 | 43401518 | Burgess Hill to Hassocks (Dn2) | 2 | 2100 | VTB3 | Weekend | W2019/6065938 | 2019-04-06 01:20 | 2019-04-08 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 42 | 816 | 42 | 833 | 17 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 2 | 154931 | G1400 | 43401518 | Burgess Hill to Hassocks (Dn2) | 2 | 2100 | VTB3 | Weekend | W2019/6065938 | 2019-04-06 01:20 | 2019-04-08 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 42 | 1034 | 42 | 1051 | 17 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 2 | 154931 | G4T42250 | 43401518 | Burgess Hill to Hassocks (Dn2) | 11 | 2100 | VTB3 | Weekend | W2019/6065938 | 2019-04-06 01:20 | 2019-04-08 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 42 | 833 | 42 | 1034 | 201 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 2 | 154146 | A35960 | 51400319 | Trowbridge-1 | 2 | 1100 | WEY | Weekend |  | 2019-04-06 08:00 | 2019-04-07 | 0 day(s) 16:00 Hrs | CORE: 1st CW Rerail Both Rails | 104 | 1276 | 105 | 1180 | 1664
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 2 | 154146 | A27170 | 51443416 | Quarry Jcn | 7 | 3100 | ESB | Weekend | W2019/0000000 | 2019-04-06 12:20 | 2019-04-07 21:20 | 1 day(s) 09:00 Hrs | CORE: 1/2 Reballast - Traxcavation Cat:07 | 3 | 1100 | 3 | 1210 | 110
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 2 | 154146 | A27180 | 51443416 | Quarry Jcn | 15a | 3100 | ESB | Weekend | W2019/0000000 | 2019-04-06 12:20 | 2019-04-07 21:20 | 1 day(s) 09:00 Hrs | CORE: 1/2 Drain (Associated with Track Renewal) Cat:15A | 3 | 1110 | 3 | 1215 | 105
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 2 | 154341 | A339330 | 23303117s | COT Berkhampstead North | 14 | 1200 | LEC1 | Weekend | W2019/6061112 | 2019-04-06 20:00 | 2019-04-07 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 170yds | 28 | 170 | 28 | 340 | 170
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 2 | 154334 | A51800 | 113180 | Gas House Curve | 2 | 2100 | TES | Weekend | W2019/5824937 | 2019-04-06 23:00 | 2019-04-08 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 02 - Rerail - 144yds | 0 | 0 | 0 | 144 | 144 | Volume amended as per agreed C/C ref: PLS-1920-106 (rerailing added) | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 2 | 154334 | A51850 | 113180 | Gas House Curve | 2 | 2100 | TES | Weekend | W2019/5824937 | 2019-04-06 23:00 | 2019-04-08 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 02 - Rerail - 73yds | 0 | 483 | 0 | 556 | 73 | Volume amended as per agreed C/C ref: PLS-1920-106 (rerailing added) | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 2 | 154334 | A51860 | 113180 | Gas House Curve | 1 | 2100 | TES | Weekend | W2019/5824937 | 2019-04-06 23:00 | 2019-04-08 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 01 - Rerail (Single rail) - 12yds | 0 | 556 | 0 | 568 | 12 | Volume amended as per agreed C/C ref: PLS-1920-106 (rerailing added) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 2 | 154343 | A2867010 | 32203118 | Dryffe Water Viaduct | 11 | 2100 | WCM1 | Weekend |  | 2019-04-07 00:01 | 2019-04-08 03:01 | 1 day(s) 03:00 Hrs | CORE: Soddom Dn [Week 04] Cat 11:700 yds | 27 | 56 | 27 | 637 | 581 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 2 | 154343 | A291320 | 32300218a | Rutherglen Coup South | 11 | 2100 | WCM2 | Weekend |  | 2019-04-07 00:01 | 2019-04-08 05:01 | 1 day(s) 05:00 Hrs | CORE: Rutherglen Coup South [Week 02] Cat 11:563 yds | 99 | 186 | 99 | 749 | 563 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 2 | 154335 | A2476310 | 124189 | Dore South - Dore West | 11 | 3100 | MAS | Weekend | W2019/5732149 | 2019-04-07 00:05 | 2019-04-08 07:40 | 1 day(s) 07:35 Hrs | CORE: CAT11 : Rerail, Resleeper, Reballast - Trax : 401yds | 153 | 1660 | 154 | 301 | 401 | PLN-1920-053. Phasing per weekend required. | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 2 | 154335 | A2484550 | 124189 | Dore South - Dore West | 2 | 3100 | MAS | Weekend | W2019/5732149 | 2019-04-07 00:05 | 2019-04-08 07:40 | 1 day(s) 07:35 Hrs | CORE: CAT02 : Rerail (Both Rails) : 6yds | 153 | 1654 | 153 | 1660 | 6 | PLN-1920-053. Phasing per weekend required. | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 2 | 154934 | G4T14610 | 44401714 | Blackwater station | 11 | 2100 | GTW2 | Weekend | P2019/6065038 | 2019-04-07 00:45 | 2019-04-08 04:00 | 1 day(s) 03:15 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 55 | 1186 | 55 | 1381 | 195 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 2 | 154146 | A25960 | 51140719 | Paddington Platform 11-1 | 2 | 3611 | MLN1 | Weekend | W2019/0000000 | 2019-04-10 01:00 | 2019-04-10 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 0 | 68 | 0 | 268 | 200
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 3 | 154146 | A19630 | 51443416 | Quarry Jcn | 15a | 3100 | ESB | Weekend | W2019/0000000 | 2019-04-13 01:00 | 2019-04-14 21:20 | 1 day(s) 20:20 Hrs | CORE: 2/2 Drain (Associated with Track Renewal) Cat:15A | 3 | 1215 | 3 | 1320 | 105
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 3 | 154335 | A2487030 | 124191 | East Bank Tunnel | 14 | 1100 | TJC1 | Weekend | W2019/5739446 | 2019-04-13 01:00 | 2019-04-14 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 232yds | 158 | 72 | 158 | 304 | 232
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 3 | 154931 | G4T166940 | 43101512 | Thornton Heath to Selhurst | 14 | 2100 | VTB1 | Weekend | W2019/000000 | 2019-04-13 01:20 | 2019-04-15 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 8 | 660 | 8 | 1320 | 660
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 3 | 154931 | G4T168040 | 43101512 | Thornton Heath to Selhurst | 2 | 2100 | VTB1 | Weekend | W2019/000000 | 2019-04-13 01:20 | 2019-04-15 04:00 | 2 day(s) 02:40 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 8 | 647 | 8 | 660 | 13
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 3 | 154929 | G4T392840 | 41100118 | West Ham Up | 11 | 1100 | FSS1 | Weekend | W2019/0000000 | 2019-04-13 01:25 | 2019-04-15 04:00 | 2 day(s) 02:35 Hrs | CORE: 1/3 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 1741 | 4 | 102 | 121
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 3 | 154929 | OLD1150 | 41100118 | West Ham Up | 2 | 1100 | FSS1 | Weekend | W2019/0000000 | 2019-04-13 01:25 | 2019-04-15 04:00 | 2 day(s) 02:35 Hrs | CORE: 1/3 Rerail - Both Rails Cat:02 | 3 | 1739 | 3 | 1741 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 3 | 154929 | A936000 | 41219920df1 | Stowmarket 1100 | 15aa | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-04-13 01:45 | 2019-04-15 04:55 | 2 day(s) 03:10 Hrs | CORE: 1/4 Drainage - Associated Renewal P01 | 80 | 1215 | 80 | 725 | 490 | Staging of works amended to ensure the priority section through the Platform is delivered. CC ref: EA-1920-38 applies
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 3 | 154146 | A18770 | 51443416 | Quarry Jcn | 7 | 3100 | ESB | Weekend | W2019/0000000 | 2019-04-13 12:20 | 2019-04-14 21:20 | 1 day(s) 09:00 Hrs | CORE: 2/2 Reballast - Traxcavation Cat:07 | 3 | 1210 | 3 | 1320 | 110
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 3 | 154339 | A2901640 | COT21304199 | Eden valley | 14 | 2100 | CGJ7 | Weekend |  | 2019-04-13 21:40 | 2019-04-14 11:00 | 0 day(s) 13:20 Hrs | CORE: 1 of 2: Cat 14 - Reballast, Resleeper, Rerail - Trax - 185yds | 47 | 1430 | 47 | 1615 | 185
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 3 | 158412 | A2457720 | 23512499 | COT Lodge Lane | 15aa | 2100 | HNR | Weekend | W2019/6046797 | 2019-04-13 22:00 | 2019-04-14 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT Lodge Lane - CAT15aa - 220yds | 74 | 880 | 74 | 1100 | 220
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 3 | 154338 | A14330 | 122110 | Peterborough | 2 | 1150 | PMJ | Weekend |  | 2019-04-13 23:00 | 2019-04-15 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 2: Rerail - Both Rails - 13yds | 21 | 1607 | 21 | 1620 | 13 | CC PLS-1920-051 - Amend from all CAT14 to 107y CAT 14, 13y CAT 2, 20y CAT 2, 53y CAT 14, 20y CAT2
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 3 | 154338 | A14340 | 122110 | Peterborough | 2 | 1150 | PMJ | Weekend |  | 2019-04-13 23:00 | 2019-04-15 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 2: Rerail - Both Rails - 20yds | 21 | 1666 | 21 | 1686 | 20 | CC PLS-1920-051 - Amend from all CAT14 to 107y CAT 14, 13y CAT 2, 20y CAT 2, 53y CAT 14, 20y CAT2
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 3 | 154338 | A14350 | 122110 | Peterborough | 14 | 1150 | PMJ | Weekend |  | 2019-04-13 23:00 | 2019-04-15 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax - 53yds | 21 | 1686 | 21 | 1739 | 53 | CC PLS-1920-051 - Amend from all CAT14 to 107y CAT 14, 13y CAT 2, 20y CAT 2, 53y CAT 14, 20y CAT2
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 3 | 154338 | A14360 | 122110 | Peterborough | 2 | 1150 | PMJ | Weekend |  | 2019-04-13 23:00 | 2019-04-15 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 2: Rerail - Both Rails - 20yds | 21 | 1739 | 21 | 1759 | 20 | CC PLS-1920-051 - Amend from all CAT14 to 107y CAT 14, 13y CAT 2, 20y CAT 2, 53y CAT 14, 20y CAT2
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 3 | 154338 | A9410 | 122110 | Peterborough | 14 | 1150 | PMJ | Weekend |  | 2019-04-13 23:00 | 2019-04-15 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax - 107yds | 21 | 1500 | 21 | 1607 | 107 | CC PLS-1920-051 - Amend from all CAT14 to 107y CAT 14, 13y CAT 2, 20y CAT 2, 53y CAT 14, 20y CAT2
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 3 | 154341 | A323730 | 23501219 | COT Lodge Lane | 12 | 2100 | HNR | Weekend | W2019/6046797 | 2019-04-13 23:55 | 2019-04-15 05:00 | 1 day(s) 05:05 Hrs | CORE: 1 of 1 Reballast, Formation - Trax - Cat12 - 250yds | 74 | 880 | 74 | 1130 | 250 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 3 | 154343 | A291330 | 32300218a | Rutherglen Coup South | 11 | 2100 | WCM2 | Weekend |  | 2019-04-14 00:01 | 2019-04-15 05:01 | 1 day(s) 05:00 Hrs | CORE: Rutherglen Coup South [Week 03] Cat 11:563 yds | 98 | 749 | 99 | 1312 | 563 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 3 | 154335 | A2484560 | 124189 | Dore South - Dore West | 2 | 3100 | MAS | Weekend | W2019/5732151 | 2019-04-14 00:05 | 2019-04-15 07:40 | 1 day(s) 07:35 Hrs | CORE: CAT02 : Rerail (Both Rails) : 9yds | 154 | 301 | 154 | 310 | 9 | PLN-1920-053. Phasing per weekend required. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 3 | 154343 | A2867930 | 32203118 | Dryffe Water Viaduct | 11 | 2100 | WCM1 | Weekend |  | 2019-04-14 01:00 | 2019-04-15 04:00 | 1 day(s) 03:00 Hrs | CORE: Soddom Dn [Week 05] Cat 11:380 yds | 27 | 637 | 27 | 1218 | 581 |  | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 3 | 154934 | G4T2130 | 44601513 | Worting Jn | 11 | 2200 | BML1 | Weekend |  | 2019-04-14 01:15 | 2019-04-15 03:00 | 1 day(s) 01:45 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 50 | 440 | 50 | 708 | 268
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 4 | 154929 | A933750 | 41100118 | West Ham Up | 11 | 1100 | FSS1 | Weekend | W2019/0000000 | 2019-04-19 01:25 | 2019-04-23 04:00 | 4 day(s) 02:35 Hrs | CORE: 2/3 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 102 | 4 | 128 | 26
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 4 | 154929 | G4T392850 | 41100118 | West Ham Up | 11 | 1100 | FSS1 | Weekend | W2019/0000000 | 2019-04-19 01:25 | 2019-04-23 04:00 | 4 day(s) 02:35 Hrs | CORE: 2/3 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 4 | 128 | 4 | 343 | 215
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 4 | 154341 | A351810 | RBS1210954s | Canley | 14 | 2100 | RBS1 | Weekend | W2019/WIP | 2019-04-19 01:40 | 2019-04-22 05:00 | 3 day(s) 03:20 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 981yds | 95 | 940 | 96 | 161 | 981
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 4 | 154335 | A2447090 | 124182 | Wellhouse Tunnel | 11 | 3100 | PEH | Weekend | W2018/5838039 | 2019-04-20 01:00 | 2019-04-21 07:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 240yds | 12 | 603 | 12 | 843 | 240 | PLN-1920-060 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 4 | 154931 | G4T167840 | 43101512 | Thornton Heath to Selhurst | 14 | 2100 | VTB1 | Weekend | W2019/000000 | 2019-04-20 01:20 | 2019-04-22 04:00 | 2 day(s) 02:40 Hrs | CORE: 2/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 8 | 1320 | 9 | 220 | 660 | SUS-1819-45 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 4 | 154931 | G4T168050 | 43101512 | Thornton Heath to Selhurst | 2 | 2100 | VTB1 | Weekend | W2019/000000 | 2019-04-20 01:20 | 2019-04-22 04:00 | 2 day(s) 02:40 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 9 | 220 | 9 | 233 | 13
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 4 | 154339 | A2905300 | COT21304199 | Eden valley | 14 | 2100 | CGJ7 | Weekend |  | 2019-04-20 21:40 | 2019-04-21 11:00 | 0 day(s) 13:20 Hrs | CORE: 2 of 2: Cat 14 - Reballast, Resleeper, Rerail - Trax - 185yds | 47 | 1615 | 48 | 40 | 185
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 4 | 154334 | A49600 | 114619 | Islip Street UM | 14 | 1100 | MCL | Weekend |  | 2019-04-20 23:00 | 2019-04-22 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 - Formation, Reballast, Resleeper, Rerail - Trax - 640yds | 3 | 110 | 3 | 750 | 640 | CC 2019/20 - 30/16/17 - Add to 1920 workbank, CC PLS-1920-045 Amend Milage to read 3m 110y to 3m 750y. Moved from Wk.9 to Wk.4 as per agreed C/C ref: PLS-1920-113.
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 4 | 154343 | A2861770 | FD32203317 | Bodsbury Level Crossing Down | 45A | 2100 | WCM1 | Weekend |  | 2019-04-21 00:01 | 2019-04-23 06:01 | 2 day(s) 06:00 Hrs | CORE: Bodsbury Level Crossing Down [Week 04] Cat 45A:0 yds | 51 | 1042 | 51 | 1051 | 0 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 4 | 154343 | A291340 | FD32203317 | Bodsbury Level Crossing Down | 11 | 2100 | WCM1 | Weekend |  | 2019-04-21 00:01 | 2019-04-23 06:01 | 2 day(s) 06:00 Hrs | CORE: Bodsbury Level Crossing Down [Week 04] Cat 11:107 yds | 51 | 997 | 51 | 1104 | 107 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 4 | 154343 | A291350 | 32203317b | Bodsbury Level Crossing Up | 45A | 1100 | WCM1 | Weekend |  | 2019-04-21 00:01 | 2019-04-23 06:01 | 2 day(s) 06:00 Hrs | CORE: Bodsbury Level Crossing Up [Week 04] Cat 45A:0 yds | 51 | 1042 | 51 | 1051 | 0 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 4 | 154343 | A4410 | 32203317b | Bodsbury Level Crossing Up | 11 | 1100 | WCM1 | Weekend |  | 2019-04-21 00:01 | 2019-04-23 06:01 | 2 day(s) 06:00 Hrs | CORE: Bodsbury Level Crossing Up [Week 04] Cat 11:120 yds | 51 | 980 | 51 | 1100 | 120 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 4 | 154343 | A6410 | 32202911 | Soddom Dn | 11 | 2100 | WCM1 | Weekend |  | 2019-04-21 00:01 | 2019-04-23 06:01 | 2 day(s) 06:00 Hrs | CORE: Soddom Dn [Week 04] Cat 11:700 yds | 48 | 961 | 48 | 1661 | 700 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 4 | 154335 | A2448090 | 124183 | Frickley | 11 | 1100 | SMJ2 | Weekend | W2019/5742425 | 2019-04-21 00:01 | 2019-04-22 05:00 | 1 day(s) 04:59 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 452yds | 12 | 1120 | 12 | 1572 | 452 | PLN-1920-092
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 4 | 154339 | A2646830 | 22700418 | Golborne | 14 | 1100 | CGJ4 | Weekend |  | 2019-04-21 00:30 | 2019-04-22 05:50 | 1 day(s) 05:20 Hrs | CORE: 1of 1: Cat 14 - Reballast, Resleeper, Rerail - Trax - 266yds | 186 | 1515 | 187 | 21 | 266
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 5 | 154343 | A2861740 | 32202911 | Soddom Dn | 11 | 2100 | WCM1 | Weekend |  | 2019-04-27 01:00 | 2019-04-29 07:00 | 2 day(s) 06:00 Hrs | CORE: Soddom Dn [Week 05] Cat 11:380 yds | 48 | 1661 | 49 | 281 | 380 |  | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 5 | 154934 | G4T5250 | 44200715df1 | Swaythling DM | 11 | 2100 | BML1 | Weekend |  | 2019-04-27 01:00 | 2019-04-29 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 75 | 110 | 75 | 1324 | 1214
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 5 | 154335 | A2484800 | 124182 | Wellhouse Tunnel | 11 | 3100 | PEH | Weekend | W2018/5377883 | 2019-04-27 01:00 | 2019-04-28 07:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 240yds | 12 | 843 | 12 | 1083 | 240 | PLN-1920-060 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 5 | 154334 | A22450 | 114006 | Harlington | 11 | 2200 | SPC1 | Weekend |  | 2019-04-27 23:00 | 2019-04-29 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11 - Reballast, Resleeper, Rerail - Trax - 90yds | 37 | 285 | 37 | 375 | 90 | CC PLS-1920-010 amend mileages from 37m320-37m580y to 37m285y-37m375y 90yds Cat 11 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 5 | 154334 | A40160 | 114006 | Harlington | 14 | 2200 | SPC1 | Weekend |  | 2019-04-27 23:00 | 2019-04-29 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 - Formation, Reballast, Resleeper, Rerail - Trax - 209yds | 37 | 375 | 37 | 584 | 209 | CC PLS-1920-010 amend mileages from 37m320-37m580y to 37m375y-37m584y 209yds Cat 14 | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 5 | 154335 | A2484670 | 124183 | Frickley | 11 | 1100 | SMJ2 | Weekend | W2019/5742479 | 2019-04-28 00:01 | 2019-04-29 05:00 | 1 day(s) 04:59 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 452yds | 12 | 1572 | 13 | 264 | 452 | PLN-1920-092.
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 6 | 154934 | G4T28130 | HV1017df2 | Havant Plat 2 | 11 | 2100 | WPH2 | Weekend |  | 2019-05-04 00:45 | 2019-05-07 04:00 | 3 day(s) 03:15 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 37 | 692 | 37 | 1163 | 471
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 6 | 154335 | A2484810 | 124182 | Wellhouse Tunnel | 11 | 3100 | PEH | Weekend | W2018/5762260 | 2019-05-04 01:00 | 2019-05-05 07:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Rerail, Resleeper, Reballast - Trax: 239yds | 12 | 1083 | 12 | 1322 | 239 | PLN-1920-060 | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 6 | 154929 | A933760 | 41100118 | West Ham Up | 11 | 1100 | FSS1 | Weekend | W2019/0000000 | 2019-05-04 01:25 | 2019-05-07 04:00 | 3 day(s) 02:35 Hrs | CORE: 3/3 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 4 | 343 | 4 | 450 | 107
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 6 | 154929 | A933770 | 41100118 | West Ham Up | 11 | 1100 | FSS1 | Weekend | W2019/0000000 | 2019-05-04 01:25 | 2019-05-07 04:00 | 3 day(s) 02:35 Hrs | CORE: 3/3 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 450 | 4 | 811 | 361
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 6 | 154929 | A933780 | 41100118 | West Ham Up | 2 | 1100 | FSS1 | Weekend | W2019/0000000 | 2019-05-04 01:25 | 2019-05-07 04:00 | 3 day(s) 02:35 Hrs | CORE: 3/3 Rerail - Both Rails Cat:02 | 4 | 811 | 4 | 877 | 66
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 6 | 154341 | A334130 | 23300318s | COT North Wembley UP | 12 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-05-04 02:00 | 2019-05-07 04:00 | 3 day(s) 02:00 Hrs | CORE: 1 of 1 Reballast, Formation - Trax - Cat12 - 675yds | 8 | 1065 | 8 | 1740 | 675
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 6 | 154339 | A2451740 | 22700114 | Coppull HallHABD | 14 | 1100 | CGJ5 | Weekend |  | 2019-05-04 11:55 | 2019-05-06 12:15 | 2 day(s) 00:20 Hrs | CORE: 1 of 1: CAT14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 190yds | 10 | 950 | 10 | 1140 | 190
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 6 | 158412 | A2453560 | 23400517 | North Wembley | 15aa | 2100 | LEC1 | Weekend |  | 2019-05-04 22:00 | 2019-05-05 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: North Wembley - CAT15aa - 806yds | 8 | 1100 | 9 | 146 | 806
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 6 | 154334 | A49500 | 114595 | Islip Street DM | 14 | 2100 | MCL | Weekend |  | 2019-05-04 23:00 | 2019-05-06 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 - Formation, Reballast, Resleeper, Rerail - Trax - 320yds | 3 | 110 | 3 | 430 | 320 | East Mids 2019-20 IP Plain Line Complete Trax Workbank - extract from RAMP on 26-09-2016. LP CC PLS-1920-043 Amend principal treatments to read 110y CAT 14, 529 CAT 13, 529y CAT 1. Amended to Cat 14 - 639yds as per C/C ref: PLS-1920-112. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 6 | 154343 | A2861890 | 32200715 | Gibsons 17/18 Falldown | 11 | 2100 | WCM1 | Weekend |  | 2019-05-05 00:01 | 2019-05-06 03:01 | 1 day(s) 03:00 Hrs | CORE: Gibsons 17/18 Falldown [Week 06] Cat 11:147 yds | 23 | 593 | 23 | 740 | 147
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 6 | 154335 | A2487060 | 124183 | Frickley | 11 | 1100 | SMJ2 | Weekend | W2019/5742479 | 2019-05-05 00:01 | 2019-05-06 05:00 | 1 day(s) 04:59 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 452yds | 13 | 264 | 13 | 716 | 452 | PLN-1920-092.
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 7 | 154343 | A261410 | 32202219 | Leggatfoot North | 11 | 1100 | WCM1 | Weekend |  | 2019-05-11 01:00 | 2019-05-12 04:00 | 1 day(s) 03:00 Hrs | CORE: Leggatfoot North [Week 07] Cat 11:495 yds | 70 | 796 | 70 | 1291 | 495 |  | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 7 | 154934 | G4T33360 | 44201812Bsf1 | Wallers Ash DM | 11 | 2100 | BML1 | Weekend |  | 2019-05-11 01:00 | 2019-05-13 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 61 | 964 | 61 | 1400 | 436
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 7 | 154934 | G4T35350 | 44201812Bsf1 | Wallers Ash DM | 14 | 2100 | BML1 | Weekend |  | 2019-05-11 01:00 | 2019-05-13 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 61 | 1400 | 61 | 1582 | 182
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 7 | 154335 | A2456090 | 125197 | Ulceby | 16 | 3100 | HAU | Weekend | W2019/0000000 | 2019-05-11 01:00 | 2019-05-12 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify/Skim (all non steel sleeper types) : 144yds (Not in PPS) | 0 | 849 | 0 | 993 | 144 | PLN-1920-070 (Core Week 07 not in PPS but showing midweek FUW) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 7 | 154335 | A2484860 | 125197 | Ulceby | 11 | 3100 | HAU | Weekend | W2019/0000000 | 2019-05-11 01:00 | 2019-05-12 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 82yds (Not in PPS) | 0 | 767 | 0 | 849 | 82 | PLN-1920-070 (Core Week 07 not in PPS but showing midweek FUW) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 7 | 154335 | A2484870 | 125197 | Ulceby | 16 | 3100 | HAU | Weekend | W2019/0000000 | 2019-05-11 01:00 | 2019-05-12 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify/Skim (all non steel sleeper types) : 848yds (Not in PPS) | 0 | 1093 | 1 | 181 | 848 | PLN-1920-070 (Core Week 07 not in PPS but showing midweek FUW) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 7 | 154335 | A2484880 | 125197 | Ulceby | 11 | 3100 | HAU | Weekend | W2019/0000000 | 2019-05-11 01:00 | 2019-05-12 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 100yds (Not in PPS) | 0 | 993 | 0 | 1093 | 100 | PLN-1920-070 (Core Week 07 not in PPS but showing midweek FUW) | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 7 | 154146 | A22930 | 51430120 | Trowbridge | 14 | 1100 | WEY | Weekend | W2019/0000000 | 2019-05-11 01:30 | 2019-05-13 05:00 | 2 day(s) 03:30 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 104 | 950 | 104 | 1276 | 326
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 7 | 154146 | WES12550 | 52100315 | Oddingley (Dn) | 11 | 2100 | BAG2 | Weekend | W2019/0000000 | 2019-05-11 02:30 | 2019-05-13 05:30 | 2 day(s) 03:00 Hrs | CORE: 1/ Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 62 | 1049 | 63 | 830 | 1541
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 7 | 154334 | A15450 | 114085 11 | Silkstream | 2 | 2100 | SPC1 | Weekend |  | 2019-05-11 23:00 | 2019-05-13 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 02 Rerail - Both Rails - 9yds | 7 | 856 | 7 | 865 | 9 | CC 02.03.17 - PLS-1920-009 mileage changed from 7m840y-7m1600y (760yds of Cat 11) to 7m856y-7m865y (9yds of Cat 2)
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 7 | 154334 | A51620 | 114085 11 | Silkstream | 11 | 2100 | SPC1 | Weekend |  | 2019-05-11 23:00 | 2019-05-13 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11 Reballast, Resleeper, Rerail - Trax - 378yds | 7 | 865 | 7 | 1243 | 378 | CC 02.03.17 - PLS-1920-009 mileage changed from 7m840y-7m1600y (760yds of Cat 11) to 7m865y-7m1622y (757yds of Cat 11)
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 7 | 154343 | A9410 | 31201921 | Byrnes Bridge | 11 | 1100 | ECA2 | Weekend |  | 2019-05-12 00:01 | 2019-05-13 03:01 | 1 day(s) 03:00 Hrs | CORE: Byrnes Bridge [Week 07] Cat 11:360 yds | 93 | 1548 | 94 | 148 | 360 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 7 | 154341 | A383010 | 24300619 | COT Rugeley Town | 11 | 2100 | RRN2 | Weekend | W2019/WIP | 2019-05-12 00:40 | 2019-05-13 05:40 | 1 day(s) 05:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 530 | 13 | 350 | 13 | 880 | 530
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 8 | 154343 | A8410 | 32200219 | Kirkpatrick | 11 | 2100 | WCM1 | Weekend |  | 2019-05-18 01:00 | 2019-05-19 04:00 | 1 day(s) 03:00 Hrs | CORE: Kirkpatrick [Week 08] Cat 11:475 yds | 12 | 1725 | 13 | 440 | 475
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 8 | 154341 | A354930 | 24100712 | Beaconsfield Up Platform | 14 | 1100 | NAJ2 | Weekend | W2019/WIP | 2019-05-18 01:00 | 2019-05-20 05:00 | 2 day(s) 04:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 784yds | 11 | 446 | 11 | 1230 | 784
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 8 | 154146 | WES13570 | 52102111SF | Oddingley UM | 11 | 1100 | BAG2 | Weekend | W2019/0000000 | 2019-05-18 02:30 | 2019-05-20 05:30 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 62 | 619 | 62 | 1650 | 1031
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 8 | 154334 | A40140 | 114085 11 | Silkstream | 11 | 2100 | SPC1 | Weekend |  | 2019-05-18 23:00 | 2019-05-20 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11 Reballast, Resleeper, Rerail - Trax - 379yds | 7 | 1243 | 7 | 1622 | 379 | CC 02.03.17 - PLS-1920-009 mileage changed from 7m840y-7m1600y (760yds of Cat 11) to 7m865y-7m1622y (757yds of Cat 11)
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 8 | 154334 | A40150 | 114085 11 | Silkstream | 1 | 2100 | SPC1 | Weekend |  | 2019-05-18 23:00 | 2019-05-20 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 01 Rerail - One Rail only - 17yds | 7 | 1622 | 7 | 1639 | 17 | CC 18.05.17 - PLS-1920-049 - ROW code changed from CAT 02 to 01. EA
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 8 | 154335 | A2484760 | 125197 | Ulceby | 16 | 3100 | HAU | Weekend | W2019/5761461 | 2019-05-18 23:50 | 2019-05-20 03:00 | 1 day(s) 03:10 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify/Skim (all non steel sleeper types) : 566yds | 1 | 281 | 1 | 847 | 566 | PLN-1920-070 (also Week 09 core?) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 8 | 154335 | A2484890 | 125197 | Ulceby | 11 | 3100 | HAU | Weekend | W2019/5761461 | 2019-05-18 23:50 | 2019-05-20 03:00 | 1 day(s) 03:10 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 100yds | 1 | 181 | 1 | 281 | 100 | PLN-1920-070 (also Week 09 core?) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 8 | 154335 | A2484900 | 125197 | Ulceby | 11 | 3100 | HAU | Weekend | W2019/5761461 | 2019-05-18 23:50 | 2019-05-20 03:00 | 1 day(s) 03:10 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 82yds | 1 | 847 | 1 | 929 | 82 | PLN-1920-070 (also Week 09 core?) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 8 | 154343 | A2861780 | 31201921 | Byrnes Bridge | 11 | 1100 | ECA2 | Weekend |  | 2019-05-19 00:01 | 2019-05-20 03:01 | 1 day(s) 03:00 Hrs | CORE: Byrnes Bridge [Week 08] Cat 11:360 yds | 94 | 148 | 94 | 508 | 360 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 9 | 154341 | A336210 | 23300519 | COT Pitstone Down | 12 | 2100 | LEC1 | Weekend | W2019/WIP | 2019-05-24 22:30 | 2019-05-28 04:00 | 3 day(s) 05:30 Hrs | CORE: 1 of 1 Reballast, Formation - Trax - Cat12 - 710yds | 33 | 1100 | 34 | 50 | 710
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 9 | 154929 | A936860 | 41219920df1 | Stowmarket 1100 | 15aa | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-05-25 02:05 | 2019-05-28 04:00 | 3 day(s) 01:55 Hrs | CORE: 2/4 Drainage - Associated Renewal P03 | 80 | 725 | 80 | 55 | 670 | Staging of works amended to ensure the priority section through the Platform is delivered. CC ref: EA-1920-38 applies
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 9 | 154339 | A2449190 | COT22202699 | Acton Bridge Stn | 14 | 1200 | CGJ1 | Weekend |  | 2019-05-25 11:55 | 2019-05-27 12:15 | 2 day(s) 00:20 Hrs | CORE: 1 of 1: Cat14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 478yds | 172 | 455 | 172 | 933 | 478 | CC Ref - LNWPL-1920-043
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 9 | 154334 | A51870 | 114595 | Islip Street DM | 14 | 2100 | MCL | Weekend |  | 2019-05-25 23:00 | 2019-05-27 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 - Formation, Reballast, Resleeper, Rerail - Trax - 319yds | 3 | 430 | 3 | 749 | 319 | East Mids 2019-20 IP Plain Line Complete Trax Workbank - extract from RAMP on 26-09-2016. LP CC PLS-1920-043 Amend principal treatments to read 110y CAT 14, 529 CAT 13, 529y CAT 1. Amended to Cat 14 - 639yds as per C/C ref: PLS-1920-112. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 9 | 154343 | A2410 | 32201118 | Cleghorn North | 11 | 1100 | WCM1 | Weekend |  | 2019-05-26 00:01 | 2019-05-28 04:01 | 2 day(s) 04:00 Hrs | CORE: Cleghorn North [Week 09] Cat 11:1004 yds | 76 | 1312 | 77 | 556 | 1004
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 9 | 154930 | A26370 | 42300411sf2 | Canterbury East Station Dn (Shortfall) | 6 | 2100 | FDM | Weekend | W2019/000000 | 2019-05-26 00:20 | 2019-05-28 04:00 | 2 day(s) 03:40 Hrs | CORE: 1/1 Reballast, Rerail - Trax Cat:06 | 61 | 1272 | 61 | 1540 | 268 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 9 | 154930 | G2570 | 42300411sf2 | Canterbury East Station Dn (Shortfall) | 2 | 2100 | FDM | Weekend | W2019/000000 | 2019-05-26 00:20 | 2019-05-28 04:00 | 2 day(s) 03:40 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 61 | 1540 | 61 | 1552 | 12 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 10 | 154343 | A260410 | 32201018 | Float Viaduct | 11 | 2100 | WCM1 | Weekend |  | 2019-06-01 01:00 | 2019-06-02 04:00 | 1 day(s) 03:00 Hrs | CORE: Float Viaduct [Week 10] Cat 11:289 yds | 72 | 1037 | 72 | 1326 | 289
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 10 | 154343 | A7410 | 32201119 | Hopper | 11 | 2100 | WCM1 | Weekend |  | 2019-06-01 01:00 | 2019-06-02 04:00 | 1 day(s) 03:00 Hrs | CORE: Hopper [Week 10] Cat 11:500 yds | 38 | 440 | 38 | 940 | 500
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 10 | 154341 | A363250 | 24101919 | COT Sudbury & Harrow Road | 12 | 1100 | NAJ1 | Weekend | W2019/WIP | 2019-06-01 01:00 | 2019-06-03 05:00 | 2 day(s) 04:00 Hrs | CORE: 1 of 1 Reballast, Formation - Trax - Cat12 - 440yds | 3 | 880 | 3 | 1320 | 440
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 10 | 154929 | A936970 | 41219920df1 | Stowmarket 1100 | 2 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-06-01 02:00 | 2019-06-03 04:00 | 2 day(s) 02:00 Hrs | CORE: 3/4 Rerail - Both Rails Cat:02 P03 | 80 | 1274 | 80 | 1258 | 16 | Staging of works amended to ensure the priority section through the Platform is delivered. CC ref: EA-1920-38 applies
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 10 | 154929 | A936980 | 41219920df1 | Stowmarket 1100 | 14 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-06-01 02:00 | 2019-06-03 04:00 | 2 day(s) 02:00 Hrs | CORE: 3/4 Formation, Reballast, Resleeper, Rerail - Trax Cat:14 P03 | 80 | 823 | 80 | 723 | 100 | Staging of works amended to ensure the priority section through the Platform is delivered. CC ref: EA-1920-38 applies
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 10 | 154929 | A938080 | 41219920df1 | Stowmarket 1100 | 11 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-06-01 02:00 | 2019-06-03 04:00 | 2 day(s) 02:00 Hrs | CORE: 3/4 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 P03 | 80 | 1258 | 80 | 823 | 435 | Staging of works amended to ensure the priority section through the Platform is delivered. CC ref: EA-1920-38 applies
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 10 | 158412 | A2456680 | 23406399 | COT Harlesden Drainage | 15aa | 2801 | WTS | Weekend |  | 2019-06-01 22:00 | 2019-06-02 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: COT Harlesden Drainage - CAT15aa - 225yds | 6 | 708 | 6 | 933 | 225
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 10 | 154334 | A39860 | 114456 | Harpenden | 11 | 1100 | SPC1 | Weekend |  | 2019-06-01 23:00 | 2019-06-03 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11: Reballast, Resleeper, Rerail - Trax - 489yds | 24 | 811 | 24 | 1300 | 489 | CC 02.03.17 - PLS-1819-220 Deferral to 19/20 under CC PLS-1920-014. LP 07.03.17
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 10 | 154335 | A2487160 | 125045 | Carcroft - Skellow | 11 | 1100 | CJS | Weekend | W2019/5997748 | 2019-06-01 23:00 | 2019-06-03 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 268yds | 160 | 322 | 160 | 600 | 268 | PLN-1920-096 | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 10 | 154146 | A19810 | 52240616 | Rodford Up | 14 | 1100 | YAT | Weekend | P2019/2416887 | 2019-06-01 23:40 | 2019-06-03 04:30 | 1 day(s) 04:50 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 120 | 880 | 120 | 1188 | 308
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 11 | 154146 | A28440 | 51140119 | Greenford Platform | 30 | 3100 | WEL2 | Weekend | W2019/0000000 | 2019-06-08 01:00 | 2019-06-09 04:00 | 1 day(s) 03:00 Hrs | CORE: 1st CW Sleeper Changing 1 in 3 | 8 | 1518 | 9 | 147 | 389
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 11 | 154335 | A2461090 | 136244 | Shay Lane Viaduct | 11 | 1100 | DOL1 | Weekend | W2019/0000000 | 2019-06-08 01:00 | 2019-06-09 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 200yds (Not in PPS) | 172 | 1145 | 172 | 1345 | 200 | PLN-1920-051 (Not in PPS) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 11 | 154335 | A2484540 | 136244 | Shay Lane Viaduct | 2 | 1100 | DOL1 | Weekend | W2019/0000000 | 2019-06-08 01:00 | 2019-06-09 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT02: Rerail (Both Rails) : 7yds (Not in PPS) | 172 | 1138 | 172 | 1145 | 7 | PLN-1920-051 (Not in PPS) | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 11 | 154929 | A936960 | 41219920df1 | Stowmarket 1100 | 14 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-06-08 02:00 | 2019-06-10 04:00 | 2 day(s) 02:00 Hrs | CORE: 4/4 Formation, Reballast, Resleeper, Rerail - Trax Cat:14 P03 | 80 | 723 | 80 | 49 | 674 | Staging of works amended to ensure the priority section through the Platform is delivered. CC ref: EA-1920-38 applies
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 11 | 154929 | A936990 | 41219920df1 | Stowmarket 1100 | 2 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-06-08 02:00 | 2019-06-10 04:00 | 2 day(s) 02:00 Hrs | CORE: 4/4 Rerail - Both Rails Cat:02 P03 | 80 | 49 | 80 | 43 | 6 | Staging of works amended to ensure the priority section through the Platform is delivered. CC ref: EA-1920-38 applies
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 11 | 154335 | A2488020 | 125045 | Carcroft - Skellow | 11 | 1100 | CJS | Weekend | W2019/0000000 | 2019-06-08 16:00 | 2019-06-09 08:00 | 0 day(s) 16:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 267yds (Not in PPS) | 160 | 600 | 160 | 867 | 267 | PLN-1920-096 | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 11 | 154146 | WES37030 | 52101711 | Worcester Forgate St Up | 11 | 3102 | WAH | Weekend | W2019/0000000 | 2019-06-08 21:10 | 2019-06-10 05:10 | 1 day(s) 08:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 120 | 1406 | 121 | 21 | 375
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 11 | 158412 | A2457540 | 23406399 | COT Harlesden Drainage | 15aa | 2801 | WTS | Weekend |  | 2019-06-08 22:00 | 2019-06-09 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: COT Harlesden Drainage - CAT15aa - 225yds | 6 | 933 | 6 | 1158 | 225
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 11 | 154334 | A48540 | 114618 | Dock Junction | 13 | 1100 | MCL | Weekend |  | 2019-06-08 23:00 | 2019-06-10 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 13 - Resleeper, Reballast, Formation - Trax - 137yds | 2 | 1523 | 2 | 1660 | 137 | CC 11.01.17 Add into 19.20 workbank - CC 10.05.17 - Amend CAT to CAT 12, Amend milage to 2m 1523 y - 2M 1660y. ROW code changed from Cat 12 to Cat 13 as per C/C ref: PLS-1920-134
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 11 | 154343 | A83410 | 31103219 | Priest Inch | 11 | 1100 | EGM1 | Weekend |  | 2019-06-09 00:01 | 2019-06-10 05:01 | 1 day(s) 05:00 Hrs | CORE: Priest Inch [Week 11] Cat 11:550 yds | 34 | 470 | 34 | 1020 | 550 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 11 | 154339 | A2896430 | JTC22302319 | Hartford Chord | 11 | 2100 | HCN | Weekend |  | 2019-06-09 00:40 | 2019-06-10 05:40 | 1 day(s) 05:00 Hrs | CORE: 1 of 2: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 455yds | 0 | 605 | 0 | 1460 | 455
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 11 | 154341 | A362210 | 24101619 | COT Wembley Stadium Down | 14 | 2100 | NAJ1 | Weekend | W2019/WIP | 2019-06-09 01:00 | 2019-06-10 05:00 | 1 day(s) 04:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 280yds | 5 | 161 | 5 | 441 | 280 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 12 | 154930 | A12790 | 42400217df1 | East Dulwich (Down) | 11 | 2100 | BTH1 | Weekend | W2019/000000 | 2019-06-15 00:25 | 2019-06-17 03:10 | 2 day(s) 02:45 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 398 | 4 | 678 | 280 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 12 | 154930 | A12800 | 42400217df1 | East Dulwich (Down) | 11 | 2100 | BTH1 | Weekend | W2019/000000 | 2019-06-15 00:25 | 2019-06-17 03:10 | 2 day(s) 02:45 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 330 | 4 | 371 | 41 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 12 | 154930 | A31370 | 42400217df1 | East Dulwich (Down) | 2 | 2100 | BTH1 | Weekend | W2019/000000 | 2019-06-15 00:25 | 2019-06-17 03:10 | 2 day(s) 02:45 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 4 | 371 | 4 | 398 | 27 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 12 | 154930 | A936860 | 42400217df1 | East Dulwich (Down) | 2 | 2100 | BTH1 | Weekend | W2019/000000 | 2019-06-15 00:25 | 2019-06-17 03:10 | 2 day(s) 02:45 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 4 | 320 | 4 | 330 | 10 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 12 | 154930 | A936870 | 42400217df1 | East Dulwich (Down) | 2 | 2100 | BTH1 | Weekend | W2019/000000 | 2019-06-15 00:25 | 2019-06-17 03:10 | 2 day(s) 02:45 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 4 | 678 | 4 | 688 | 10 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 12 | 154146 | A35650 | 52101711 | Worcester Forgate St Up | 11 | 3102 | WAH | Weekend | W2019/0000000 | 2019-06-15 21:10 | 2019-06-17 05:10 | 1 day(s) 08:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 121 | 21 | 121 | 396 | 375
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 12 | 154334 | A20450 | 114601 | Track Freeze Sundon High Bridge | 14 | 1100 | SPC1 | Weekend |  | 2019-06-15 23:00 | 2019-06-17 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 270yds | 34 | 1075 | 34 | 1345 | 270 | CC PLS-1920-053 amend mileage from 34m1088y-35m125y (797yds) to 34m1075y-35m125y (810 yds). LP | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 12 | 154335 | A2466090 | 136167 | Ardsley | 11 | 2100 | DOL2 | Weekend | W2019/5761544 | 2019-06-15 23:10 | 2019-06-17 04:00 | 1 day(s) 04:50 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 440yds | 180 | 1276 | 180 | 1716 | 440 | PLN-1920-066 (Not in PPS) | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 12 | 154343 | A84410 | 31103419 | 36 Arch Viaduct | 11 | 2100 | EGM1 | Weekend |  | 2019-06-16 00:01 | 2019-06-17 05:01 | 1 day(s) 05:00 Hrs | CORE: 36 Arch Viaduct [Week 12] Cat 11:472 yds | 37 | 1035 | 37 | 1507 | 472 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 12 | 154339 | A2903680 | JTC22302319 | Hartford Chord | 11 | 2100 | HCN | Weekend |  | 2019-06-16 00:40 | 2019-06-17 05:40 | 1 day(s) 05:00 Hrs | CORE: 2 of 2: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 400yds | 0 | 1032 | 0 | 1460 | 400
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 12 | 154339 | A2903880 | JTC22302319 | Hartford Chord | 2 | 2100 | HCN | Weekend |  | 2019-06-16 00:40 | 2019-06-17 05:40 | 1 day(s) 05:00 Hrs | CORE: 1 of 1: Cat 02 - Rerail - Both Rails - 21yds | 0 | 1460 | 0 | 1481 | 21
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 12 | 154341 | A361170 | 24101419 | COT Seer Green and Jordans | 12 | 2100 | NAJ2 | Weekend | W2019/WIP | 2019-06-16 01:00 | 2019-06-17 05:00 | 1 day(s) 04:00 Hrs | CORE: 1 of 1 Reballast, Formation - Trax - Cat12 - 470yds | 9 | 1300 | 10 | 10 | 470
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 13 | 154334 | A2480470 | 113058 | Cossington | 14 | 1200 | SPC5 | Weekend | W2019/0000000 | 2019-06-22 01:00 | 2019-06-23 08:00 | 1 day(s) 07:00 Hrs | CORE: CAT14 : Rerail, Resleeper, Reballast, Formation - Trax : 214yds (Not in PPS) | 104 | 1537 | 105 | 418 | 214 | (Not in PPS)
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 13 | 154930 | OLD1150 | 42500619 | Crofton Park Down | 2 | 2100 | CAT | Weekend | W2019/000000 | 2019-06-22 01:15 | 2019-06-24 04:00 | 2 day(s) 02:45 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 6 | 1090 | 6 | 1100 | 10 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 13 | 154930 | OLD1585 | 42500619 | Crofton Park Down | 11 | 2100 | CAT | Weekend | W2019/000000 | 2019-06-22 01:15 | 2019-06-24 04:00 | 2 day(s) 02:45 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 6 | 1100 | 7 | 147 | 807 |  | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 13 | 154334 | A51630 | 114601 | Track Freeze Sundon High Bridge | 14 | 1100 | SPC1 | Weekend |  | 2019-06-22 23:00 | 2019-06-24 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 270yds | 34 | 1345 | 34 | 1615 | 270 | CC PLS-1920-053 amend mileage from 34m1088y-35m125y (797yds) to 34m1075y-35m125y (810 yds). LP | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 13 | 154146 | WES3370 | 51322513 | Coopers (Up) | 2 | 1100 | DCL | Weekend | W2019/0000000 | 2019-06-22 23:35 | 2019-06-24 04:55 | 1 day(s) 05:20 Hrs | CORE: 1/2Rerail - Both Rails Cat:02 | 74 | 902 | 75 | 0 | 429
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 13 | 154341 | A19760 | 23500822 | Hazel Tree Farm | 12 | 1100 | HNR | Weekend | W2019/WIP | 2019-06-22 23:55 | 2019-06-24 05:00 | 1 day(s) 05:05 Hrs | CORE: 1 of 1: Hazel Tree Farm - Reballast, Formaion -Trax - CAT12 - 420yds | 72 | 1000 | 72 | 1420 | 420
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 13 | 154343 | A85410 | FD120090 | Winchburgh Quarry | 11 | 1100 | EGM1 | Weekend |  | 2019-06-23 00:01 | 2019-06-24 05:01 | 1 day(s) 05:00 Hrs | CORE: Winchburgh Quarry [Week 13] Cat 11:219 yds | 33 | 420 | 33 | 639 | 219 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 19/20 | 13 | 154932 | A9300 | 53100220 | Llanwern UR Pan 9's | 11 | 1200 | SWM2 | Weekend | W2019/0000000 | 2019-06-23 00:01 | 2019-06-24 05:00 | 1 day(s) 04:59 Hrs | CORE: 1st ReRail, ReSleeper, ReBallast - Trax | 155 | 253 | 155 | 664 | 429
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 13 | 154339 | A2861070 | TSR22500419 | Altrincham Down | 11 | 2100 | CDM2 | Weekend |  | 2019-06-23 00:40 | 2019-06-24 05:00 | 1 day(s) 04:20 Hrs | CORE: 1of 1: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 328yds | 8 | 552 | 8 | 880 | 328
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 14 | 154334 | A2484630 | 113058 | Cossington | 14 | 1200 | SPC5 | Weekend | W2019/0000000 | 2019-06-29 01:00 | 2019-06-30 08:00 | 1 day(s) 07:00 Hrs | CORE: CAT14 : Rerail, Resleeper, Reballast, Formation - Trax : 214yds (Not in PPS) | 104 | 1537 | 105 | 418 | 214 | (Not in PPS)
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 14 | 154930 | G2580 | 42500619 | Crofton Park Down | 11 | 2100 | CAT | Weekend | W2019/000000 | 2019-06-29 01:15 | 2019-07-01 04:00 | 2 day(s) 02:45 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 7 | 147 | 7 | 550 | 403 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 14 | 154930 | OLD1160 | 42500619 | Crofton Park Down | 2 | 2100 | CAT | Weekend | W2019/000000 | 2019-06-29 01:15 | 2019-07-01 04:00 | 2 day(s) 02:45 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 7 | 550 | 7 | 560 | 10 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 14 | 154929 | G4T387670 | 41506019 | Bishopsgate Tunnel Down | 14 | 2154 | LTN1 | Weekend | W2019/0000000 | 2019-06-29 02:35 | 2019-07-01 03:15 | 2 day(s) 00:40 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 0 | 865 | 0 | 1365 | 500
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 14 | 154341 | A319570 | 23181713s | MLF Banbury Lane | 12 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-06-29 22:10 | 2019-06-30 12:00 | 0 day(s) 13:50 Hrs | CORE: 1 of 6 Reballast, Formation - Trax - Cat12 - 190yds | 65 | 830 | 65 | 1020 | 190
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 14 | 154341 | A374690 | 23200415 | Colwich Junction US | 14 | 1200 | LEC2 | Weekend | W2019/WIP | 2019-06-29 22:30 | 2019-06-30 09:00 | 0 day(s) 10:30 Hrs | CORE: 1 of 5 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 148yds | 126 | 1210 | 126 | 1358 | 148
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 14 | 154334 | A51640 | 114601 | Track Freeze Sundon High Bridge | 14 | 1100 | SPC1 | Weekend |  | 2019-06-29 23:00 | 2019-07-01 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 270yds | 34 | 1615 | 35 | 125 | 270 | CC PLS-1920-053 amend mileage from 34m1088y-35m125y (797yds) to 34m1075y-35m125y (810 yds). LP | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 14 | 154146 | A35660 | 51322513 | Coopers (Up) | 2 | 1100 | DCL | Weekend | W2019/0000000 | 2019-06-29 23:35 | 2019-07-01 15:35 | 1 day(s) 16:00 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 74 | 902 | 75 | 0 | 429
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 14 | 154343 | A281410 | 31200719 | Todds Farm | 16 | 2100 | EGS2 | Weekend |  | 2019-06-30 00:01 | 2019-07-01 04:01 | 1 day(s) 04:00 Hrs | CORE: Todds Farm [Week 14] Cat 16:450 yds | 15 | 1140 | 15 | 1590 | 450 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 19/20 | 14 | 154932 | A10330 | 53100220 | Llanwern UR Pan 9's | 11 | 1200 | SWM2 | Weekend | W2019/0000000 | 2019-06-30 00:01 | 2019-07-01 05:00 | 1 day(s) 04:59 Hrs | CORE: 2nd ReRail, ReSleeper, ReBallast - Trax | 155 | 664 | 155 | 1093 | 429
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 14 | 154934 | G4T18770 | FL1032df4 | Richmond Platform 2 | 11 | 1100 | RDG1 | Weekend |  | 2019-06-30 01:20 | 2019-07-01 04:20 | 1 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 9 | 1095 | 9 | 1415 | 320 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 15 | 154339 | A2903790 | GAC22700519 | Upholland Tunnel Down | 11 | 2100 | WKL2 | Weekend |  | 2019-07-05 20:25 | 2019-07-08 05:30 | 2 day(s) 09:05 Hrs | CORE: 1 of 2: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 506yds | 21 | 1282 | 22 | 28 | 506 | CC LNWNPL-1920-037 rec'd 01.06.17 to add worksite from unassigned to 19/20. LP | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 15 | 154334 | A2484640 | 113058 | Cossington | 14 | 1200 | SPC5 | Weekend | W2019/0000000 | 2019-07-06 01:00 | 2019-07-07 08:00 | 1 day(s) 07:00 Hrs | CORE: CAT14 : Rerail, Resleeper, Reballast, Formation - Trax : 213yds (Not in PPS) | 104 | 1537 | 105 | 418 | 213 | (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 15 | 154335 | A2460090 | 135096 | Spring Lodge | 11 | 2100 | KWS | Weekend | W2019/0000000 | 2019-07-06 01:00 | 2019-07-07 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 427yds (Not in PPS) | 61 | 1 | 61 | 428 | 427 | CC PLN 1920 - 040 - Update CAT 11 to 427 yds - Add CAT 2, 8 yds (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 15 | 154335 | A2475110 | 135096 | Spring Lodge | 2 | 2100 | KWS | Weekend | W2019/0000000 | 2019-07-06 01:00 | 2019-07-07 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT02: Rerail - Both Rails : 8yds (Not in PPS) | 61 | 428 | 61 | 436 | 8 | (Not in PPS)
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 15 | 154930 | A27420 | 42400115df2 | South Bermondsey Dn | 2 | 2100 | BTH1 | Weekend | W2019/000000 | 2019-07-06 01:05 | 2019-07-08 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 1 | 1276 | 1 | 1291 | 15 | KENT-1920-24 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 15 | 154930 | A27430 | 42400115df2 | South Bermondsey Dn | 11 | 2100 | BTH1 | Weekend | W2019/000000 | 2019-07-06 01:05 | 2019-07-08 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 1 | 1291 | 1 | 1500 | 209 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 15 | 154929 | A6610 | 41506019 | Bishopsgate Tunnel Down | 14 | 2154 | LTN1 | Weekend | W2019/0000000 | 2019-07-06 02:35 | 2019-07-08 03:15 | 2 day(s) 00:40 Hrs | CORE: 2/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 0 | 531 | 0 | 600 | 69
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 15 | 154929 | G4T387680 | 41506019 | Bishopsgate Tunnel Down | 2 | 2154 | LTN1 | Weekend | W2019/0000000 | 2019-07-06 02:35 | 2019-07-08 03:15 | 2 day(s) 00:40 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 0 | 600 | 0 | 611 | 11
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 15 | 154929 | G4T387690 | 41506019 | Bishopsgate Tunnel Down | 44A | 2154 | LTN1 | Weekend | W2019/0000000 | 2019-07-06 02:35 | 2019-07-08 03:15 | 2 day(s) 00:40 Hrs | CORE: 2/2 Baseplate Changing Cat:44a | 0 | 600 | 0 | 611 | 11
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 15 | 154929 | G4T392700 | 41506019 | Bishopsgate Tunnel Down | 14 | 2154 | LTN1 | Weekend | W2019/0000000 | 2019-07-06 02:35 | 2019-07-08 03:15 | 2 day(s) 00:40 Hrs | CORE: 2/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 0 | 611 | 0 | 865 | 254
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 15 | 154341 | A392600 | 23181713s | MLF Banbury Lane | 12 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-07-06 22:10 | 2019-07-07 12:00 | 0 day(s) 13:50 Hrs | CORE: 2 of 6 Reballast, Formation - Trax - Cat12 - 190yds | 65 | 1020 | 65 | 1210 | 190
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 15 | 154341 | A392370 | 23200415 | Colwich Junction US | 14 | 1200 | LEC2 | Weekend | W2019/WIP | 2019-07-06 22:30 | 2019-07-07 09:00 | 0 day(s) 10:30 Hrs | CORE: 2 of 5 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 148yds | 126 | 1358 | 126 | 1506 | 148
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 15 | 154334 | A21450 | 114602 | Track Freeze Sundon High Bridge-1 | 14 | 2100 | SPC1 | Weekend |  | 2019-07-06 23:00 | 2019-07-08 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 269yds | 34 | 1080 | 34 | 1349 | 269 | Approved CC PLS-1920-025 mileage amended from 34m1088y-35m125y to 34m1080y-35m125y. LP | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 15 | 154146 | A21890 | 51220513 | Tilehurst | 2 | 1200 | MLN1 | Weekend | W2019/0000000 | 2019-07-06 23:10 | 2019-07-08 04:00 | 1 day(s) 04:50 Hrs | CORE: 1/2Rerail - Both Rails Cat: 02 | 37 | 1370 | 37 | 1540 | 170
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 15 | 154146 | A22750 | 51220513 | Tilehurst | 1 | 1200 | MLN1 | Weekend | W2019/0000000 | 2019-07-06 23:10 | 2019-07-08 04:00 | 1 day(s) 04:50 Hrs | CORE: 1/2 Rerail - One Rail Cat: 01 | 37 | 1540 | 38 | 100 | 320
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 15 | 154343 | A291560 | 31200719 | Todds Farm | 11 | 2100 | EGS2 | Weekend |  | 2019-07-07 00:01 | 2019-07-08 04:01 | 1 day(s) 04:00 Hrs | CORE: Todds Farm [Week 15] Cat 11:461 yds | 15 | 1590 | 16 | 291 | 461 |  | APC
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 19/20 | 15 | 154932 | A10340 | 53100220 | Llanwern UR Pan 9's | 11 | 1200 | SWM2 | Weekend | W2019/0000000 | 2019-07-07 00:01 | 2019-07-08 05:00 | 1 day(s) 04:59 Hrs | CORE: 3rd ReRail, ReSleeper, ReBallast - Trax | 155 | 1093 | 155 | 1540 | 429
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 16 | 154339 | A2897470 | GAC22700519 | Upholland Tunnel Down | 11 | 2100 | WKL2 | Weekend |  | 2019-07-12 20:25 | 2019-07-15 05:30 | 2 day(s) 09:05 Hrs | CORE: 2 of 2: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 506yds | 21 | 776 | 21 | 1282 | 506 | CC LNWNPL-1920-037 rec'd 01.06.17 to add worksite from unassigned to 19/20. LP | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 16 | 154930 | A27440 | 42400115df2 | South Bermondsey Dn | 2 | 2100 | BTH1 | Weekend | W2019/000000 | 2019-07-13 01:05 | 2019-07-15 04:00 | 2 day(s) 02:55 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 1 | 1710 | 1 | 1724 | 14 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 16 | 154930 | G4T123180 | 42400115df2 | South Bermondsey Dn | 11 | 2100 | BTH1 | Weekend | W2019/000000 | 2019-07-13 01:05 | 2019-07-15 04:00 | 2 day(s) 02:55 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 1 | 1500 | 1 | 1710 | 210 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 16 | 154341 | A392380 | 23200415 | Colwich Junction US | 14 | 1200 | LEC2 | Weekend | W2019/WIP | 2019-07-13 22:30 | 2019-07-14 09:00 | 0 day(s) 10:30 Hrs | CORE: 3 of 5 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 148yds | 126 | 1506 | 126 | 1654 | 148
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 16 | 154334 | A28450 | 113211 | Syston South | 14 | 2100 | SPC5 | Weekend |  | 2019-07-13 23:00 | 2019-07-15 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 - Rerail, Resleeper, Reballast, Formation - Trax - 137yds | 103 | 1120 | 103 | 1257 | 137 | CC PLS-1920-012 amend mileage from 103m850y-103m1270y cat 11 to 103m814y-103m828y cat 02. Yardage & Cat amended as per c/c ref. PLS-1920-090. Moved to Wk.16 vice Wk.23 as per C/C ref:- PLN-1920-090 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 16 | 154334 | A40170 | 113211 | Syston South | 11 | 2100 | SPC5 | Weekend |  | 2019-07-13 23:00 | 2019-07-15 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11 - Reballast, Resleeper, Rerail - Trax- 291yds | 103 | 829 | 103 | 1120 | 291 | CC PLS-1920-012 amend mileage from 103m850y-103m1270y cat 11 to 103m829y-103m1257y cat 11. Yardage amended as per c/c PLS-1920-090. Moved to Wk.16 vice Wk.23 as per C/C ref: PLN-1920-090 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 16 | 154334 | A51650 | 114602 | Track Freeze Sundon High Bridge-1 | 14 | 2100 | SPC1 | Weekend |  | 2019-07-13 23:00 | 2019-07-15 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 268yds | 34 | 1349 | 34 | 1617 | 268 | Approved CC PLS-1920-025 mileage amended from 34m1088y-35m125y to 34m1080y-35m125y. LP | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 16 | 154146 | A21900 | 51220513 | Tilehurst | 2 | 1200 | MLN1 | Weekend | W2019/0000000 | 2019-07-13 23:10 | 2019-07-15 04:00 | 1 day(s) 04:50 Hrs | CORE: 2/2 Rerail - Both Rails Cat: 02 | 38 | 100 | 38 | 456 | 356
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 16 | 154343 | A268410 | 32200520 | Akitmuir | 14 | 2100 | GSW | Weekend |  | 2019-07-14 00:01 | 2019-07-16 06:01 | 2 day(s) 06:00 Hrs | CORE: Akitmuir [Week 16] Cat 14:733 yds | 100 | 677 | 100 | 1410 | 733
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 16 | 154343 | A291390 | FD32102110 | Mennock Dn | 14 | 2100 | GSW | Weekend |  | 2019-07-14 00:01 | 2019-07-15 06:01 | 1 day(s) 06:00 Hrs | CORE: Mennock Dn [Week 16] Cat 14:570 yds | 68 | 788 | 68 | 1358 | 570
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 16 | 154343 | A88410 | 32202118 | Whitespots A | 13 | 1100 | GSW | Weekend |  | 2019-07-14 00:01 | 2019-07-16 06:01 | 2 day(s) 06:00 Hrs | CORE: Whitespots A [Week 16] Cat 13:556 yds | 82 | 1204 | 83 | 0 | 556
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 16 | 154343 | A91410 | FD32102110 | Mennock Dn | 14 | 2100 | GSW | Weekend |  | 2019-07-14 00:01 | 2019-07-15 06:01 | 1 day(s) 06:00 Hrs | CORE: Mennock Dn [Week 16] Cat 14:571 yds | 68 | 217 | 68 | 788 | 571
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 17 | 154929 | A5570 | 41501519 | Bishopsgate Tunnel Up Suburban | 14 | 1154 | LTN1 | Weekend | W2019/0000000 | 2019-07-20 02:35 | 2019-07-22 03:15 | 2 day(s) 00:40 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 0 | 538 | 0 | 597 | 59
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 17 | 154929 | G4T401090 | 41501519 | Bishopsgate Tunnel Up Suburban | 2 | 1154 | LTN1 | Weekend | W2019/0000000 | 2019-07-20 02:35 | 2019-07-22 03:15 | 2 day(s) 00:40 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 0 | 597 | 0 | 607 | 10
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 17 | 154929 | G4T401100 | 41501519 | Bishopsgate Tunnel Up Suburban | 14 | 1154 | LTN1 | Weekend | W2019/0000000 | 2019-07-20 02:35 | 2019-07-22 03:15 | 2 day(s) 00:40 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 0 | 607 | 0 | 1048 | 441
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 17 | 154339 | A2850670 | GAC22100119 | Sutton Tunnel Down | 14 | 2100 | CHW1 | Weekend |  | 2019-07-20 12:00 | 2019-07-23 04:00 | 2 day(s) 16:00 Hrs | CORE: 1 of 3 Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 1130yds | 11 | 1200 | 12 | 1700 | 2260
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 17 | 154339 | A2903840 | GAC22100119 | Sutton Tunnel Down | 2 | 2100 | CHW1 | Weekend |  | 2019-07-20 12:00 | 2019-07-23 04:00 | 2 day(s) 16:00 Hrs | CORE: 2 of 3 Cat 02 - Rerail Both Rails. 8yds | 11 | 1192 | 11 | 1200 | 8
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 17 | 154339 | A2903850 | GAC22100119 | Sutton Tunnel Down | 2 | 2100 | CHW1 | Weekend |  | 2019-07-20 12:00 | 2019-07-23 04:00 | 2 day(s) 16:00 Hrs | CORE: 3 of 3 Cat 02 - Rerail Both Rails. 4yds | 12 | 1700 | 12 | 1704 | 4
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 17 | 154334 | A2481510 | 111229 | Harlaston | 11 | 2100 | DBP1 | Weekend | W2019/0000000 | 2019-07-20 17:00 | 2019-07-21 22:00 | 1 day(s) 05:00 Hrs | CORE: CAT11 : Rerail, Resleeper, Reballast - Trax: 110yds (Not in PPS) | 20 | 1200 | 20 | 1310 | 110 | (Not in PPS)
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 17 | 154341 | A392610 | 23181713s | MLF Banbury Lane | 12 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-07-20 22:10 | 2019-07-21 09:00 | 0 day(s) 10:50 Hrs | CORE: 3 of 6 Reballast, Formation - Trax - Cat12 - 134yds | 65 | 1210 | 65 | 1344 | 134
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 17 | 154334 | A51660 | 114602 | Track Freeze Sundon High Bridge-1 | 14 | 2100 | SPC1 | Weekend |  | 2019-07-20 23:00 | 2019-07-22 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 268yds | 34 | 1617 | 35 | 125 | 268 | Approved CC PLS-1920-025 mileage amended from 34m1088y-35m125y to 34m1080y-35m125y. LP | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 17 | 154343 | A90410 | 32101919 | Auchinleck Station Down A | 14 | 2100 | GSW | Weekend |  | 2019-07-21 00:01 | 2019-07-22 06:01 | 1 day(s) 06:00 Hrs | CORE: Auchinleck Station Down A [Week 17] Cat 14:581 yds | 48 | 1604 | 49 | 425 | 581
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 17 | 154146 | A8370 | 51210119 | Half Way House | 4 | 3100 | MWB | Weekend | W2019/0000000 | 2019-07-21 00:40 | 2019-07-23 05:15 | 2 day(s) 04:35 Hrs | CORE: 1/5 Rerail, Resleeper (steel) - Cat04 | 1 | 792 | 1 | 892 | 100
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 18 | 154930 | A27390 | 42201114df1 | Cannon Street Plat. 3 Up | 44A | 3603 | CBM | Weekend | W2019/000000 | 2019-07-27 01:20 | 2019-07-29 04:00 | 2 day(s) 02:40 Hrs | CORE: Baseplate Changing Cat:44a | 0 | 31 | 0 | 54 | 23
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 18 | 154930 | A27400 | 42201114df1 | Cannon Street Plat. 3 Up | 11 | 3603 | CBM | Weekend | W2019/000000 | 2019-07-27 01:20 | 2019-07-29 04:00 | 2 day(s) 02:40 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 0 | 54 | 0 | 186 | 132
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 18 | 154930 | A27410 | 42201114df1 | Cannon Street Plat. 3 Up | 2 | 3603 | CBM | Weekend | W2019/000000 | 2019-07-27 01:20 | 2019-07-29 04:00 | 2 day(s) 02:40 Hrs | CORE: Rerail - Both Rails Cat:02 | 0 | 186 | 0 | 196 | 10
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 18 | 154930 | A5570 | 42201114df1 | Cannon Street Plat. 3 Up | 2 | 3603 | CBM | Weekend | W2019/000000 | 2019-07-27 01:20 | 2019-07-29 04:00 | 2 day(s) 02:40 Hrs | CORE: Rerail - Both Rails Cat:02 | 0 | 31 | 0 | 54 | 23
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 18 | 154929 | G4T390530 | 41501519 | Bishopsgate Tunnel Up Suburban | 14 | 1154 | LTN1 | Weekend | W2019/0000000 | 2019-07-27 02:35 | 2019-07-29 03:15 | 2 day(s) 00:40 Hrs | CORE: 2/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 0 | 1048 | 0 | 1392 | 344
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 18 | 154929 | G4T401110 | 41501519 | Bishopsgate Tunnel Up Suburban | 2 | 1154 | LTN1 | Weekend | W2019/0000000 | 2019-07-27 02:35 | 2019-07-29 03:15 | 2 day(s) 00:40 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 0 | 1392 | 0 | 1399 | 7
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 18 | 154929 | G4T401120 | 41501519 | Bishopsgate Tunnel Up Suburban | 1 | 1154 | LTN1 | Weekend | W2019/0000000 | 2019-07-27 02:35 | 2019-07-29 03:15 | 2 day(s) 00:40 Hrs | CORE: 2/2 Rerail - One Rail Only Cat:01 | 0 | 1399 | 0 | 1402 | 3
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 18 | 154334 | A2482370 | 111229 | Harlaston | 14 | 2100 | DBP1 | Weekend | W2019/0000000 | 2019-07-27 17:00 | 2019-07-28 22:00 | 1 day(s) 05:00 Hrs | CORE: CAT14: Rerail, Resleeper, Reballast, Formation : Trax: 520yds (Not in PPS) | 20 | 1310 | 21 | 70 | 520 | (Not in PPS)
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 18 | 154341 | A392620 | 23181713s | MLF Banbury Lane | 12 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-07-27 22:10 | 2019-07-28 09:00 | 0 day(s) 10:50 Hrs | CORE: 4 of 6 Reballast, Formation - Trax - Cat12 - 134yds | 65 | 1344 | 65 | 1478 | 134
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 18 | 154341 | A392390 | 23200415 | Colwich Junction US | 14 | 1200 | LEC2 | Weekend | W2019/WIP | 2019-07-27 22:30 | 2019-07-28 09:00 | 0 day(s) 10:30 Hrs | CORE: 4 of 5 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 148yds | 126 | 1654 | 127 | 42 | 148
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 18 | 154334 | A50640 | 114198 SF | Belsize Tunnel | 16 | 2100 | SPC1 | Weekend | W2019/0000000 | 2019-07-27 23:00 | 2019-07-29 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 16 - Resleeper, Rerail, Scarify/Skim - 282yds | 2 | 1320 | 2 | 1602 | 282 | CC 2019/20 - 39/16/17 - Addition of shortfall
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 18 | 154146 | A16690 | 52202115 | POD Exit (Parson st) | 12 | 1100 | POD | Weekend | W2019/0000000 | 2019-07-27 23:15 | 2019-07-29 05:15 | 1 day(s) 06:00 Hrs | CORE: 1/1Reballast, Formation - Trax Cat: 12 | 120 | 734 | 120 | 1008 | 274
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 18 | 154146 | A17550 | 52202115 | POD Exit (Parson st) | 14 | 1100 | POD | Weekend | W2019/0000000 | 2019-07-27 23:15 | 2019-07-29 05:15 | 1 day(s) 06:00 Hrs | CORE: 1/1Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 120 | 1008 | 120 | 1028 | 20
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 18 | 154343 | A273410 | 32403820 | Ferry Road Up | 12 | 1100 | NEM7 | Weekend |  | 2019-07-28 00:01 | 2019-07-29 05:01 | 1 day(s) 05:00 Hrs | CORE: Ferry Road Up [Week 18] Cat 12:230 yds | 19 | 440 | 19 | 670 | 230 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 18 | 154343 | A274410 | FD32411311b | Ardmore Level Crossing | 12 | 1100 | NEM7 | Weekend |  | 2019-07-28 00:01 | 2019-07-29 05:01 | 1 day(s) 05:00 Hrs | CORE: Ardmore Level Crossing [Week 18] Cat 12:53 yds | 21 | 375 | 21 | 428 | 53 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 18 | 154146 | A35670 | 51210119 | Half Way House | 4 | 3100 | MWB | Weekend | W2019/0000000 | 2019-07-28 00:40 | 2019-07-29 05:15 | 1 day(s) 04:35 Hrs | CORE: 2/5 Rerail, Resleeper (steel) - Cat04 | 1 | 892 | 1 | 992 | 100
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 18 | 154339 | A2849630 | GAC22200517 | Sutton Tunnel Up | 14 | 1100 | CHW1 | Midweek Nights |  | 2019-07-29 01:00 | 2019-08-02 05:00 | 4 day(s) 04:00 Hrs | CORE: 1 of 1: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 2260yds | 11 | 1200 | 12 | 1700 | 2260
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 18 | 154339 | A2903860 | GAC22200517 | Sutton Tunnel Up | 2 | 1100 | CHW1 | Midweek Nights |  | 2019-07-29 01:00 | 2019-08-02 05:00 | 4 day(s) 04:00 Hrs | CORE: 1 of 1: Cat 02 - Rerail - Both Rails- 5yds | 11 | 1195 | 11 | 1200 | 5
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 18 | 154339 | A2903870 | GAC22200517 | Sutton Tunnel Up | 2 | 1100 | CHW1 | Midweek Nights |  | 2019-07-29 01:00 | 2019-08-02 05:00 | 4 day(s) 04:00 Hrs | CORE: 1 of 1: Cat 02 - Rerail - Both Rails- 4yds | 12 | 1700 | 12 | 1704 | 4
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 19 | 154934 | A1480 | 44300717 | New Kew Jn | 11 | 2100 | NKE2 | Weekend |  | 2019-08-03 00:35 | 2019-08-05 03:00 | 2 day(s) 02:25 Hrs | CORE 1/1: Reballast, Resleeper, Rerail, Trax Cat:11 | 9 | 583 | 9 | 1541 | 958 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 19 | 154929 | A3490 | 41640111 | Hampstead Heath Tunnel to Brondesbury Up | 11 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-03 00:55 | 2019-08-05 05:00 | 2 day(s) 04:05 Hrs | CORE: 1/3 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 2 | 1319 | 2 | 1426 | 107
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 19 | 154929 | G4T400150 | 41640111 | Hampstead Heath Tunnel to Brondesbury Up | 2 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-03 00:55 | 2019-08-05 05:00 | 2 day(s) 04:05 Hrs | CORE: 1/3 Rerail - Both Rails Cat:02 | 2 | 903 | 2 | 1175 | 272
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 19 | 154929 | G4T400160 | 41640111 | Hampstead Heath Tunnel to Brondesbury Up | 14 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-03 00:55 | 2019-08-05 05:00 | 2 day(s) 04:05 Hrs | CORE: 1/3 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 2 | 1175 | 2 | 1319 | 144
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 19 | 154929 | G4T400170 | 41640111 | Hampstead Heath Tunnel to Brondesbury Up | 14 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-03 00:55 | 2019-08-05 05:00 | 2 day(s) 04:05 Hrs | CORE: 1/3 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 2 | 1426 | 2 | 1575 | 149 | 04/06/18 - GG - Job restaged. CC ref: WA-1920-25
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 19 | 154930 | A27360 | 42201014df1 | Cannon Street Plat. 2 Dn | 44A | 3602 | CBM | Weekend | W2019/000000 | 2019-08-03 01:20 | 2019-08-05 04:00 | 2 day(s) 02:40 Hrs | CORE: Baseplate Changing Cat:44a | 0 | 24 | 0 | 56 | 32
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 19 | 154930 | A27370 | 42201014df1 | Cannon Street Plat. 2 Dn | 11 | 3602 | CBM | Weekend | W2019/000000 | 2019-08-03 01:20 | 2019-08-05 04:00 | 2 day(s) 02:40 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 0 | 56 | 0 | 201 | 145
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 19 | 154930 | A27380 | 42201014df1 | Cannon Street Plat. 2 Dn | 2 | 3602 | CBM | Weekend | W2019/000000 | 2019-08-03 01:20 | 2019-08-05 04:00 | 2 day(s) 02:40 Hrs | CORE: Rerail - Both Rails Cat:02 | 0 | 201 | 0 | 219 | 18
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 19 | 154930 | A4530 | 42201014df1 | Cannon Street Plat. 2 Dn | 2 | 3602 | CBM | Weekend | W2019/000000 | 2019-08-03 01:20 | 2019-08-05 04:00 | 2 day(s) 02:40 Hrs | CORE: Rerail - Both Rails Cat:02 | 0 | 24 | 0 | 56 | 32
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 19 | 154334 | A2481520 | 111229 | Harlaston | 11 | 2100 | DBP1 | Weekend | W2019/0000000 | 2019-08-03 09:00 | 2019-08-04 14:00 | 1 day(s) 05:00 Hrs | CORE: CAT11 : Rerail, Resleeper, Reballast - Trax: 585yds (Not in PPS) | 21 | 70 | 21 | 655 | 585 | (Not in PPS)
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 19/20 | 19 | 154932 | A3270 | 53100119 | Llandavenny | 11 | 1200 | SWM2 | Weekend | W2019/0000000 | 2019-08-03 22:00 | 2019-08-05 06:00 | 1 day(s) 08:00 Hrs | CORE: 1st ReRail, ReSleeper, ReBallast - Trax | 151 | 1540 | 152 | 165 | 385
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 19 | 158412 | A2469160 | 23405899 | COT Camden Drainage | 15aa | 1200 | LEC1 | Weekend |  | 2019-08-03 22:00 | 2019-08-04 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT Camden Drainage - CAT15aa - 170yds | 1 | 930 | 1 | 1100 | 170
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 19 | 154341 | A392630 | 23181713s | MLF Banbury Lane | 12 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-08-03 22:10 | 2019-08-04 12:00 | 0 day(s) 13:50 Hrs | CORE: 5 of 6 Reballast, Formation - Trax - Cat12 - 190yds | 65 | 1478 | 65 | 1668 | 190
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 19 | 154334 | A51710 | 114198 SF | Belsize Tunnel | 16 | 2100 | SPC1 | Weekend | W2019/0000000 | 2019-08-03 23:00 | 2019-08-05 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 16 - Resleeper, Rerail, Scarify/Skim - 281yds | 2 | 1602 | 3 | 123 | 281 | CC 2019/20 - 39/16/17 - Addition of shortfall
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 19 | 154343 | A270410 | 32301219 | Cat and Dog Home (OB9) | 12 | 3400 | CNL | Weekend |  | 2019-08-04 00:01 | 2019-08-05 06:01 | 1 day(s) 06:00 Hrs | CORE: Cat and Dog Home (OB9) [Week 19] Cat 12:379 yds | 3 | 551 | 3 | 930 | 379
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 19 | 154343 | A272410 | 32403619 | Erskine Bridge | 14 | 2100 | NEM5 | Weekend |  | 2019-08-04 00:01 | 2019-08-05 05:01 | 1 day(s) 05:00 Hrs | CORE: Erskine Bridge [Week 19] Cat 14:494 yds | 10 | 1497 | 11 | 231 | 494
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 19 | 154146 | A35680 | 51210119 | Half Way House | 4 | 3100 | MWB | Weekend | W2019/0000000 | 2019-08-04 00:40 | 2019-08-05 05:15 | 1 day(s) 04:35 Hrs | CORE: 3/5 Rerail, Resleeper (steel) - Cat04 | 1 | 992 | 1 | 1092 | 100
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 20 | 154929 | G4T400180 | 41640111 | Hampstead Heath Tunnel to Brondesbury Up | 14 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-10 00:55 | 2019-08-12 05:00 | 2 day(s) 04:05 Hrs | CORE: 2/3 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 2 | 1575 | 3 | 200 | 385 | 04/06/18 - GG - Job restaged. CC ref: WA-1920-25
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 20 | 154930 | A27320 | 42200914df1 | Cannon Street Plat. 1 Dn | 2 | 3601 | CBM | Weekend | W2019/000000 | 2019-08-10 01:20 | 2019-08-12 04:00 | 2 day(s) 02:40 Hrs | CORE: Rerail - Both Rails Cat:02 | 0 | 26 | 0 | 56 | 30
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 20 | 154930 | A27330 | 42200914df1 | Cannon Street Plat. 1 Dn | 44A | 3601 | CBM | Weekend | W2019/000000 | 2019-08-10 01:20 | 2019-08-12 04:00 | 2 day(s) 02:40 Hrs | CORE: Baseplate Changing Cat:44a | 0 | 26 | 0 | 56 | 30
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 20 | 154930 | A27340 | 42200914df1 | Cannon Street Plat. 1 Dn | 11 | 3601 | CBM | Weekend | W2019/000000 | 2019-08-10 01:20 | 2019-08-12 04:00 | 2 day(s) 02:40 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 0 | 56 | 0 | 201 | 145
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 20 | 154930 | A27350 | 42200914df1 | Cannon Street Plat. 1 Dn | 2 | 3601 | CBM | Weekend | W2019/000000 | 2019-08-10 01:20 | 2019-08-12 04:00 | 2 day(s) 02:40 Hrs | CORE: Rerail - Both Rails Cat:02 | 0 | 201 | 0 | 206 | 5
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 20 | 154930 | A3490 | 42200914df1 | Cannon Street Plat. 1 Dn | 16 | 3601 | CBM | Weekend | W2019/000000 | 2019-08-10 01:20 | 2019-08-12 04:00 | 2 day(s) 02:40 Hrs | CORE: Resleeper, Rerail, Scarify/Skim (all non steel sleeper types) Cat:16 | 0 | 1 | 0 | 26 | 25
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 19/20 | 20 | 154932 | A10350 | 53100119 | Llandavenny | 11 | 1200 | SWM2 | Weekend | W2019/0000000 | 2019-08-10 22:00 | 2019-08-12 06:00 | 1 day(s) 08:00 Hrs | CORE: 2nd ReRail, ReSleeper, ReBallast - Trax | 152 | 165 | 152 | 550 | 385
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 20 | 158412 | A2470200 | 23406299 | Brent Biscuit Factory Drainage | 15aa | 2100 | LEC1 | Weekend |  | 2019-08-10 22:00 | 2019-08-11 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: Brent Biscuit Factory Drainage - CAT15aa - 158yds | 6 | 263 | 6 | 421 | 158
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 20 | 154341 | A392640 | 23181713s | MLF Banbury Lane | 12 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-08-10 22:10 | 2019-08-11 09:00 | 0 day(s) 10:50 Hrs | CORE: 6 of 6 Reballast, Formation - Trax - Cat12 - 132yds | 65 | 1668 | 66 | 40 | 132
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 20 | 154334 | A40270 | 114351 | Watling Street | 14 | 1200 | SPC1 | Weekend |  | 2019-08-10 23:00 | 2019-08-12 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 174yds | 4 | 872 | 4 | 1046 | 174 | Changed from 2 weeks to 3 weeks as per agreed c/c ref: PLS-1920-123 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 20 | 154343 | A166410 | 32401115 | Moss Rd Level Crossing Down | 14 | 2100 | NEM7 | Weekend |  | 2019-08-11 00:01 | 2019-08-13 06:01 | 2 day(s) 06:00 Hrs | CORE: Moss Rd Level Crossing Down [Week 20] Cat 14:111 yds | 21 | 1577 | 21 | 1688 | 111 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 20 | 154343 | A167410 | 32401015 | Moss Rd Level Crossing Up | 14 | 1100 | NEM7 | Weekend |  | 2019-08-11 00:01 | 2019-08-13 06:01 | 2 day(s) 06:00 Hrs | CORE: Moss Rd Level Crossing Up [Week 20] Cat 14:104 yds | 21 | 1584 | 21 | 1688 | 104 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 20 | 154343 | A269410 | 32300221 | OB 10 & 11 | 12 | 2100 | CNL | Weekend |  | 2019-08-11 00:01 | 2019-08-12 05:01 | 1 day(s) 05:00 Hrs | CORE: OB 10 & 11 [Week 20] Cat 12:273 yds | 4 | 43 | 4 | 316 | 273 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 20 | 154343 | A291430 | 32401115 | Moss Rd Level Crossing Down | 45A | 2100 | NEM7 | Weekend |  | 2019-08-11 00:01 | 2019-08-13 06:01 | 2 day(s) 06:00 Hrs | CORE: Moss Rd Level Crossing Down [Week 20] Cat 45A:0 yds | 21 | 1644 | 21 | 1653 | 0 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 20 | 154343 | A291440 | 32401015 | Moss Rd Level Crossing Up | 45A | 1100 | NEM7 | Weekend |  | 2019-08-11 00:01 | 2019-08-13 06:01 | 2 day(s) 06:00 Hrs | CORE: Moss Rd Level Crossing Up [Week 20] Cat 45A:0 yds | 21 | 1644 | 21 | 1653 | 0 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 20 | 154339 | A2895390 | TSR22500519 | Cheadle | 14 | 3400 | EJN | Weekend |  | 2019-08-11 00:40 | 2019-08-13 06:40 | 2 day(s) 06:00 Hrs | CORE: 1 of 1: Cat 14 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 529yds | 2 | 1560 | 3 | 329 | 529 | CC LNWNPL-1920-016 received 12/04/17, mileage amended from 2m 1569y - 3m 348y to 3m 0y - 3m 348y. EA
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 20 | 154146 | A35690 | 51210119 | Half Way House | 4 | 3100 | MWB | Weekend | W2019/0000000 | 2019-08-11 00:40 | 2019-08-12 05:15 | 1 day(s) 04:35 Hrs | CORE: 4/5 Rerail, Resleeper (steel) - Cat04 | 1 | 1092 | 1 | 1192 | 100
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 20 | 154339 | A2461710 | COT22100518 | Calverley 2100 | 14 | 2100 | CNH1 | Midweek Nights |  | 2019-08-13 21:00 | 2019-08-15 07:00 | 1 day(s) 10:00 Hrs | CORE: 1 of 1: Cat11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 320yds | 166 | 100 | 166 | 420 | 320 | CC Ref - LNWPL-1929-044
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 21 | 154929 | A938300 | 41640111 | Hampstead Heath Tunnel to Brondesbury Up | 14 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-17 00:55 | 2019-08-19 05:00 | 2 day(s) 04:05 Hrs | CORE: 3/3 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 3 | 200 | 3 | 435 | 235 | 04/06/18 - GG - Job restaged. CC ref: WA-1920-25
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 21 | 154929 | G4T391120 | 41640111 | Hampstead Heath Tunnel to Brondesbury Up | 11 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-17 00:55 | 2019-08-19 05:00 | 2 day(s) 04:05 Hrs | CORE: 3/3 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 435 | 3 | 622 | 187 | 04/06/18 - GG - Job restaged. CC ref: WA-1920-25
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 21 | 154929 | G4T400190 | 41640111 | Hampstead Heath Tunnel to Brondesbury Up | 2 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-17 00:55 | 2019-08-19 05:00 | 2 day(s) 04:05 Hrs | CORE: 3/3 Rerail - Both Rails Cat:02 | 3 | 622 | 3 | 634 | 12 | 04/06/18 - GG - Job restaged. CC ref: WA-1920-25
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 21 | 158412 | A2471060 | 23406299 | Brent Biscuit Factory Drainage | 15aa | 2100 | LEC1 | Weekend |  | 2019-08-17 22:00 | 2019-08-18 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: Brent Biscuit Factory Drainage - CAT15aa - 159yds | 6 | 421 | 6 | 580 | 159
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 21 | 154334 | A51670 | 114351 | Watling Street | 11 | 1200 | SPC1 | Weekend |  | 2019-08-17 23:00 | 2019-08-19 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11 Reballast, Resleeper, Rerail - Trax - 320yds | 4 | 1220 | 4 | 1540 | 320 | Changed from 2 weeks to 3 weeks as per agreed c/c ref: PLS-1920-123 | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 21 | 154341 | A322690 | 23500719 | COT Watfields | 12 | 1100 | HNR | Weekend |  | 2019-08-17 23:55 | 2019-08-19 05:00 | 1 day(s) 05:05 Hrs | CORE: 1 of 1: Reballast, Formation - Trax - Cat12 - 450yds | 77 | 0 | 77 | 450 | 450
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 21 | 154343 | A280410 | 32300521 | Burnside | 6 | 2100 | KHL | Weekend |  | 2019-08-18 00:01 | 2019-08-19 05:01 | 1 day(s) 05:00 Hrs | CORE: Burnside [Week 21] Cat 06:339 yds | 98 | 651 | 98 | 990 | 339
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 21 | 154343 | A291380 | 32300221 | OB 10 & 11 | 12 | 2100 | CNL | Weekend |  | 2019-08-18 00:01 | 2019-08-19 05:01 | 1 day(s) 05:00 Hrs | CORE: OB 10 & 11 [Week 21] Cat 12:300 yds | 4 | 316 | 4 | 616 | 300 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 21 | 154339 | A2905260 | 22100517 | Balderton - Green Lane | 11 | 3100 | WSJ2 | Weekend |  | 2019-08-18 00:30 | 2019-08-19 05:30 | 1 day(s) 05:00 Hrs | CORE: 1 of 6: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 699yds | 210 | 577 | 210 | 1276 | 699
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 21 | 154146 | A35700 | 51210119 | Half Way House | 4 | 3100 | MWB | Weekend | W2019/0000000 | 2019-08-18 00:40 | 2019-08-19 05:15 | 1 day(s) 04:35 Hrs | CORE: 5/5 Rerail, Resleeper (steel) - Cat04 | 1 | 1192 | 1 | 1396 | 204
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 22 | 154341 | A392700 | 23100419 | COT Linslade & Leighton Buzzard | 14 | 1100 | LEC1 | Weekend |  | 2019-08-23 22:30 | 2019-08-26 12:00 | 2 day(s) 13:30 Hrs | CORE: 1 of 3 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 600yds | 40 | 30 | 40 | 660 | 630
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 22 | 154931 | A3490 | 43400119 | Bletchingley Tunnel Up | 11 | 1100 | RTT | Weekend | W2019/000000 | 2019-08-24 00:20 | 2019-08-27 04:00 | 3 day(s) 03:40 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 26 | 490 | 27 | 112 | 1382 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 22 | 154931 | G4T169010 | 43400119 | Bletchingley Tunnel Up | 2 | 1100 | RTT | Weekend | W2019/000000 | 2019-08-24 00:20 | 2019-08-27 04:00 | 3 day(s) 03:40 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 26 | 474 | 26 | 490 | 16 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 22 | 154931 | G4T169020 | 43400119 | Bletchingley Tunnel Up | 2 | 1100 | RTT | Weekend | W2019/000000 | 2019-08-24 00:20 | 2019-08-27 04:00 | 3 day(s) 03:40 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 27 | 112 | 27 | 132 | 20 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 22 | 154929 | A17010 | 41600319 | Hampstead Heath Up | 14 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-24 00:55 | 2019-08-26 05:00 | 2 day(s) 04:05 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 1 | 451 | 1 | 1116 | 665 | 04/06/18 GG - Job restaged. CC ref WA-1920-26 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 22 | 154929 | G4T1000 | 41600319 | Hampstead Heath Up | 2 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-24 00:55 | 2019-08-26 05:00 | 2 day(s) 04:05 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 1 | 444 | 1 | 451 | 7 | 04/06/18 GG - Job restaged. CC ref WA-1920-26 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 22 | 154929 | G4T387710 | 41600319 | Hampstead Heath Up | 2 | 1100 | BOK2 | Weekend | W2019/0000000 | 2019-08-24 00:55 | 2019-08-26 05:00 | 2 day(s) 04:05 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 1 | 1116 | 1 | 1125 | 9 | 04/06/18 GG - Job restaged. CC ref WA-1920-26 refers
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 22 | 154343 | A245410 | 31500118 | Keith Platform | 11 | 3400 | ANI2 | Weekend |  | 2019-08-25 00:01 | 2019-08-27 06:01 | 2 day(s) 06:00 Hrs | CORE: Keith Platform [Week 22] Cat 11:400 yds | 30 | 360 | 30 | 760 | 400 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 22 | 154343 | A291530 | 32300521 | Burnside | 6 | 2100 | KHL | Weekend |  | 2019-08-25 00:01 | 2019-08-26 05:01 | 1 day(s) 05:00 Hrs | CORE: Burnside [Week 22] Cat 06:415 yds | 98 | 990 | 98 | 1405 | 415
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 22 | 154339 | A2496030 | 22500217 | Cheadle Hulme | 12 | 1100 | MCH | Weekend |  | 2019-08-25 00:10 | 2019-08-26 05:40 | 1 day(s) 05:30 Hrs | CORE: 1 of 1: Cat12 - Formation, Reballast - Traxcavate - 415yds | 0 | 905 | 0 | 1320 | 415
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 23 | 154931 | G4T103990 | 43300414df1 | Hove Tunnel (Dn) | 11 | 2100 | BLI1 | Weekend | W2019/000000 | 2019-08-31 00:25 | 2019-09-02 04:00 | 2 day(s) 03:35 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 0 | 607 | 0 | 892 | 285 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 23 | 154931 | G4T168810 | 43300414df1 | Hove Tunnel (Dn) | 2 | 2100 | BLI1 | Weekend | W2019/000000 | 2019-08-31 00:25 | 2019-09-02 04:00 | 2 day(s) 03:35 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 0 | 600 | 0 | 607 | 7 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 23 | 154931 | G4T168820 | 43300414df1 | Hove Tunnel (Dn) | 2 | 2100 | BLI1 | Weekend | W2019/000000 | 2019-08-31 00:25 | 2019-09-02 04:00 | 2 day(s) 03:35 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 0 | 892 | 0 | 903 | 11 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 23 | 154146 | A31560 | 51240115 | Twyford Bay (MDR) | 11 | 3600 | HEN | Weekend |  | 2019-08-31 01:00 | 2019-09-01 04:00 | 1 day(s) 03:00 Hrs | CORE: 1st CW Rerail, Resleeper, Reballast-Trax | 31 | 46 | 31 | 110 | 64
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 23 | 154146 | A33640 | 51240119 | Shiplake | 11 | 3100 | HEN | Weekend | W2019/0000000 | 2019-08-31 01:00 | 2019-09-01 04:00 | 1 day(s) 03:00 Hrs | CORE: 1st CW Rerail, Resleeper, Reballast-Trax | 33 | 1146 | 33 | 1452 | 306
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 23 | 154335 | A2472090 | 136062 | Armley - Kirkstall | 2 | 2100 | LEH1 | Weekend | W2019/0000000 | 2019-08-31 01:00 | 2019-09-01 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT02: Rerail - Both Rails : 25yds (Not in PPS) | 0 | 603 | 0 | 628 | 25 | PLN-1920-071 (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 23 | 154335 | A2475100 | 136062 | Armley - Kirkstall | 11 | 2100 | LEH1 | Weekend | W2019/0000000 | 2019-08-31 01:00 | 2019-09-01 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 362yds (Not in PPS) | 0 | 625 | 0 | 987 | 362 | PLN-1920-071 (Not in PPS)
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 23 | 154929 | G4T393900 | 41100211df1 | Morley Hill Up | 2 | 1100 | TLL | Weekend | W2019/0000000 | 2019-08-31 01:10 | 2019-09-02 04:20 | 2 day(s) 03:10 Hrs | CORE: 1/3 Rerail - Both Rails Cat:02 | 28 | 787 | 28 | 792 | 5
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 23 | 154929 | G4T400200 | 41100211df1 | Morley Hill Up | 11 | 1100 | TLL | Weekend | W2019/0000000 | 2019-08-31 01:10 | 2019-09-02 04:20 | 2 day(s) 03:10 Hrs | CORE: 1/3 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 28 | 792 | 28 | 1584 | 792
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 23 | 154146 | A23970 | 51140619 | West Drayton UM Platform | 11 | 1100 | MLN1 | Weekend | W2019/0000000 | 2019-08-31 22:00 | 2019-09-01 14:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 13 | 149 | 13 | 331 | 182
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 23 | 158412 | A2458760 | 23606999 | COT Curborough | 15aa | 2100 | LEC2 | Weekend |  | 2019-08-31 22:00 | 2019-09-01 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: COT Curborough - CAT15aa - 124yds | 117 | 170 | 117 | 294 | 124
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 23 | 154334 | A52250 | 114351 | Watling Street | 14 | 1200 | SPC1 | Weekend |  | 2019-08-31 23:00 | 2019-09-02 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 174yds | 4 | 1046 | 4 | 1220 | 174 | Changed from 2 weeks to 3 weeks as per agreed c/c ref: PLS-1920-123 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 23 | 154343 | A279410 | FD32100113 | Kingspark | 4 | 2100 | KHL | Weekend |  | 2019-09-01 00:01 | 2019-09-02 05:01 | 1 day(s) 05:00 Hrs | CORE: Kingspark [Week 23] Cat 04:338 yds | 100 | 38 | 100 | 375 | 338
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 23 | 154339 | A2903980 | 22100517 | Balderton - Green Lane | 11 | 3100 | WSJ2 | Weekend |  | 2019-09-01 00:30 | 2019-09-02 05:30 | 1 day(s) 05:00 Hrs | CORE: 3 of 3: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 208yds | 209 | 1471 | 209 | 1679 | 208
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 23 | 154339 | A2904950 | 22100517 | Balderton - Green Lane | 16 | 3100 | WSJ2 | Weekend |  | 2019-09-01 00:30 | 2019-09-02 05:30 | 1 day(s) 05:00 Hrs | CORE: 2 of 6: Cat 16 - Rerail, Resleeper - 38yds | 210 | 539 | 210 | 577 | 38
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 23 | 154339 | A2905270 | 22100517 | Balderton - Green Lane | 11 | 3100 | WSJ2 | Weekend |  | 2019-09-01 00:30 | 2019-09-02 05:30 | 1 day(s) 05:00 Hrs | CORE: 4 of 3: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 393yds | 210 | 1276 | 210 | 1669 | 393
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 24 | 154934 | G4T7330 | 44100718 | Vauxhall Platform 8 | 11 | 2200 | BML1 | Weekend |  | 2019-09-07 00:15 | 2019-09-09 04:00 | 2 day(s) 03:45 Hrs | CORE: 1/2 Rerail, Resleeper, Reballast - Trax | 1 | 374 | 1 | 704 | 330
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 24 | 154146 | A32420 | 51240115 | Twyford Bay (MDR) | 15a | 3600 | HEN | Weekend |  | 2019-09-07 01:00 | 2019-09-08 04:00 | 1 day(s) 03:00 Hrs | CORE: 2nd CW Drainage Associated | 31 | 46 | 31 | 110 | 64
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 24 | 154335 | A2475270 | 122113 | Uffington | 11 | 1150 | PMJ | Weekend | W2019/0000000 | 2019-09-07 01:00 | 2019-09-08 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax : 574yds (Not in PPS) | 14 | 1590 | 15 | 404 | 574 | (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 24 | 154335 | A2484610 | 136062 | Armley - Kirkstall | 11 | 2100 | LEH1 | Weekend | W2019/0000000 | 2019-09-07 01:00 | 2019-09-08 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 361yds (Not in PPS) | 0 | 987 | 0 | 1348 | 361 | PLN-1920-071 (Not in PPS)
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 24 | 154929 | G4T393910 | 41100211df1 | Morley Hill Up | 11 | 1100 | TLL | Weekend | W2019/0000000 | 2019-09-07 01:10 | 2019-09-09 04:20 | 2 day(s) 03:10 Hrs | CORE: 2/3 Reballast, Resleeper, Rerail - Trax (all non steel sleepert types) Cat:11 | 28 | 1584 | 29 | 600 | 776
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 24 | 154146 | A35710 | 51140619 | West Drayton UM Platform | 11 | 1100 | MLN1 | Weekend | W2019/0000000 | 2019-09-07 22:00 | 2019-09-08 14:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 13 | 331 | 13 | 512 | 181
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 24 | 158412 | A2452520 | 23400619 | West London | 15aa | 2200 | LEC1 | Weekend |  | 2019-09-07 22:00 | 2019-09-08 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: West London - CAT15aa - 177yds | 5 | 35 | 5 | 212 | 177
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 24 | 158412 | A2459620 | 23606999 | COT Curborough | 15aa | 2100 | LEC2 | Weekend |  | 2019-09-07 22:00 | 2019-09-08 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: COT Curborough - CAT15aa - 124yds | 117 | 294 | 117 | 418 | 124
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 24 | 154334 | A51840 | 114600 | Track Freeze Napsbury Lane | 14 | 2200 | SPC1 | Weekend |  | 2019-09-07 23:00 | 2019-09-09 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 212yds | 18 | 936 | 18 | 1148 | 212 | CC 02.03.17 - PLS-1920-007 mileage changed from 18m941y-18m1570y (629yds) to 18m936y-18m1572y (636yds). LP | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 24 | 154343 | A278410 | 31201818 | Niddrie Curve | 6 | 2100 | MHY | Weekend |  | 2019-09-08 00:01 | 2019-09-09 03:01 | 1 day(s) 03:00 Hrs | CORE: Niddrie Curve [Week 24] Cat 06:460 yds | 6 | 1436 | 7 | 136 | 460
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 24 | 154343 | A2861790 | 31201818 | Niddrie Curve | 2 | 2100 | MHY | Weekend |  | 2019-09-08 00:01 | 2019-09-09 03:01 | 1 day(s) 03:00 Hrs | CORE: Niddrie Curve [Week 24] Cat 02:14 yds | 7 | 136 | 7 | 150 | 14
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 24 | 154343 | A291520 | FD32100113 | Kingspark | 4 | 2100 | KHL | Weekend |  | 2019-09-08 00:01 | 2019-09-09 05:01 | 1 day(s) 05:00 Hrs | CORE: Kingspark [Week 24] Cat 04:339 yds | 100 | 38 | 375 | 711 | 339
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 24 | 154339 | A2904940 | 22100517 | Balderton - Green Lane | 2 | 3100 | WSJ2 | Weekend |  | 2019-09-08 00:30 | 2019-09-09 05:30 | 1 day(s) 05:00 Hrs | CORE: 5 of 6: Cat 02 - Rerail (Both Rails) - 48yds | 209 | 1423 | 209 | 1471 | 48
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 24 | 154339 | A2905250 | 22100517 | Balderton - Green Lane | 11 | 3100 | WSJ2 | Weekend |  | 2019-09-08 00:30 | 2019-09-09 05:30 | 1 day(s) 05:00 Hrs | CORE: 6 of 6: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 620yds | 209 | 1679 | 210 | 539 | 620
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 25 | 154341 | A367410 | 24102419 | COT Carlyon House | 14 | 2100 | NAJ2 | Weekend | W2019/WIP | 2019-09-14 01:00 | 2019-09-16 05:00 | 2 day(s) 04:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat:14 - 781yds | 28 | 439 | 28 | 1220 | 781 |  | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 25 | 154335 | A2463090 | 131186 | Seaham | 11 | 1100 | LEN3 | Weekend | W2019/0000000 | 2019-09-14 01:00 | 2019-09-15 08:00 | 1 day(s) 07:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 731yds (Not in PPS) | 84 | 1429 | 85 | 400 | 731 | PLN-1920-034 (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 25 | 154335 | A2476130 | 122113 | Uffington | 11 | 1150 | PMJ | Weekend | W2019/0000000 | 2019-09-14 01:00 | 2019-09-15 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax : 574yds (Not in PPS) | 15 | 404 | 15 | 978 | 574 | (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 25 | 154335 | A2486990 | 122113 | Uffington | 2 | 1150 | PMJ | Weekend | W2019/0000000 | 2019-09-14 01:00 | 2019-09-15 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT02: Rerail - Both Rals : 14yds (Not in PPS) | 14 | 1272 | 14 | 1286 | 14 | (Not in PPS)
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 25 | 154929 | G4T400020 | 41100211df1 | Morley Hill Up | 11 | 1100 | TLL | Weekend | W2019/0000000 | 2019-09-14 01:10 | 2019-09-16 04:20 | 2 day(s) 03:10 Hrs | CORE: 3/3 Reballast, Resleeper, Rerail - Trax (all non steel sleeperr types) Cat:11 | 29 | 600 | 29 | 1014 | 414
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 25 | 154929 | G4T400030 | 41100211df1 | Morley Hill Up | 14 | 1100 | TLL | Weekend | W2019/0000000 | 2019-09-14 01:10 | 2019-09-16 04:20 | 2 day(s) 03:10 Hrs | CORE: 3/3 Formation, Reballast, Resleeper, Rerail - Trax Cat:14 | 29 | 1014 | 29 | 1277 | 263
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 25 | 154929 | G4T400040 | 41100211df1 | Morley Hill Up | 2 | 1100 | TLL | Weekend | W2019/0000000 | 2019-09-14 01:10 | 2019-09-16 04:20 | 2 day(s) 03:10 Hrs | CORE: 3/3 Rerail - Both Rails Cat:02 | 29 | 1277 | 29 | 1279 | 2
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 25 | 154146 | WES33970 | 51400511 | Bruton Station Up | 14 | 1100 | WEY | Weekend | W2019/0000000 | 2019-09-14 21:20 | 2019-09-16 06:20 | 1 day(s) 09:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 125 | 1700 | 126 | 560 | 620
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 25 | 154334 | A17450 | 114600 | Track Freeze Napsbury Lane | 14 | 2200 | SPC1 | Weekend |  | 2019-09-14 23:00 | 2019-09-16 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 212yds | 18 | 1148 | 18 | 1360 | 212 | CC 02.03.17 - PLS-1920-007 mileage changed from 18m941y-18m1570y (629yds) to 18m936y-18m1572y (636yds). LP | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 25 | 154343 | A275410 | FD31200115 | Calton South Tunnel | 11 | 2100 | ECM8 | Weekend |  | 2019-09-15 00:01 | 2019-09-17 03:01 | 2 day(s) 03:00 Hrs | CORE: Calton South Tunnel [Week 25] Cat 11:422 yds | 0 | 591 | 0 | 1013 | 422
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 25 | 154343 | A82100 | FD100307 | Portobello Falldown | 16 | 2100 | ECM8 | Weekend |  | 2019-09-15 00:01 | 2019-09-15 16:01 | 0 day(s) 16:00 Hrs | CORE: Portobello Falldown [Week 25] Cat 16:97 yds | 3 | 93 | 3 | 190 | 97
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 25 | 154934 | A8920 | 44100718 | Vauxhall Platform 8 | 11 | 2200 | BML1 | Weekend |  | 2019-09-15 00:45 | 2019-09-16 04:30 | 1 day(s) 03:45 Hrs | CORE: 2/2 Rerail, Resleeper, Reballast - Trax | 1 | 704 | 1 | 1045 | 341
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 26 | 154934 | G4T12530 | 44202515 | Romsey | 11 | 2100 | ECR | Weekend |  | 2019-09-21 00:25 | 2019-09-23 03:00 | 2 day(s) 02:35 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 79 | 1573 | 80 | 682 | 869
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 26 | 154343 | A276410 | 31202319 | Ham Burn | 11 | 1100 | ECM8 | Weekend |  | 2019-09-21 01:00 | 2019-09-23 01:00 | 2 day(s) 00:00 Hrs | CORE: Ham Burn [Week 26] Cat 11:394 yds | 48 | 100 | 48 | 694 | 594
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 26 | 154335 | A2484750 | 122113 | Uffington | 11 | 1150 | PMJ | Weekend | W2019/0000000 | 2019-09-21 01:00 | 2019-09-22 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax : 574yds (Not in PPS) | 15 | 978 | 15 | 1552 | 574 | (Not in PPS)
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 26 | 154929 | A4530 | 41418719 | Diss Up Platform | 11 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-09-21 01:35 | 2019-09-23 04:55 | 2 day(s) 03:20 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 94 | 1464 | 94 | 1759 | 295 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 26 | 154930 | A15970 | 42300811df1 | Gillingham Tunnel Up | 11 | 1200 | VIR | Weekend | W2019/000000 | 2019-09-21 02:00 | 2019-09-23 03:30 | 2 day(s) 01:30 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 35 | 109 | 35 | 574 | 465
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 26 | 154930 | G2590 | 42300811df1 | Gillingham Tunnel Up | 2 | 1200 | VIR | Weekend | W2019/000000 | 2019-09-21 02:00 | 2019-09-23 03:30 | 2 day(s) 01:30 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 35 | 90 | 35 | 109 | 19
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 26 | 158412 | A2453380 | 23400619 | West London | 15aa | 2200 | LEC1 | Weekend |  | 2019-09-21 22:00 | 2019-09-22 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: West London - CAT15aa - 178yds | 5 | 212 | 5 | 390 | 178
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 26 | 154146 | WES30910 | 51400612 | East Somerset Jn (HME) (Dn) | 11 | 2100 | WEY | Weekend | W2019/0000000 | 2019-09-21 22:10 | 2019-09-22 21:20 | 0 day(s) 23:10 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 120 | 1060 | 120 | 1496 | 436
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 26 | 154334 | A51680 | 114600 | Track Freeze Napsbury Lane | 14 | 2200 | SPC1 | Weekend |  | 2019-09-21 23:00 | 2019-09-23 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14 Formation, Reballast, Resleeper, Rerail - Trax - 212yds | 18 | 1360 | 18 | 1572 | 212 | CC 02.03.17 - PLS-1920-007 mileage changed from 18m941y-18m1570y (629yds) to 18m936y-18m1572y (636yds). LP | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 26 | 154343 | A246410 | 31202419 | Burnmouth South | 14 | 2100 | ECM8 | Weekend |  | 2019-09-22 00:01 | 2019-09-23 05:01 | 1 day(s) 05:00 Hrs | CORE: Burnmouth South [Week 26] Cat 14:457 yds | 52 | 1523 | 53 | 220 | 457
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 26 | 154341 | A17700 | 24101320 | SLF Beaconsfield North Up | 2 | 1100 | NAJ2 | Weekend |  | 2019-09-22 01:00 | 2019-09-23 05:00 | 1 day(s) 04:00 Hrs | CORE: 1 of 1: SLF Beaconsfield North Up - Rerail - Both Rails - CAT02 - 1180yds | 11 | 1242 | 12 | 482 | 1180
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 27 | 154934 | G4T1090 | CM1032xdf5 | Waterloo Plat 11 | 11 | 3611 | BML1 | Weekend |  | 2019-09-28 00:35 | 2019-09-30 04:00 | 2 day(s) 03:25 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 0 | 118 | 0 | 369 | 251 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 27 | 154343 | A168410 | FD31200610B | Lamberton | 11 | 2100 | ECM8 | Weekend |  | 2019-09-28 01:00 | 2019-09-29 09:00 | 1 day(s) 08:00 Hrs | CORE: Lamberton [Week 27] Cat 11:472 yds | 53 | 1028 | 53 | 1500 | 472
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 27 | 154343 | A291450 | 31202319 | Ham Burn | 11 | 1100 | ECM8 | Weekend |  | 2019-09-28 01:00 | 2019-09-29 09:00 | 1 day(s) 08:00 Hrs | CORE: Ham Burn [Week 27] Cat 11:394 yds | 48 | 694 | 48 | 1288 | 594
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 27 | 154930 | A16830 | 42300811df1 | Gillingham Tunnel Up | 11 | 1200 | VIR | Weekend | W2019/000000 | 2019-09-28 02:00 | 2019-09-30 03:30 | 2 day(s) 01:30 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 35 | 574 | 35 | 1039 | 465
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 27 | 154930 | G2600 | 42300811df1 | Gillingham Tunnel Up | 2 | 1200 | VIR | Weekend | W2019/000000 | 2019-09-28 02:00 | 2019-09-30 03:30 | 2 day(s) 01:30 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 35 | 1039 | 35 | 1059 | 20
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 27 | 154341 | A348690 | 23400619 | West London Junction Slow | 14 | 2200 | LEC1 | Weekend | W2019/WIP | 2019-09-28 20:00 | 2019-09-29 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 151yds | 5 | 115 | 5 | 266 | 151
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 27 | 154341 | A392520 | 23100819A | COT Loughton | 14 | 1200 | LEC1 | Weekend |  | 2019-09-28 20:00 | 2019-09-29 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 160yds | 48 | 1106 | 48 | 1266 | 160
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 27 | 154334 | A13450 | 114598 | Cricklewood-1 | 11 | 1200 | SPC1 | Weekend |  | 2019-09-28 23:00 | 2019-09-30 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11 Reballast, Resleeper, Rerail - Trax - 294yds | 5 | 36 | 5 | 330 | 294 | CC 02.03.17 - PLS-1920-005 mileage changed from 5m50y-5m300y (250yds) to 5m36y-5m300y (264yds). LP | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 27 | 154146 | A7330 | 52201520 | Flax Bourton Tunnel Up | 11 | 1100 | MLN1 | Weekend | W2019/0000000 | 2019-09-28 23:15 | 2019-09-30 15:15 | 1 day(s) 16:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 123 | 1264 | 124 | 1622 | 358
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 27 | 154339 | A2893310 | COT22800319 | Dinting 3 | 11 | 3400 | DSD | Weekend |  | 2019-09-29 00:20 | 2019-09-30 05:20 | 1 day(s) 05:00 Hrs | CORE: 1 of 1: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 250yds | 0 | 1590 | 1 | 80 | 250 | CC 12.06.17 - LNWNPL-1920-040 - Amend ROW code from 7 to 11
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 28 | 154343 | A277410 | 31200721 | Palmerston | 14 | 1100 | ECM8 | Weekend |  | 2019-10-05 01:00 | 2019-10-06 09:00 | 1 day(s) 08:00 Hrs | CORE: Palmerston [Week 28] Cat 14:617 yds | 34 | 1253 | 35 | 110 | 617
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 28 | 154929 | A21170 | 41412019 | Dunston Hall Up | 11 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-10-05 01:35 | 2019-10-07 04:55 | 2 day(s) 03:20 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 108 | 1399 | 109 | 239 | 600
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 28 | 154929 | G4T400050 | 41412019 | Dunston Hall Up | 2 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-10-05 01:35 | 2019-10-07 04:55 | 2 day(s) 03:20 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 108 | 1385 | 108 | 1399 | 14
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 28 | 154341 | A335170 | 23300319 | COT Pitstone Up | 12 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-10-05 20:00 | 2019-10-06 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2 Reballast, Formation - Trax - Cat12 - 157yds | 33 | 1490 | 34 | 1647 | 157
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 28 | 154341 | A341410 | 23400217 | Brent Biscuit Factory | 12 | 2100 | LEC1 | Weekend | W0219/WIP | 2019-10-05 20:00 | 2019-10-07 04:00 | 1 day(s) 08:00 Hrs | CORE: 1 of 1 Reballast, Formation - Trax - Cat12 - 340yds | 6 | 288 | 6 | 628 | 340
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 28 | 154338 | A10410 | 122111 | Nene Up | 2 | 1100 | EMP | Weekend |  | 2019-10-05 23:00 | 2019-10-07 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail - 249yds | 100 | 511 | 100 | 760 | 249
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 28 | 154146 | A35720 | 52201520 | Flax Bourton Tunnel Up | 11 | 1100 | MLN1 | Weekend | W2019/0000000 | 2019-10-05 23:15 | 2019-10-07 15:15 | 1 day(s) 16:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 123 | 1622 | 124 | 220 | 358
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 28 | 154343 | A169410 | FD31200615A | Grantshouse North | 14 | 2100 | ECM8 | Weekend |  | 2019-10-06 00:01 | 2019-10-07 08:01 | 1 day(s) 08:00 Hrs | CORE: Grantshouse North [Week 28] Cat 14:634 yds | 40 | 266 | 40 | 900 | 634
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 28 | 154339 | A2876670 | COT22800119 | Dinting | 11 | 3400 | GDW | Weekend |  | 2019-10-06 00:20 | 2019-10-07 05:20 | 1 day(s) 05:00 Hrs | CORE: 1 of 1: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 286yds | 0 | 1590 | 1 | 116 | 286 | CC 12.06.2017 - LNWNPL-1920-038 Amend ROW code from 7 to 11
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 29 | 154343 | A291460 | 31200721 | Palmerston | 14 | 1100 | ECM8 | Weekend |  | 2019-10-12 01:00 | 2019-10-13 09:00 | 1 day(s) 08:00 Hrs | CORE: Palmerston [Week 29] Cat 14:340 yds | 35 | 110 | 35 | 450 | 340
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 29 | 154934 | G4T4210 | 44600519 | Hook Platform 2 | 14 | 2200 | BML1 | Weekend |  | 2019-10-12 01:00 | 2019-10-14 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast, Formation - Trax | 41 | 1585 | 42 | 494 | 669
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 29 | 154335 | A2465090 | 134059 | Hessay | 2 | 3100 | HAY1 | Weekend | W2019/0000000 | 2019-10-12 01:00 | 2019-10-13 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT02: Rerail - Both Rails : 18yds (Not in PPS) | 5 | 887 | 5 | 905 | 18 | PLN-1920-042 (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 29 | 154335 | A2475120 | 134059 | Hessay | 16 | 3100 | HAY1 | Weekend | W2019/0000000 | 2019-10-12 01:00 | 2019-10-13 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify (all non steel sleeper types) : 965yds (Not in PPS) | 5 | 905 | 6 | 110 | 965 | PLN-1920-042 (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 29 | 154335 | A2475130 | 134059 | Hessay | 11 | 3100 | HAY1 | Weekend | W2019/0000000 | 2019-10-12 01:00 | 2019-10-13 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 19yds (Not in PPS) | 6 | 110 | 6 | 129 | 19 | PLN-1920-042 (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 29 | 154335 | A2488200 | 131172 | Dawdon | 11 | 2100 | LEN3 | Weekend | W2019/0000000 | 2019-10-12 01:00 | 2019-10-13 | 0 day(s) 23:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 539yds | 83 | 854 | 83 | 1393 | 539 | PLN-1920-097 | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 29 | 154929 | G4T391590 | 41412019 | Dunston Hall Up | 11 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-10-12 01:35 | 2019-10-14 04:55 | 2 day(s) 03:20 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 109 | 239 | 109 | 920 | 681
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 29 | 154929 | G4T400060 | 41412019 | Dunston Hall Up | 11 | 1100 | LTN1 | Weekend | W2019/0000000 | 2019-10-12 01:35 | 2019-10-14 04:55 | 2 day(s) 03:20 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 109 | 920 | 109 | 932 | 12
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 29 | 158412 | A2459800 | 23108599 | COT Milton Keynes North | 15aa | 2100 | LEC1 | Weekend |  | 2019-10-12 22:00 | 2019-10-13 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: COT Milton Keynes North - CAT15aa - 128yds | 50 | 824 | 50 | 952 | 128
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 29 | 154146 | A14610 | 52240117 SF | Meads Crossing (Down Line) | 7 | 2100 | MLN1 | Weekend | W2019/0000000 | 2019-10-12 23:00 | 2019-10-14 02:00 | 1 day(s) 03:00 Hrs | CORE: 1/2 Reballast - Traxcavation Cat 07 | 152 | 1457 | 152 | 1604 | 147
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 29 | 154146 | A35730 | 52240117 SF | Meads Crossing (Down Line) | 11 | 2100 | MLN1 | Weekend | W2019/0000000 | 2019-10-12 23:00 | 2019-10-13 15:00 | 0 day(s) 16:00 Hrs | CORE: 1/2 Rerail, Resleeper, Reballast - Trax | 152 | 1604 | 152 | 1685 | 81
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 29 | 154338 | A15450 | 122112 | Nene Dn | 11 | 2100 | EMP | Weekend |  | 2019-10-12 23:00 | 2019-10-14 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 131yds | 100 | 516 | 100 | 647 | 131 | Yardage amended as per agreed c/c ref: PLS-1920-082
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 29 | 154341 | A397230 | 23512999 | Watford Lodge South | 14 | 1100 | HNR | Weekend |  | 2019-10-12 23:55 | 2019-10-14 05:00 | 1 day(s) 05:05 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 200yds | 78 | 750 | 78 | 950 | 200
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 29 | 154343 | A170410 | FD31200315 | Tyne Bridge | 11 | 2100 | ECM8 | Weekend |  | 2019-10-13 00:01 | 2019-10-14 08:01 | 1 day(s) 08:00 Hrs | CORE: Tyne Bridge [Week 29] Cat 11:518 yds | 23 | 34 | 23 | 552 | 518 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | A6610 | 43300119 | Chichester Up | 14 | 1100 | TBH2 | Weekend | W2019/000000 | 2019-10-19 01:00 | 2019-10-21 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 28 | 770 | 28 | 1266 | 496 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | G1420 | 43300119 | Chichester Up | 2 | 1100 | TBH2 | Weekend | W2019/000000 | 2019-10-19 01:00 | 2019-10-21 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 28 | 754 | 28 | 770 | 16 |  | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 30 | 154934 | G4T29090 | 44500814df1 | Alderbury Up | 14 | 1100 | RTJ2 | Weekend |  | 2019-10-19 01:00 | 2019-10-21 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) | 91 | 612 | 91 | 1612 | 1000
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 30 | 154335 | A2475140 | 134059 | Hessay | 16 | 3100 | HAY1 | Weekend | W2019/0000000 | 2019-10-19 01:00 | 2019-10-20 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT16: Resleeper, Rerail, Scarify (all non steel sleeper types) : 190yds (Not in PPS) | 6 | 129 | 6 | 319 | 190 | PLN-1920-042 (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 30 | 154335 | A2475150 | 134059 | Hessay | 2 | 3100 | HAY1 | Weekend | W2019/0000000 | 2019-10-19 01:00 | 2019-10-20 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT02: Rerail - Both Rails : 19yds (Not in PPS) | 6 | 319 | 6 | 338 | 19 | PLN-1920-042 (Not in PPS)
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 30 | 158412 | A2460660 | 23108599 | COT Milton Keynes North | 15aa | 2100 | LEC1 | Weekend |  | 2019-10-19 14:00 | 2019-10-20 06:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: COT Milton Keynes North - CAT15aa - 129yds | 50 | 952 | 50 | 1081 | 129
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 30 | 154335 | A2489060 | 131172 | Dawdon | 11 | 2100 | LEN3 | Weekend | W2019/0000000 | 2019-10-19 17:00 | 2019-10-20 16:00 | 0 day(s) 23:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 539yds | 83 | 1393 | 84 | 172 | 539 | PLN-1920-097 | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 30 | 154341 | A392570 | 23300319 | COT Pitstone Up | 12 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-10-19 20:00 | 2019-10-20 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2 Reballast, Formation - Trax - Cat12 - 158yds | 33 | 1647 | 34 | 45 | 158
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 30 | 154338 | A11410 | 122112 | Nene Dn | 11 | 2100 | EMP | Weekend |  | 2019-10-19 23:00 | 2019-10-21 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 132yds | 100 | 647 | 100 | 779 | 132 | Yardage amended as per agreed c/c ref: PLS-1920-082
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 30 | 154146 | A6290 | 52201620 | Flax Bourton Tunnel Dn | 11 | 2100 | MLN1 | Weekend | W2019/0000000 | 2019-10-19 23:15 | 2019-10-21 15:15 | 1 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 123 | 1324 | 123 | 1476 | 152
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 30 | 154343 | A165410 | 31300423 | Clunyden | 7 | 1100 | CWH3 | Weekend |  | 2019-10-20 00:01 | 2019-10-21 06:01 | 1 day(s) 06:00 Hrs | CORE: Clunyden [Week 11] Cat 07:650 yds | 31 | 1000 | 31 | 1650 | 650 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 30 | 154343 | A171410 | 31501020 | Luncarty Joiners Shop | 11 | 1100 | HGL1 | Weekend |  | 2019-10-20 00:01 | 2019-10-21 05:01 | 1 day(s) 05:00 Hrs | CORE: Luncarty Joiners Shop [Week 30] Cat 11:393 yds | 155 | 591 | 155 | 984 | 393 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | A12760 | 43300419 | Bosham Down | 2 | 2100 | TBH2 | Midweek Nights | W2019/000000 | 2019-10-21 04:00 | 2019-10-25 22:00 | 4 day(s) 18:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 31 | 598 | 31 | 612 | 14 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | A12770 | 43300419 | Bosham Down | 11 | 2100 | TBH2 | Midweek Nights | W2019/000000 | 2019-10-21 04:00 | 2019-10-25 22:00 | 4 day(s) 18:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 31 | 612 | 31 | 981 | 369 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | A12780 | 43300419 | Bosham Down | 2 | 2100 | TBH2 | Midweek Nights | W2019/000000 | 2019-10-21 04:00 | 2019-10-25 22:00 | 4 day(s) 18:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 31 | 1320 | 31 | 1339 | 19 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | A8690 | 43300419 | Bosham Down | 14 | 2100 | TBH2 | Midweek Nights | W2019/000000 | 2019-10-21 04:00 | 2019-10-25 22:00 | 4 day(s) 18:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 31 | 981 | 31 | 1320 | 339 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | A935740 | 43300518 | Bosham Up | 11 | 1100 | TBH2 | Midweek Nights | W2019/000000 | 2019-10-21 04:00 | 2019-10-25 22:00 | 4 day(s) 18:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 31 | 612 | 31 | 981 | 369 | SUS-1929-17 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | A935750 | 43300518 | Bosham Up | 14 | 1100 | TBH2 | Midweek Nights | W2019/000000 | 2019-10-21 04:00 | 2019-10-25 22:00 | 4 day(s) 18:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 31 | 981 | 31 | 1320 | 339 | SUS-1929-17 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | A935760 | 43300518 | Bosham Up | 2 | 1100 | TBH2 | Midweek Nights | W2019/000000 | 2019-10-21 04:00 | 2019-10-25 22:00 | 4 day(s) 18:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 31 | 1320 | 31 | 1336 | 16 | SUS-1929-17 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 30 | 154931 | G4T15790 | 43300518 | Bosham Up | 2 | 1100 | TBH2 | Midweek Nights | W2019/000000 | 2019-10-21 04:00 | 2019-10-25 22:00 | 4 day(s) 18:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 31 | 597 | 31 | 612 | 15 | SUS-1929-17 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 31 | 154931 | A7650 | 43300219 | Chichester Down | 14 | 2100 | TBH2 | Weekend | W2019/000000 | 2019-10-25 22:00 | 2019-10-28 04:00 | 2 day(s) 06:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 28 | 770 | 28 | 1261 | 491 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 31 | 154931 | G1410 | 43300219 | Chichester Down | 2 | 2100 | TBH2 | Weekend | W2019/000000 | 2019-10-25 22:00 | 2019-10-28 04:00 | 2 day(s) 06:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 28 | 754 | 28 | 770 | 16 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 31 | 154341 | A368450 | 24102519 | P76 Crendon Road | 14 | 2100 | NAJ2 | Weekend | W2019/WIP | 2019-10-26 01:00 | 2019-10-28 05:00 | 2 day(s) 04:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 685yds | 31 | 1325 | 32 | 250 | 685
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 31 | 154335 | A2451090 | 125228 | Askham Tunnel | 11 | 2100 | ECM1 | Weekend | W2019/0000000 | 2019-10-26 01:00 | 2019-10-27 11:30 | 1 day(s) 10:30 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 528yds (Not in PPS) | 134 | 440 | 134 | 968 | 528 | (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 31 | 154335 | A2485000 | 125258 | Peascliffe-Gadds Bridge Up | 14 | 1100 | ECM1 | Weekend | W2019/0000000 | 2019-10-26 01:00 | 2019-10-27 11:30 | 1 day(s) 10:30 Hrs | CORE: CAT14: Rerail, Resleeper, Reballast, Formation - Trax: 282yds (Not in PPS) | 108 | 638 | 108 | 920 | 282 | Not in PPS
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 31 | 154339 | A2904930 | 21100919 | Park South | 2 | 3400 | CBC1 | Weekend |  | 2019-10-26 22:45 | 2019-10-28 05:35 | 1 day(s) 06:50 Hrs | CORE: 2 of 3: Park South - Rerail (Both Rails) - CAT02 - 6yds | 32 | 1634 | 32 | 1640 | 6
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 31 | 154339 | A4310 | 21100919 | Park South | 11 | 3400 | CBC1 | Weekend |  | 2019-10-26 22:45 | 2019-10-28 05:35 | 1 day(s) 06:50 Hrs | CORE: 1 of 3: Park South - Rerail, Resleeper, Reballast (Trax) - CAT11 - 254yds | 32 | 1135 | 32 | 1389 | 254
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 31 | 154338 | A15460 | 121048 | Watton on Stone Up | 14 | N/A | HDB | Weekend |  | 2019-10-26 23:00 | 2019-10-28 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax - 374yds | 23 | 220 | 23 | 594 | 374 | Job moved from Wk's 34 & 35 to Wk's 31, 32 & 33 as per C/C ref: PLS-1920-120 | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 31 | 154146 | WES16630 | 52240415 | Wick (Dn) | 14 | 2100 | BGL2 | Weekend | W2019/0000000 | 2019-10-26 23:40 | 2019-10-28 04:30 | 1 day(s) 04:50 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 110 | 535 | 110 | 1143 | 608
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 31 | 154343 | A164410 | FD100019 | Dunfermline Station | 14 | 1100 | CWH1 | Weekend |  | 2019-10-27 00:01 | 2019-10-28 05:01 | 1 day(s) 05:00 Hrs | CORE: Dunfermline Station [Week 12] Cat 14:105 yds | 16 | 1627 | 16 | 1732 | 105
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 31 | 154343 | A291400 | FD100019 | Dunfermline Station | 11 | 1100 | CWH1 | Weekend |  | 2019-10-27 00:01 | 2019-10-28 05:01 | 1 day(s) 05:00 Hrs | CORE: Dunfermline Station [Week 12] Cat 11:319 yds | 17 | 66 | 17 | 385 | 319
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 31 | 154343 | A291510 | 31502123 | Perth North Down | 13 | 2100 | HGL1 | Weekend |  | 2019-10-27 00:01 | 2019-10-28 05:01 | 1 day(s) 05:00 Hrs | CORE: Perth North Down [Week 31] Cat 13:331 yds | 151 | 1097 | 151 | 1428 | 331
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 31 | 154934 | A1350 | 44500814df1 | Alderbury Up | 14 | 1100 | RTJ2 | Weekend |  | 2019-10-27 00:25 | 2019-10-28 04:00 | 1 day(s) 03:35 Hrs | CORE: 2/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) | 91 | 1612 | 92 | 188 | 336
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 31 | 154341 | A47580 | 24100812s | P76 Brill | 2 | 2100 | NAJ3 | Weekend |  | 2019-10-27 01:00 | 2019-10-28 05:00 | 1 day(s) 04:00 Hrs | CORE: 1 of 1: P76 Brill - Rerail - Both Rails - CAT02 - 903yds | 1 | 861 | 2 | 4 | 903
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 32 | 154335 | A2486040 | 125259 | Peascliffe-Gadds Bridge Dn | 14 | 2100 | ECM1 | Weekend | W2019/0000000 | 2019-11-02 01:00 | 2019-11-03 | 0 day(s) 23:00 Hrs | CORE: CAT14: Rerail, Resleeper, Reballast, Formation - Trax: 228yds (Not in PPS) | 108 | 638 | 109 | 866 | 228 | Not in PPS
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 32 | 154930 | A29660 | 42200518 | Mottingham to Sidcup Dn | 2 | 2100 | HDR | Weekend | W2019/000000 | 2019-11-02 01:15 | 2019-11-04 02:50 | 2 day(s) 01:35 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 9 | 868 | 9 | 880 | 12 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 32 | 154930 | A30610 | 42200518 | Mottingham to Sidcup Dn | 11 | 2100 | HDR | Weekend | W2019/000000 | 2019-11-02 01:15 | 2019-11-04 02:50 | 2 day(s) 01:35 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 9 | 880 | 10 | 0 | 880 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 32 | 154929 | A13890 | 41501619 | Mile End Dn Main | 11 | 2100 | LTN1 | Weekend | W2019/0000000 | 2019-11-02 01:30 | 2019-11-04 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 13 | 3 | 196 | 183
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 32 | 154929 | A931530 | 41501619 | Mile End Dn Main | 1 | 2100 | LTN1 | Weekend | W2019/0000000 | 2019-11-02 01:30 | 2019-11-04 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/1 Rerail - One Rail Only Cat:01 | 2 | 1757 | 2 | 1759 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 32 | 154929 | A931540 | 41501619 | Mile End Dn Main | 2 | 2100 | LTN1 | Weekend | W2019/0000000 | 2019-11-02 01:30 | 2019-11-04 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 2 | 1759 | 3 | 13 | 14
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 32 | 154929 | A931550 | 41501619 | Mile End Dn Main | 2 | 2100 | LTN1 | Weekend | W2019/0000000 | 2019-11-02 01:30 | 2019-11-04 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 3 | 196 | 3 | 199 | 3
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 32 | 154929 | A931570 | 41501619 | Mile End Dn Main | 11 | 2100 | LTN1 | Weekend | W2019/0000000 | 2019-11-02 01:30 | 2019-11-04 04:00 | 2 day(s) 02:30 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 268 | 3 | 416 | 148
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 32 | 154341 | A349730 | WTS280163s | COT Harlesden | 11 | 2801 | WTS | Weekend | W2019/WIP | 2019-11-02 20:00 | 2019-11-04 05:00 | 1 day(s) 09:00 Hrs | CORE: 1 of 3 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat11 - 159yds | 6 | 689 | 6 | 848 | 159
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 32 | 154339 | A2905280 | 21100919 | Park South | 11 | 3400 | CBC1 | Weekend |  | 2019-11-02 22:45 | 2019-11-04 05:35 | 1 day(s) 06:50 Hrs | CORE: 3 of 3: Park South - Rerail, Resleeper, Reballast (Trax) - CAT11 - 245yds | 32 | 1389 | 32 | 1634 | 245
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 32 | 154338 | A6410 | 121048 | Watton on Stone Up | 14 | N/A | HDB | Weekend |  | 2019-11-02 23:00 | 2019-11-04 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax - 373yds | 23 | 594 | 23 | 967 | 373 | Job moved from Wk's 34 & 35 to Wk's 31, 32 & 33 as per C/C ref: PLS-1920-120 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 32 | 154343 | A291410 | FD100019 | Dunfermline Station | 14 | 1100 | CWH1 | Weekend |  | 2019-11-03 00:01 | 2019-11-04 05:01 | 1 day(s) 05:00 Hrs | CORE: Dunfermline Station [Week 13] Cat 14:94 yds | 16 | 1732 | 17 | 66 | 94
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 32 | 154343 | A291420 | FD100019 | Dunfermline Station | 11 | 1100 | CWH1 | Weekend |  | 2019-11-03 00:01 | 2019-11-04 05:01 | 1 day(s) 05:00 Hrs | CORE: Dunfermline Station [Week 13] Cat 11:321 yds | 17 | 385 | 17 | 706 | 321
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 32 | 154343 | A291500 | 31502123 | Perth North Down | 13 | 2100 | HGL1 | Weekend |  | 2019-11-03 00:01 | 2019-11-04 05:01 | 1 day(s) 05:00 Hrs | CORE: Perth North Down [Week 32] Cat 13:332 yds | 151 | 1428 | 152 | 0 | 332
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 32 | 154146 | A2130 | 51240519 | Windsor | 2 | 3100 | WIN | Weekend | W2019/0000000 | 2019-11-03 00:25 | 2019-11-04 05:30 | 1 day(s) 05:05 Hrs | CORE: 1/2 Rerail - Both Rails Cat: 02 | 19 | 1320 | 20 | 363 | 803
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 32 | 154341 | A386130 | 24301119 | COT Trent River Bridge | 14 | 1100 | RRN2 | Weekend |  | 2019-11-03 00:40 | 2019-11-04 05:40 | 1 day(s) 05:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 280yds | 14 | 250 | 14 | 530 | 280
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 32 | 154934 | G4T30240 | 44601015 | Walton on Thames | 11 | 1200 | BML1 | Weekend |  | 2019-11-03 01:10 | 2019-11-04 04:00 | 1 day(s) 02:50 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 16 | 1667 | 17 | 288 | 381
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 33 | 154934 | G4T6290 | 44602115 | Basingstoke Canal aquaduct | 11 | 1200 | BML1 | Weekend |  | 2019-11-09 01:00 | 2019-11-11 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 31 | 440 | 31 | 1391 | 951
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 33 | 154335 | A2453090 | 125230 | Grantham Up | 11 | 1100 | ECM1 | Weekend | W2019/0000000 | 2019-11-09 01:00 | 2019-11-10 11:00 | 1 day(s) 10:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 248yds (Not in PPS) | 104 | 1480 | 104 | 1728 | 248 | CC PLN-1920-043
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 33 | 154335 | A2475170 | 125230 | Grantham Up | 2 | 1100 | ECM1 | Weekend | W2019/0000000 | 2019-11-09 01:00 | 2019-11-10 11:00 | 1 day(s) 10:00 Hrs | CORE: CAT02: Rerail - Both Rails : 6yds (Not in PPS) | 104 | 1728 | 104 | 1734 | 6 | CC PLN-1920-043
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 33 | 154335 | A2487000 | 125259 | Peascliffe-Gadds Bridge Dn | 14 | 2100 | ECM1 | Weekend | W2019/0000000 | 2019-11-09 01:00 | 2019-11-10 | 0 day(s) 23:00 Hrs | CORE: CAT14: Rerail, Resleeper, Reballast, Formation - Trax: 227yds (Not in PPS) | 108 | 866 | 109 | 1093 | 227 | Not in PPS
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 33 | 154930 | A30620 | 42200518 | Mottingham to Sidcup Dn | 2 | 2100 | HDR | Weekend | W2019/000000 | 2019-11-09 01:15 | 2019-11-11 02:50 | 2 day(s) 01:35 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 10 | 880 | 10 | 892 | 12 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 33 | 154930 | G4T123220 | 42200518 | Mottingham to Sidcup Dn | 11 | 2100 | HDR | Weekend | W2019/000000 | 2019-11-09 01:15 | 2019-11-11 02:50 | 2 day(s) 01:35 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 10 | 0 | 10 | 880 | 880 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 33 | 154146 | A5250 | 51140519 | Ealing Broadway DR Platform | 11 | 2200 | MLN1 | Weekend | W2019/0000000 | 2019-11-09 20:00 | 2019-11-10 12:00 | 0 day(s) 16:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 5 | 1130 | 5 | 1322 | 192
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 33 | 154341 | A342450 | 23400219 | COT Camden | 14 | 1200 | LEC1 | Weekend |  | 2019-11-09 20:00 | 2019-11-10 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 170yds | 1 | 930 | 1 | 1100 | 170
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 33 | 154341 | A394800 | 23100819A | COT Loughton | 14 | 1200 | LEC1 | Weekend |  | 2019-11-09 20:00 | 2019-11-10 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 160yds | 48 | 1266 | 48 | 1426 | 160
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 33 | 154339 | A2902680 | 21101416 | DRIGG | 11 | 1100 | CBC1 | Weekend |  | 2019-11-09 21:15 | 2019-11-11 06:20 | 1 day(s) 09:05 Hrs | CORE: 1 of 1: CAT11 - Rerail, Resleeper, Reballast - Trax - 236yds | 62 | 147 | 62 | 383 | 300
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 33 | 154338 | A16580 | 121048 | Watton on Stone Up | 14 | N/A | HDB | Weekend |  | 2019-11-09 23:00 | 2019-11-11 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax - 373yds | 23 | 967 | 23 | 1340 | 373 | Job moved from Wk's 34 & 35 to Wk's 31, 32 & 33 as per C/C ref: PLS-1920-120 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 33 | 154343 | A2868030 | 31404017 | Kingussie | 11 | 2500 | HGL2 | Weekend |  | 2019-11-10 00:01 | 2019-11-11 05:01 | 1 day(s) 05:00 Hrs | CORE: Luncarty Joiners Shop [Week 30] Cat 11:393 yds | 71 | 670 | 71 | 1230 | 560 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 33 | 154343 | A2869040 | 31400917 | Kingussie Gynack Bridge | 41A | 2500 | HGL2 | Weekend |  | 2019-11-10 00:01 | 2019-11-11 05:01 | 1 day(s) 05:00 Hrs | CORE: Luncarty Joiners Shop [Week 30] Cat 11:393 yds | 71 | 1090 | 71 | 1100 | 10 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 33 | 154146 | A35740 | 51240519 | Windsor | 2 | 3100 | WIN | Weekend | W2019/0000000 | 2019-11-10 00:25 | 2019-11-11 05:30 | 1 day(s) 05:05 Hrs | CORE: 2/2 Rerail - Both Rails Cat: 02 | 20 | 363 | 20 | 1166 | 803
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 34 | 154931 | A5570 | 43300519 | Little Browns and Edenbridge Tunnel | 11 | 2100 | SCU1 | Weekend | W2019/000000 | 2019-11-16 00:50 | 2019-11-18 04:00 | 2 day(s) 03:10 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 24 | 206 | 24 | 564 | 358 | SUS-1920-32 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 34 | 154931 | G4T168950 | 43300519 | Little Browns and Edenbridge Tunnel | 2 | 2100 | SCU1 | Weekend | W2019/000000 | 2019-11-16 00:50 | 2019-11-18 04:00 | 2 day(s) 03:10 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 193 | 24 | 206 | 13 | SUS-1920-32 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 34 | 154931 | G4T168960 | 43300519 | Little Browns and Edenbridge Tunnel | 2 | 2100 | SCU1 | Weekend | W2019/000000 | 2019-11-16 00:50 | 2019-11-18 04:00 | 2 day(s) 03:10 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 564 | 24 | 577 | 13 | SUS-1920-32 | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 34 | 154934 | G4T11490 | 44205715 | Northam Curve Down | 11 | 3104 | BML2 | Weekend |  | 2019-11-16 01:00 | 2019-11-18 03:00 | 2 day(s) 02:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 78 | 291 | 78 | 667 | 376
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 34 | 154335 | A2487010 | 125259 | Peascliffe-Gadds Bridge Dn | 14 | 2100 | ECM1 | Weekend | W2019/0000000 | 2019-11-16 01:00 | 2019-11-17 | 0 day(s) 23:00 Hrs | CORE: CAT14: Rerail, Resleeper, Reballast, Formation - Trax: 227yds (Not in PPS) | 108 | 1093 | 109 | 1320 | 227 | Not in PPS
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 34 | 154146 | A35750 | 51140519 | Ealing Broadway DR Platform | 11 | 2200 | MLN1 | Weekend | W2019/0000000 | 2019-11-16 20:00 | 2019-11-17 12:00 | 0 day(s) 16:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 5 | 1322 | 5 | 1513 | 191
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 34 | 154341 | A392680 | WTS280163s | COT Harlesden | 11 | 2801 | WTS | Weekend | W2019/WIP | 2019-11-16 20:00 | 2019-11-18 05:00 | 1 day(s) 09:00 Hrs | CORE: 2 of 3 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat11 - 159yds | 6 | 848 | 6 | 1007 | 159
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 34 | 154341 | A394810 | 23100819A | COT Loughton | 14 | 1200 | LEC1 | Weekend |  | 2019-11-16 20:00 | 2019-11-17 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 159yds | 48 | 1426 | 48 | 1585 | 159
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 34 | 154339 | A12410 | 21101019 | Ravenglass / Drigg | 4 | 2100 | CBC1 | Weekend |  | 2019-11-16 21:15 | 2019-11-18 06:20 | 1 day(s) 09:05 Hrs | CORE: 1 of 7: Ravenglass / Drigg - Rerail, Resleeper (Steel) - CAT04 - 590yds | 59 | 1170 | 60 | 0 | 590
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 34 | 154339 | A12420 | 21101019 | Ravenglass / Drigg | 2 | 2100 | CBC1 | Weekend |  | 2019-11-16 21:15 | 2019-11-18 06:20 | 1 day(s) 09:05 Hrs | CORE: 2 of 7: Ravenglass / Drigg - Rerail (Both Rails) - CAT02 - 70yds | 59 | 1100 | 59 | 1170 | 70
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 34 | 154338 | A7410 | 121157 | Watton on Stone Dn | 14 | 2100 | HDB | Weekend |  | 2019-11-16 23:00 | 2019-11-18 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax - 374yds | 23 | 220 | 23 | 594 | 374 | Job moved from Wk's 31 & 32 to Wk's 34,35 & 36 as per C/C ref: PLS-1920-121 | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 34 | 154146 | WES41110 | 51225615 | Furze Platt (Sgl) | 11 | 3100 | WBB | Weekend | W2019/0000000 | 2019-11-17 00:40 | 2019-11-18 05:15 | 1 day(s) 04:35 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 25 | 748 | 25 | 1001 | 253
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 34 | 154146 | WES57360 | 51225615 | Furze Platt (Sgl) | 15a | 3100 | WBB | Weekend | W2019/0000000 | 2019-11-17 00:40 | 2019-11-18 05:15 | 1 day(s) 04:35 Hrs | CORE:1/1 Drain (Associated With Track Renewal) Cat:15a | 25 | 748 | 25 | 918 | 170
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 34 | 154343 | A248410 | 31100322 | Whitemoss South | 11 | 2100 | SCM4 | Weekend |  | 2019-11-17 01:00 | 2019-11-18 06:00 | 1 day(s) 05:00 Hrs | CORE: Whitemoss South [Week 34] Cat 11:497 yds | 139 | 1123 | 139 | 1620 | 497 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 35 | 154930 | A25330 | 42200814sf1 | Forest Hill Up Slow (Drain) | 15ba | 1200 | LBW | Weekend | W2019/000000 | 2019-11-23 01:00 | 2019-11-25 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/1 Drain (Unassociated With Track Renewal) Cat:15b | 5 | 1630 | 6 | 614 | 744 | KENT-1920-31 | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 35 | 154335 | A2452090 | 125229 | Grantham Dn | 14 | 2100 | ECM1 | Weekend | W2019/0000000 | 2019-11-23 01:00 | 2019-11-24 | 0 day(s) 23:00 Hrs | CORE: CAT14: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 295yds (Not in PPS) | 104 | 1480 | 105 | 15 | 295 | (Not in PPS)
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 35 | 154146 | A35820 | 51440117 | Leonards Mill | 11 | 3100 | FNS2 | Weekend | W2019/0000000 | 2019-11-23 19:30 | 2019-11-24 19:30 | 1 day(s) 00:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 1 | 0 | 1 | 220 | 220
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 35 | 154341 | A316450 | 23100819A | COT Loughton | 14 | 1200 | LEC1 | Weekend |  | 2019-11-23 20:00 | 2019-11-24 12:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 159yds | 48 | 1585 | 48 | 1744 | 159
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 35 | 154341 | A392690 | WTS280163s | COT Harlesden | 11 | 2801 | WTS | Weekend | W2019/WIP | 2019-11-23 20:00 | 2019-11-25 05:00 | 1 day(s) 09:00 Hrs | CORE: 3 of 3 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat11 - 158yds | 6 | 1007 | 6 | 1165 | 158
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 35 | 154339 | A12400 | 21101019 | Ravenglass / Drigg | 4 | 2100 | CBC1 | Weekend |  | 2019-11-23 21:15 | 2019-11-25 06:20 | 1 day(s) 09:05 Hrs | CORE: 3 of 7: Ravenglass / Drigg - Rerail, Resleeper (Steel) - CAT04 - 1400yds | 58 | 300 | 58 | 1700 | 1400
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 35 | 154338 | A15440 | 121157 | Watton on Stone Dn | 14 | 2100 | HDB | Weekend |  | 2019-11-23 23:00 | 2019-11-25 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax - 373yds | 23 | 594 | 23 | 967 | 373 | Job moved from Wk's 31 & 32 to Wk's 34,35 & 36 as per C/C ref: PLS-1920-121 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 35 | 154343 | A263410 | 31500721 | Inchture Level Crossing | 14 | 2100 | SCM5 | Weekend |  | 2019-11-24 00:01 | 2019-11-26 04:01 | 2 day(s) 04:00 Hrs | CORE: Inchture Level Crossing [Week 35] Cat 14:345 yds | 8 | 50 | 8 | 395 | 345 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 35 | 154146 | A35760 | 51225615 | Furze Platt (Sgl) | 11 | 3100 | WBB | Weekend | W2019/0000000 | 2019-11-24 00:40 | 2019-11-25 05:15 | 1 day(s) 04:35 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 25 | 1001 | 25 | 1254 | 253
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 35 | 154146 | A35790 | 51225615 | Furze Platt (Sgl) | 15a | 3100 | WBB | Weekend | W2019/0000000 | 2019-11-24 00:40 | 2019-11-25 05:15 | 1 day(s) 04:35 Hrs | CORE:1/1 Drain (Associated With Track Renewal) Cat:15a | 25 | 918 | 25 | 1088 | 170
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 35 | 154343 | A291540 | 31100322 | Whitemoss South | 11 | 2100 | SCM4 | Weekend |  | 2019-11-24 01:00 | 2019-11-25 06:00 | 1 day(s) 05:00 Hrs | CORE: Whitemoss South [Week 35] Cat 11:470 yds | 139 | 1620 | 140 | 330 | 470 |  | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 36 | 154929 | G4T394010 | 41120212df1 | Thorpe Bay | 11 | 2100 | FSS3 | Weekend |  | 2019-11-30 01:00 | 2019-12-02 03:00 | 2 day(s) 02:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 37 | 1239 | 37 | 1430 | 191 | 04/06/18 GG - Job restaged. CC ref WA-1920-24 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 36 | 154929 | G4T394920 | 41120212df1 | Thorpe Bay | 2 | 2100 | FSS3 | Weekend |  | 2019-11-30 01:00 | 2019-12-02 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 37 | 1237 | 37 | 1239 | 2 | 04/06/18 GG - Job restaged. CC ref WA-1920-24 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 36 | 154929 | G4T394930 | 41120212df1 | Thorpe Bay | 2 | 2100 | FSS3 | Weekend |  | 2019-11-30 01:00 | 2019-12-02 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 38 | 261 | 38 | 271 | 10 | 04/06/18 GG - Job restaged. CC ref WA-1920-24 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 36 | 154929 | G4T394940 | 41120212df1 | Thorpe Bay | 11 | 2100 | FSS3 | Weekend |  | 2019-11-30 01:00 | 2019-12-02 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 37 | 1430 | 38 | 261 | 591 | 04/06/18 GG - Job restaged. CC ref WA-1920-24 refers
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 36 | 154146 | A12530 | 51440117 | Leonards Mill | 11 | 3100 | FNS2 | Weekend | W2019/0000000 | 2019-11-30 19:30 | 2019-12-01 19:30 | 1 day(s) 00:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 1 | 220 | 1 | 440 | 220
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 36 | 154341 | A338290 | 23302399 | West London Junction | 14 | 2100 | LEC1 | Weekend | W2019/WIP | 2019-11-30 20:00 | 2019-12-01 12:00 | 0 day(s) 16:00 Hrs | CORE: 1of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 71yds | 5 | 264 | 5 | 335 | 71
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 36 | 154339 | A11450 | 21101019 | Ravenglass / Drigg | 2 | 2100 | CBC1 | Weekend |  | 2019-11-30 21:15 | 2019-12-02 06:20 | 1 day(s) 09:05 Hrs | CORE: 4 of 7: Ravenglass / Drigg - Rerail (Both Rails) - CAT02 - 90yds | 58 | 210 | 58 | 300 | 90
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 36 | 154339 | A12380 | 21101019 | Ravenglass / Drigg | 4 | 2100 | CBC1 | Weekend |  | 2019-11-30 21:15 | 2019-12-02 06:20 | 1 day(s) 09:05 Hrs | CORE: 5 of 7: Ravenglass / Drigg - Rerail, Resleeper (Steel) - CAT04 - 244yds | 57 | 1340 | 57 | 1584 | 244
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 36 | 154339 | A12390 | 21101019 | Ravenglass / Drigg | 4 | 2100 | CBC1 | Weekend |  | 2019-11-30 21:15 | 2019-12-02 06:20 | 1 day(s) 09:05 Hrs | CORE: 6 of 7: Ravenglass / Drigg - Rerail, Resleeper (Steel) - CAT04 - 200yds | 58 | 10 | 58 | 210 | 200
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 36 | 154339 | A12430 | 21101019 | Ravenglass / Drigg | 11 | 2100 | CBC1 | Weekend |  | 2019-11-30 21:15 | 2019-12-02 06:20 | 1 day(s) 09:05 Hrs | CORE: 7 of 7: Ravenglass / Drigg - Rerail, Resleeper, Reballast - Trax - CAT11 - 186yds | 57 | 1584 | 58 | 10 | 186
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 36 | 158412 | A2454600 | 23406099 | West London Drainage (Fast Lines) | 15aa | 2100 | LEC1 | Weekend |  | 2019-11-30 22:00 | 2019-12-01 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: West London Drainage (Fast Lines) - CAT15aa - 71yds | 5 | 264 | 5 | 335 | 71
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 36 | 154338 | A16590 | 121157 | Watton on Stone Dn | 14 | 2100 | HDB | Weekend |  | 2019-11-30 23:00 | 2019-12-02 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14: Formation, Reballast, Resleeper, Rerail - Trax - 373yds | 23 | 967 | 23 | 1340 | 373 | Job moved from Wk's 31 & 32 to Wk's 34,35 & 36 as per C/C ref: PLS-1920-121 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 36 | 154343 | A264410 | 31500821 | Grange Level Crossing | 31 | 2100 | SCM5 | Weekend |  | 2019-12-01 00:01 | 2019-12-02 05:01 | 1 day(s) 05:00 Hrs | CORE: Grange Level Crossing [Week 36] Cat 31:764 yds | 8 | 395 | 8 | 1159 | 764
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 36 | 154343 | A2862820 | 31500821 | Grange Level Crossing | 31 | 2100 | SCM5 | Weekend |  | 2019-12-01 00:01 | 2019-12-02 05:01 | 1 day(s) 05:00 Hrs | CORE: Grange Level Crossing [Week 36] Cat 31:801 yds | 8 | 1159 | 9 | 200 | 801
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 36 | 154146 | A35770 | 51225615 | Furze Platt (Sgl) | 11 | 3100 | WBB | Weekend | W2019/0000000 | 2019-12-01 00:40 | 2019-12-02 05:15 | 1 day(s) 04:35 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 25 | 2177 | 25 | 1507 | 253
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 36 | 154146 | A35800 | 51225615 | Furze Platt (Sgl) | 15a | 3100 | WBB | Weekend | W2019/0000000 | 2019-12-01 00:40 | 2019-12-02 05:15 | 1 day(s) 04:35 Hrs | CORE:1/1 Drain (Associated With Track Renewal) Cat:15a | 25 | 1088 | 25 | 1258 | 170
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 36 | 154343 | A291550 | 31100322 | Whitemoss South | 11 | 2100 | SCM4 | Weekend |  | 2019-12-01 01:00 | 2019-12-03 07:00 | 2 day(s) 06:00 Hrs | CORE: Whitemoss South [Week 36] Cat 11:479 yds | 140 | 330 | 140 | 809 | 479 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 37 | 154343 | A247410 | 31501523 | Gleneagles Station | 11 | 1100 | SCM4 | Weekend |  | 2019-12-07 01:00 | 2019-12-09 07:00 | 2 day(s) 06:00 Hrs | CORE: Gleneagles Station [Week 37] Cat 11:660 yds | 135 | 671 | 135 | 1331 | 660 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 37 | 154930 | A28580 | 42300213df1sf1 | Roman Way Strood Dn (Shortfall) | 11 | 2100 | VIR | Weekend | W2019/000000 | 2019-12-07 01:00 | 2019-12-09 05:00 | 2 day(s) 04:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 31 | 1611 | 32 | 681 | 830 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 37 | 154930 | G4T123240 | 42300213df1sf1 | Roman Way Strood Dn (Shortfall) | 2 | 2100 | VIR | Weekend | W2019/000000 | 2019-12-07 01:00 | 2019-12-09 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 31 | 1597 | 31 | 1611 | 14 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 37 | 154930 | G4T123250 | 42300213df1sf1 | Roman Way Strood Dn (Shortfall) | 2 | 2100 | VIR | Weekend | W2019/000000 | 2019-12-07 01:00 | 2019-12-09 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 32 | 681 | 32 | 694 | 13 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 37 | 154146 | A29480 | 51140819 | Paddington Platform 12 | 2 | 3612 | MLN1 | Weekend | W2019/0000000 | 2019-12-07 01:00 | 2019-12-07 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW Rerail - Both Rails | 0 | 68 | 0 | 268 | 200
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 37 | 154341 | A391330 | 23400316 | South Hampstead | 14 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-12-07 20:00 | 2019-12-08 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - CAT14 - 141yds | 2 | 612 | 2 | 753 | 141
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 37 | 158412 | A2462920 | 23309299 | Northchurch Tunnel | 15aa | 1100 | LEC1 | Weekend |  | 2019-12-07 22:00 | 2019-12-08 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: Northchurch Tunnel - CAT15aa - 129yds | 29 | 440 | 29 | 569 | 129
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 37 | 154334 | A31450 | 112067 | Kingston | 14 | 1200 | SPC5 | Weekend | W2019/0000000 | 2019-12-07 23:00 | 2019-12-09 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 Formation, Reballast, Resleeper, Rerail - Trax - 297yds | 117 | 1435 | 117 | 1732 | 297 | Volume amended to Cat 14 - 297yds and dated in Week.37 as per C/C ref: PLN-1920-089. | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 37 | 154334 | A4450 | 114593 | Corby Tunnel | 11 | 1100 | GSM1 | Weekend |  | 2019-12-07 23:00 | 2019-12-09 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Rerail, Resleeper, Reballast - Trax - 2337yds | 80 | 1613 | 82 | 430 | 2337 | East Mids 2019-20 IP Plain Line Complete Trax Workbank - extract from RAMP on 26-09-2016. Work Category amended as per c/c ref: PLS-1920-091 now Cat 11 vice 14. | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 37 | 154146 | A35780 | 51225615 | Furze Platt (Sgl) | 11 | 3100 | WBB | Weekend | W2019/0000000 | 2019-12-08 00:40 | 2019-12-09 05:15 | 1 day(s) 04:35 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 25 | 1507 | 26 | 0 | 253
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 37 | 154146 | A35810 | 51225615 | Furze Platt (Sgl) | 15a | 3100 | WBB | Weekend | W2019/0000000 | 2019-12-08 00:40 | 2019-12-09 05:15 | 1 day(s) 04:35 Hrs | CORE:1/1 Drain (Associated With Track Renewal) Cat:15a | 25 | 1258 | 25 | 1430 | 172
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 37 | 154339 | A2898510 | 21201013 | Kitsonwood tunnel | 11 | 2100 | FHR6 | Weekend |  | 2019-12-08 01:00 | 2019-12-09 05:00 | 1 day(s) 04:00 Hrs | CORE: 1 of 1: CAT11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) -370yds | 28 | 1630 | 29 | 240 | 370
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 37 | 154934 | A2700 | 44200820 | Fareham | 11 | 3102 | ETF | Weekend |  | 2019-12-08 01:00 | 2019-12-09 04:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 83 | 1626 | 84 | 112 | 246
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 37 | 154934 | G4T13570 | 44200820 | Fareham | 11 | 3102 | ETF | Weekend |  | 2019-12-08 01:00 | 2019-12-09 04:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 83 | 1409 | 83 | 1582 | 173
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 38 | 158412 | A2463780 | 23309299 | Northchurch Tunnel | 15aa | 1100 | LEC1 | Weekend |  | 2019-12-14 14:00 | 2019-12-15 06:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: Northchurch Tunnel - CAT15aa - 129yds | 29 | 569 | 29 | 698 | 129
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 38 | 154341 | A392660 | 23400316 | South Hampstead | 14 | 1100 | LEC1 | Weekend | W2019/WIP | 2019-12-14 20:00 | 2019-12-15 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - CAT14 - 141yds | 2 | 753 | 2 | 894 | 141
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 38 | 154334 | A52240 | 114594D | Corby Tunnel Drainage | 15ba | 2100 | GSM1 | Weekend |  | 2019-12-14 23:00 | 2019-12-16 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 15a - PL Drainage - associated - 2014yds | 80 | 1595 | 82 | 89 | 2014 | Separate Drainage job created as per c/c ref: PLS-1920-132
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Carillion Rail | Peterborough | 19/20 | 38 | 154334 | A5450 | 114594 | Corby Tunnel-1 | 11 | 2100 | GSM1 | Weekend |  | 2019-12-14 23:00 | 2019-12-16 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Rerail, Resleeper, Reballast, Trax - 2337yds | 80 | 1613 | 82 | 430 | 2337 | East Mids 2019-20 IP Plain Line Complete Trax Workbank - extract from RAMP on 26-09-2016. Work Cat amended to Cat 11 vice Cat 14 as per c/c ref: PLS-1920-092 | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 38 | 154934 | G4T22930 | 44450418 | Wallington viaduct | 11 | 1100 | SDP2 | Weekend |  | 2019-12-15 01:00 | 2019-12-16 04:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 85 | 633 | 85 | 972 | 339
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 39 | 154930 | A18050 | 42300119 | Herne Bay Up | 14 | 1100 | VIR | Weekend | W2019/000000 | 2019-12-21 01:00 | 2019-12-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 62 | 220 | 62 | 1001 | 781
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 39 | 154930 | G4T123260 | 42300119 | Herne Bay Up | 2 | 1100 | VIR | Weekend | W2019/000000 | 2019-12-21 01:00 | 2019-12-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 62 | 205 | 62 | 220 | 15
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 39 | 154146 | A15650 | 51100319 | Paddington | 11 | 3611 | MLN1 | Weekend | W2019/0000000 | 2019-12-21 01:00 | 2019-12-22 01:00 | 1 day(s) 00:00 Hrs | CORE: 1/1 Reballast, Formation - Trax Cat: 12 | 1 | 220 | 1 | 440 | 220
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 39 | 154934 | G4T23970 | 44501515sf2 | Chetnole | 4 | 3100 | WEY | Weekend |  | 2019-12-21 21:10 | 2019-12-23 04:30 | 1 day(s) 07:20 Hrs | CORE: 1/1 Rerail, Resleeper | 148 | 507 | 148 | 1361 | 854
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 39 | 154146 | WES45190 | 51140213 | Paddington Line 3 | 12 | 3103 | MLN1 | Weekend | W2019/0000000 | 2019-12-21 23:00 | 2019-12-23 02:00 | 1 day(s) 03:00 Hrs | CORE:1/1 Reballast, Formation - Trax Cat:12 | 1 | 220 | 1 | 440 | 220
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 39 | 154343 | A250410 | 32301119 | Shields Road | 14 | 2100 | AYR1 | Weekend |  | 2019-12-22 00:01 | 2019-12-23 09:01 | 1 day(s) 09:00 Hrs | CORE: Shields Road [Week 39] Cat 14:344 yds | 0 | 504 | 0 | 848 | 344
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 39 | 154339 | A2639550 | COT22202999 | Crewe DF Through Line | 11 | 2100 | LEC5 | Weekend |  | 2019-12-25 01:00 | 2019-12-27 05:00 | 2 day(s) 04:00 Hrs | CORE: 1 of 1: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 530yds | 157 | 1450 | 158 | 220 | 487
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 40 | 154339 | A16610 | 22703118 | Norton Crossing | 7 | 2100 | CGJ2 | Weekend |  | 2019-12-28 22:30 | 2019-12-30 05:00 | 1 day(s) 06:30 Hrs | CORE: 1 of 1: Norton Crossing - Reballast (Trax) - CAT07 - 160yds | 177 | 800 | 177 | 960 | 160
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 40 | 154343 | A291570 | 32301119 | Shields Road | 14 | 2100 | AYR1 | Weekend |  | 2019-12-29 00:01 | 2019-12-30 09:01 | 1 day(s) 09:00 Hrs | CORE: Shields Road [Week 40] Cat 14:175 yds | 0 | 1033 | 0 | 1208 | 175
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 40 | 154341 | A313330 | 23100419 | COT Linslade & Leighton Buzzard | 14 | 1100 | LEC1 | Weekend |  | 2019-12-29 01:00 | 2020-01-02 05:00 | 4 day(s) 04:00 Hrs | CORE: 2 of 3 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 650yds | 40 | 660 | 40 | 1310 | 650
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 40 | 154341 | A370530 | 24102719 | COT Wembley Stadium Up | 14 | 1100 | NAJ1 | Weekend | W2019/WIP | 2019-12-29 01:00 | 2020-01-02 05:00 | 4 day(s) 04:00 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 860yds | 4 | 1620 | 5 | 720 | 860 |  | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 40 | 154341 | A392500 | 23100419 | COT Linslade & Leighton Buzzard | 11 | 1100 | LEC1 | Weekend |  | 2019-12-29 01:00 | 2020-01-02 05:00 | 4 day(s) 04:00 Hrs | CORE: 3 of 3 Rerail, Resleeper, Reballast - Cat11 - 370yds | 40 | 1280 | 40 | 1650 | 370
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 41 | 154929 | A931670 | 41419919 | Hassingham Down | 2 | 2100 | NOL | Weekend | W2019/0000000 | 2020-01-04 01:00 | 2020-01-06 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/4 Rerail - Both Rails Cat:02 | 7 | 1482 | 7 | 1484 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 41 | 154929 | G4T392100 | 41419919 | Hassingham Down | 4 | 2100 | NOL | Weekend | W2019/0000000 | 2020-01-04 01:00 | 2020-01-06 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/4 Steel Sleeper, Relay, Rerail - Cat:04 | 7 | 1484 | 8 | 454 | 730
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 41 | 154341 | A321650 | 23500419 | COT Hunsbury Hill Tunnel | 12 | 1100 | HNR | Weekend | W2019/WIP | 2020-01-04 01:40 | 2020-01-05 05:00 | 1 day(s) 03:20 Hrs | CORE: 1 of 1 Reballast, Formation - Trax - Cat12 - 215yds | 63 | 1550 | 64 | 5 | 215
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 41 | 158412 | A2455640 | 23512299 | COT Hunsbury Hill Drainage | 15aa | 1100 | HNR | Weekend |  | 2020-01-04 22:00 | 2020-01-05 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT Hunsbury Hill Drainage - CAT15aa - 215yds | 63 | 1550 | 64 | 5 | 215
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 41 | 154343 | A251410 | 32100218 | Elderslie South | 14 | 1100 | AYR3 | Weekend |  | 2020-01-05 00:01 | 2020-01-06 05:01 | 1 day(s) 05:00 Hrs | CORE: Elderslie South [Week 41] Cat 14:351 yds | 9 | 915 | 9 | 1266 | 351
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 41 | 154343 | A284410 | FD31500819 | Cove Bay South | 11 | 1100 | ECN5 | Weekend |  | 2020-01-05 00:01 | 2020-01-06 05:01 | 1 day(s) 05:00 Hrs | CORE: Cove Bay South [Week 41] Cat 11:448 yds | 235 | 1320 | 236 | 8 | 448
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 19/20 | 41 | 154932 | A8370 | 53310319 | Swansea Loop SWL 1100 | 11 | 1100 | SWL | Weekend | W2019/0000000 | 2020-01-05 00:01 | 2020-01-06 05:00 | 1 day(s) 04:59 Hrs | CORE: 1st ReRail, ReSleeper, ReBallast - Trax | 0 | 0 | 0 | 1056 | 1056
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 41 | 154339 | A2899550 | COT22500420 | Cheadle Hulme MCH Dn South | 12 | 2100 | MCH | Weekend |  | 2020-01-05 00:10 | 2020-01-06 05:40 | 1 day(s) 05:30 Hrs | CORE: 1 of 1: CAT12 - Reballast, Formation -Trax - 440yds | 0 | 1540 | 1 | 220 | 440
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 41 | 154934 | G4T32320 | 44600217 | Byfleet & New Haw Platform | 11 | 2200 | BML1 | Weekend |  | 2020-01-05 01:10 | 2020-01-06 04:00 | 1 day(s) 02:50 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 20 | 596 | 20 | 750 | 154
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 41 | 154934 | G4T35360 | 44600217 | Byfleet & New Haw Platform | 14 | 2200 | BML1 | Weekend |  | 2020-01-05 01:10 | 2020-01-06 04:00 | 1 day(s) 02:50 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 20 | 750 | 20 | 930 | 180
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 42 | 154343 | A285410 | 31500217 | Ironshill Dn | 11 | 2100 | ECN4 | Weekend |  | 2020-01-11 01:00 | 2020-01-12 06:00 | 1 day(s) 05:00 Hrs | CORE: Ironshill Dn [Week 42] Cat 11:484 yds | 23 | 325 | 23 | 809 | 484
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 42 | 154929 | A931680 | 41419919 | Hassingham Down | 44A | 2100 | NOL | Weekend | W2019/0000000 | 2020-01-11 01:00 | 2020-01-13 05:00 | 2 day(s) 04:00 Hrs | CORE: 2/4 Baseplate Changing Cat:44a | 8 | 1013 | 8 | 1034 | 21
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 42 | 154929 | A932530 | 41419919 | Hassingham Down | 11 | 2100 | NOL | Weekend | W2019/0000000 | 2020-01-11 01:00 | 2020-01-13 05:00 | 2 day(s) 04:00 Hrs | CORE: 2/4 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat:11 | 8 | 993 | 8 | 1013 | 20
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 42 | 154929 | G4T401040 | 41419919 | Hassingham Down | 4 | 2100 | NOL | Weekend | W2019/0000000 | 2020-01-11 01:00 | 2020-01-13 05:00 | 2 day(s) 04:00 Hrs | CORE: 2/4 Steel Sleeper, Relay, Rerail - Cat:04 | 8 | 454 | 8 | 993 | 539
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 42 | 154929 | G4T401050 | 41419919 | Hassingham Down | 2 | 2100 | NOL | Weekend | W2019/0000000 | 2020-01-11 01:00 | 2020-01-13 05:00 | 2 day(s) 04:00 Hrs | CORE: 2/4 Rerail - Both Rails Cat:02 | 8 | 1013 | 8 | 1034 | 21
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 42 | 154335 | A2458090 | 124188 | Wombwell Stn | 11 | 1100 | SHB | Weekend | W2019/0000000 | 2020-01-11 01:00 | 2020-01-11 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1: CAT 11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 260yds | 170 | 880 | 170 | 1010 | 260
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 42 | 154338 | A15630 | 121034 | Finsbury Park-1 | 11 | 2300 | ECM1 | Weekend |  | 2020-01-11 02:00 | 2020-01-13 05:00 | 2 day(s) 03:00 Hrs | CORE: Cat 11: Rerail, Resleeper, Reballast - Trax - 180yds | 2 | 336 | 2 | 516 | 180 | Addition to workbank as per c/c ref: PLS-1920-109. Moved from Wk.22 to Wk.42 as per C/C ref: PLS-1920-127 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 42 | 154338 | A16490 | 121034 | Finsbury Park-1 | 11 | 2300 | ECM1 | Weekend |  | 2020-01-11 02:00 | 2020-01-13 05:00 | 2 day(s) 03:00 Hrs | CORE: Cat 11: Rerail, Resleeper, Reballast - Trax - 437yds | 2 | 708 | 2 | 1145 | 437 | Addition to workbank as per c/c ref: PLS-1920-109. Moved from Wk.22 to Wk.42 as per C/C ref: PLS-1920-127 | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 42 | 154341 | A9460 | 23209099 | Jackson's | 14 | 1100 | LEC2 | Weekend |  | 2020-01-11 22:00 | 2020-01-12 09:00 | 0 day(s) 11:00 Hrs | CORE: 1 of 7: Jackson's - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 148yds | 122 | 1490 | 122 | 1638 | 148
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 42 | 154343 | A291590 | 32100218 | Elderslie South | 14 | 1100 | AYR3 | Weekend |  | 2020-01-12 00:01 | 2020-01-13 05:01 | 1 day(s) 05:00 Hrs | CORE: Elderslie South [Week 42] Cat 14:350 yds | 9 | 1266 | 9 | 1616 | 350
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 19/20 | 42 | 154932 | A5310 | 53310419 | Swansea Loop DN | 11 | 2100 | SWL | Weekend | W2019/0000000 | 2020-01-12 00:01 | 2020-01-13 05:00 | 1 day(s) 04:59 Hrs | CORE: 1st ReRail, ReSleeper, ReBallast - Trax | 0 | 0 | 0 | 1056 | 1056 | New UID Added 05-03-18 | APC
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 42 | 154339 | A2894350 | JTC22600116 | Brunswick - St James Tunnel | 11 | 2100 | HXS1 | Weekend |  | 2020-01-12 01:00 | 2020-01-14 07:00 | 2 day(s) 06:00 Hrs | CORE: 1 of 2: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 508yds | 0 | 1200 | 0 | 1708 | 508
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 42 | 154341 | A371570 | 24204919 | Stockingford | 12 | 1100 | NWO | Weekend |  | 2020-01-12 01:00 | 2020-01-13 05:00 | 1 day(s) 04:00 Hrs | CORE: 1 of 2 Reballast, Formation - Trax - Cat12 - 160yds | 8 | 770 | 8 | 930 | 160
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 42 | 154341 | A393750 | 24204919 | Stockingford | 14 | 1100 | NWO | Weekend |  | 2020-01-12 01:00 | 2020-01-13 05:00 | 1 day(s) 04:00 Hrs | CORE: 2 of 2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 210yds | 8 | 560 | 8 | 770 | 210
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 42 | 154934 | A1330 | 44601213df1 | Surbiton - Hampton Court Jn DMF | 14 | 2100 | BML2 | Weekend |  | 2020-01-12 01:00 | 2020-01-13 04:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast, Formation - Trax | 12 | 800 | 12 | 1025 | 225
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 42 | 154934 | A8980 | 44601213df1 | Surbiton - Hampton Court Jn DMF | 11 | 2100 | BML2 | Weekend |  | 2020-01-12 01:00 | 2020-01-13 04:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 12 | 1025 | 12 | 1167 | 142
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 42 | 154934 | G4T8370 | 44601213df1 | Surbiton - Hampton Court Jn DMF | 11 | 2100 | BML2 | Weekend |  | 2020-01-12 01:00 | 2020-01-13 04:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 12 | 725 | 12 | 800 | 75
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 43 | 154343 | A291600 | 31500217 | Ironshill Dn | 11 | 2100 | ECN4 | Weekend |  | 2020-01-18 01:00 | 2020-01-19 06:00 | 1 day(s) 05:00 Hrs | CORE: Ironshill Dn [Week 43] Cat 11:483 yds | 23 | 809 | 23 | 1292 | 483
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 43 | 154930 | A9730 | 42400119 | Westcombe Park to Charlton Up | 11 | 1100 | NKL | Weekend | W2019/000000 | 2020-01-18 01:00 | 2020-01-20 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 6 | 1540 | 7 | 148 | 368
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 43 | 154930 | G4T123150 | 42400119 | Westcombe Park to Charlton Up | 2 | 1100 | NKL | Weekend | W2019/000000 | 2020-01-18 01:00 | 2020-01-20 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 7 | 148 | 7 | 161 | 13
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 43 | 154930 | G4T123270 | 42400119 | Westcombe Park to Charlton Up | 2 | 1100 | NKL | Weekend | W2019/000000 | 2020-01-18 01:00 | 2020-01-20 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 6 | 1529 | 6 | 1540 | 11
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 43 | 154929 | A932620 | 41419919 | Hassingham Down | 11 | 2100 | NOL | Weekend | W2019/0000000 | 2020-01-18 01:00 | 2020-01-20 05:00 | 2 day(s) 04:00 Hrs | CORE: 3/4 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat:11 | 8 | 1034 | 8 | 1054 | 20
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 43 | 154929 | G4T401060 | 41419919 | Hassingham Down | 4 | 2100 | NOL | Weekend | W2019/0000000 | 2020-01-18 01:00 | 2020-01-20 05:00 | 2 day(s) 04:00 Hrs | CORE: 3/4 Steel Sleeper, Relay, Rerail - Cat:04 | 8 | 1054 | 9 | 114 | 820
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 43 | 154341 | A392800 | 23100819B | COT Loughton-1 | 14 | 1200 | LEC1 | Weekend |  | 2020-01-18 20:00 | 2020-01-19 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 168yds | 48 | 1744 | 49 | 152 | 168
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 43 | 154341 | A397080 | 23209099 | Jackson's | 14 | 1100 | LEC2 | Weekend |  | 2020-01-18 22:00 | 2020-01-19 09:00 | 0 day(s) 11:00 Hrs | CORE: 2 of 7: Jackson's - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 122 | 1638 | 123 | 25 | 147
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 43 | 158412 | A2463960 | 24108199 | COT Sudbury & Harrow Road | 15aa | 1100 | NAJ1 | Weekend |  | 2020-01-18 22:00 | 2020-01-19 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT Sudbury & Harrow Road - CAT15aa - 440yds | 3 | 880 | 3 | 1320 | 440
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 43 | 154343 | A252410 | 32100221 | Midton Burn | 11 | 2100 | AYR3 | Weekend |  | 2020-01-19 00:01 | 2020-01-20 05:01 | 1 day(s) 05:00 Hrs | CORE: Midton Burn [Week 43] Cat 11:536 yds | 11 | 1638 | 12 | 414 | 536
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 19/20 | 43 | 154932 | A2190 | 53310519 | Landore | 11 | 1100 | SWM2 | Weekend | W2019/0000000 | 2020-01-19 00:01 | 2020-01-20 05:00 | 1 day(s) 04:59 Hrs | CORE: 1st ReRail, ReSleeper, ReBallast - Trax | 214 | 1320 | 214 | 1540 | 220
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 43 | 154339 | A2903670 | JTC22600116 | Brunswick - St James Tunnel | 11 | 2100 | HXS1 | Weekend |  | 2020-01-19 01:00 | 2020-01-21 07:00 | 2 day(s) 06:00 Hrs | CORE: 2 of 2: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 509yds | 0 | 1708 | 1 | 457 | 509
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 43 | 154934 | A1320 | 44601213df1 | Surbiton - Hampton Court Jn DMF | 11 | 2100 | BML2 | Weekend |  | 2020-01-19 01:00 | 2020-01-20 04:00 | 1 day(s) 03:00 Hrs | CORE: 2/2 Rerail, Resleeper, Reballast - Trax | 12 | 1167 | 12 | 1342 | 175
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 43 | 154934 | G4T29200 | 44600515 | Surbiton - Hampton Court Jn | 11 | 2100 | BML1 | Weekend |  | 2020-01-19 01:00 | 2020-01-20 04:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 12 | 1342 | 12 | 1608 | 266
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 44 | 154343 | A291610 | 31500217 | Ironshill Dn | 11 | 2100 | ECN4 | Weekend |  | 2020-01-25 01:00 | 2020-01-26 06:00 | 1 day(s) 05:00 Hrs | CORE: Ironshill Dn [Week 44] Cat 11:438 yds | 23 | 1292 | 23 | 1730 | 438
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 44 | 154930 | G4T123160 | 42400119 | Westcombe Park to Charlton Up | 11 | 1100 | NKL | Weekend | W2019/000000 | 2020-01-25 01:00 | 2020-01-27 05:00 | 2 day(s) 04:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 7 | 161 | 7 | 678 | 517
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 44 | 154929 | G4T392110 | 41419919 | Hassingham Down | 4 | 2100 | NOL | Weekend | W2019/0000000 | 2020-01-25 01:00 | 2020-01-27 05:00 | 2 day(s) 04:00 Hrs | CORE: 4/4 Steel Sleeper, Relay, Rerail - Cat:04 | 9 | 114 | 9 | 935 | 821
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 44 | 154934 | G4T337800 | 44100610df2 | Motspur Park to Motspur Park Jcn | 11 | 1100 | RPE | Weekend |  | 2020-01-25 01:00 | 2020-01-27 04:00 | 2 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail, Trax. Cat11 | 9 | 1104 | 10 | 236 | 892 | Updated Start/End miles yardage | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 44 | 154341 | A35220 | 23100114s | Bletchley Station | 12 | 1100 | LEC1 | Weekend |  | 2020-01-25 20:00 | 2020-01-27 06:00 | 1 day(s) 10:00 Hrs | CORE: 1 of 1: Bletchley Station - Reballast, Formaion -Trax - CAT12 - 398yds | 46 | 940 | 46 | 1338 | 398
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 44 | 154338 | A5410 | 121155 | Letchworth Dn | 11 | 2100 | SBR | Weekend |  | 2020-01-25 23:00 | 2020-01-27 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11: Reballast, Resleeper, Rerail - Trax - 391yds | 34 | 936 | 34 | 1327 | 391 | Volume amended as per C/C ref:- PLS-1920-119
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 44 | 154343 | A291620 | 32100221 | Midton Burn | 11 | 2100 | AYR3 | Weekend |  | 2020-01-26 00:01 | 2020-01-27 05:01 | 1 day(s) 05:00 Hrs | CORE: Midton Burn [Week 44] Cat 11:536 yds | 12 | 414 | 12 | 950 | 536
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 44 | 154339 | A2497070 | 22500215 | Cheadle Hulme MCH Dn | 12 | 2100 | MCH | Weekend |  | 2020-01-26 00:10 | 2020-01-27 05:40 | 1 day(s) 05:30 Hrs | CORE: 1 of 1: Cat12 - Formation, Reballast - Traxcavate - 360yds | 0 | 960 | 0 | 1320 | 360
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 45 | 154931 | G4T112810 | 43300918df1 | Littlehaven | 14 | 2100 | TBH1 | Weekend | W2019/000000 | 2020-02-01 01:00 | 2020-02-03 05:00 | 2 day(s) 04:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 36 | 880 | 37 | 0 | 880
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 45 | 154931 | G4T169430 | 43300918df1 | Littlehaven | 2 | 2100 | TBH1 | Weekend | W2019/000000 | 2020-02-01 01:00 | 2020-02-03 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 36 | 865 | 36 | 880 | 15
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 45 | 154931 | G4T169440 | 43300918df1 | Littlehaven | 2 | 2100 | TBH1 | Weekend | W2019/000000 | 2020-02-01 01:00 | 2020-02-03 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 37 | 0 | 37 | 15 | 15
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 45 | 154341 | A398260 | 23502019 | RCF Northampton Station | 1 | 2100 | HNR | Weekend |  | 2020-02-01 01:00 | 2020-02-01 17:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Rerail - One Rail Only - CAT01 - 216yds | 65 | 1212 | 65 | 1428 | 216
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 45 | 154335 | A2464090 | 136063 13 | Micklefield | 11 | 2100 | HUL4 | Weekend | W2019/0000000 | 2020-02-01 01:00 | 2020-02-02 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 552yds (Not in PPS) | 10 | 1408 | 11 | 200 | 552 | (Not in PPS)
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 45 | 154341 | A26970 | 23300417 | Northchurch Tunnel | 14 | 1100 | LEC1 | Weekend |  | 2020-02-01 20:00 | 2020-02-02 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: Northchurch Tunnel - Formation, Reballast, Resleeper, Rerail - Trax - CAT14- 136yds | 29 | 432 | 29 | 568 | 136
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 45 | 154146 | A27400 | 51150111 | Acton PL Up Poplar (MDR) | 7 | 1100 | AWL | Weekend | W2019/0000000 | 2020-02-01 23:00 | 2020-02-02 15:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW Reballast-Trax | 0 | 306 | 0 | 374 | 68
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 45 | 154338 | A12410 | 122100 | Offord | 14 | 1200 | ECM1 | Weekend |  | 2020-02-01 23:00 | 2020-02-03 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 14: Rerail, Resleeper, Reballast, Formation - Trax - 240yds | 55 | 1400 | 55 | 1640 | 240 | Volume amended as per agreed c/c ref: PLS-1920-104 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 45 | 154343 | A286410 | 31500117 | Letham Mill | 11 | 2100 | ECN4 | Weekend |  | 2020-02-02 00:01 | 2020-02-03 05:01 | 1 day(s) 05:00 Hrs | CORE: Letham Mill [Week 45] Cat 11:497 yds | 18 | 1132 | 18 | 1629 | 497
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 45 | 154343 | A291630 | 32100221 | Midton Burn | 11 | 2100 | AYR3 | Weekend |  | 2020-02-02 00:01 | 2020-02-03 05:01 | 1 day(s) 05:00 Hrs | CORE: Midton Burn [Week 45] Cat 11:536 yds | 12 | 950 | 12 | 1486 | 536
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 19/20 | 45 | 154932 | A6330 | 53320220 | Swansea Platform 2 | 11 | 3602 | SWA | Weekend | W2019/0000000 | 2020-02-02 00:01 | 2020-02-03 05:00 | 1 day(s) 04:59 Hrs | CORE: 1st ReRail, ReSleeper, ReBallast - Trax | 215 | 1532 | 216 | 140 | 368
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 45 | 154341 | A41400 | 23501699 | COT Northampton No 1 | 11 | 2100 | HNR | Weekend |  | 2020-02-02 02:10 | 2020-02-03 05:00 | 1 day(s) 02:50 Hrs | CORE: 1 of 1: Northampton No 1 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - CAT11 - 120yds | 65 | 1092 | 65 | 1212 | 120
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 46 | 154931 | G4T169590 | 43300718df1 | Faygate | 2 | 2100 | TBH1 | Weekend | W2019/000000 | 2020-02-08 01:00 | 2020-02-10 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 34 | 204 | 34 | 220 | 16 | SUS-1920-24 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 46 | 154931 | G4T169600 | 43300718df1 | Faygate | 2 | 2100 | TBH1 | Weekend | W2019/000000 | 2020-02-08 01:00 | 2020-02-10 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 34 | 684 | 34 | 700 | 16 | SUS-1920-24 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 46 | 154931 | G4T5990 | 43300718df1 | Faygate | 14 | 2100 | TBH1 | Weekend | W2019/000000 | 2020-02-08 01:00 | 2020-02-10 05:00 | 2 day(s) 04:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 34 | 220 | 34 | 684 | 464 | SUS-1920-24 | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 46 | 154934 | W12510 | 44500118 | Dean North | 14 | 2100 | RTJ2 | Weekend |  | 2020-02-08 01:00 | 2020-02-10 04:00 | 2 day(s) 03:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax Cat 14 | 89 | 198 | 89 | 858 | 660
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 46 | 154934 | W13370 | 44500118 | Dean North | 15a | 2100 | RTJ2 | Weekend |  | 2020-02-08 01:00 | 2020-02-10 04:00 | 2 day(s) 03:00 Hrs | CORE: Install new cess drainage Cat 15a | 89 | 300 | 89 | 397 | 97
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 46 | 154335 | A2471090 | 133044SF | Danby | 2 | 3100 | MBW2 | Weekend | W2019/0000000 | 2020-02-08 01:00 | 2020-02-09 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT02: Rerail - Both Rails : 8yds (Not in PPS) | 20 | 762 | 20 | 770 | 8 | (Not in PPS) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 46 | 154335 | A2473040 | 133044SF | Danby | 4 | 3100 | MBW2 | Weekend | W2019/0000000 | 2020-02-08 01:00 | 2020-02-09 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT04: Steel Sleeper Relay and Rerail : 550yds (Not in PPS) | 20 | 770 | 20 | 1320 | 550 | (Not in PPS) | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 46 | 154341 | A398160 | 23300417 | Northchurch Tunnel | 14 | 1100 | LEC1 | Weekend |  | 2020-02-08 20:00 | 2020-02-09 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: Northchurch Tunnel - Formation, Reballast, Resleeper, Rerail - Trax - CAT14- 136yds | 29 | 568 | 29 | 704 | 136
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 46 | 158412 | A2466040 | 24102719 | COT Wembley Stadium Up | 15aa | 1100 | NAJ1 | Weekend |  | 2020-02-08 22:00 | 2020-02-09 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT Wembley Stadium Up - CAT15aa - 650yds | 5 | 70 | 5 | 720 | 650
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 46 | 154338 | A15470 | 122100 | Offord | 11 | 1200 | ECM1 | Weekend |  | 2020-02-08 23:00 | 2020-02-10 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 182yds | 55 | 1218 | 55 | 1400 | 182 | Volume amended as per agreed c/c ref: PLS-1920-104 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 46 | 154338 | A15520 | 122100 | Offord | 11 | 1200 | ECM1 | Weekend |  | 2020-02-08 23:00 | 2020-02-10 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 95yds | 55 | 1640 | 55 | 1735 | 95 | Volume amended as per agreed c/c ref: PLS-1920-104 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 46 | 154338 | A15530 | 121158 | Letchworth Up | 2 | 1100 | SBR | Weekend |  | 2020-02-08 23:00 | 2020-02-10 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 02: Rerail - Both Rails - 8yds | 34 | 1349 | 34 | 1357 | 8 | Volume amended to Cat 11 - 603yds & Cat 2 - 8yds vice Cat 11 - 640yds (C/C ref: PLS-1920-118). Moved from Wk's 42 & 43 to Wk's 46 & 47 - C/C ref: PLS-1920-125 | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 46 | 154338 | A8410 | 121158 | Letchworth Up | 11 | 1100 | SBR | Weekend |  | 2020-02-08 23:00 | 2020-02-10 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 302yds | 34 | 1357 | 34 | 1659 | 302 | Volume amended to Cat 11 - 603yds & Cat 2 - 8yds vice Cat 11 - 640yds (C/C ref: PLS-1920-118). Moved from Wk's 42 & 43 to Wk's 46 & 47 - C/C ref: PLS-1920-125 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 46 | 154343 | A2863940 | 32100317 | Dalry A/B 1718 Falldown | 14 | 1100 | AYR3 | Weekend |  | 2020-02-09 00:01 | 2020-02-10 05:01 | 1 day(s) 05:00 Hrs | CORE: Dalry A/B Falldown [Week 46] Cat 14:260 yds | 21 | 1183 | 21 | 1443 | 260 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 46 | 154343 | A291660 | 31500117 | Letham Mill | 11 | 2100 | ECN4 | Weekend |  | 2020-02-09 00:01 | 2020-02-10 05:01 | 1 day(s) 05:00 Hrs | CORE: Letham Mill [Week 46] Cat 11:593 yds | 18 | 1629 | 19 | 462 | 593
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 46 | 154339 | A2848590 | TSR22401315 | Swinton | 11 | 1100 | WBS1 | Weekend |  | 2020-02-09 01:00 | 2020-02-10 05:00 | 1 day(s) 04:00 Hrs | CORE: 1 of 2: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 225yds | 4 | 1670 | 5 | 135 | 225 | CC Ref - 1920-042
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 46 | 154341 | A347650 | 23400519 | COT Harlsden Station | 14 | 2100 | CWJ | Weekend |  | 2020-02-09 01:10 | 2020-02-10 05:00 | 1 day(s) 03:50 Hrs | CORE: 1 of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) - Cat14 - 410yds | 5 | 1610 | 6 | 265 | 415
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 47 | 154341 | A394920 | 23100920 | Potential TSR Bletchley North | 2 | 2100 | LEC1 | Weekend |  | 2020-02-15 01:00 | 2020-02-15 17:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Rerail - Both Rails - CAT02 - 362yds | 46 | 1338 | 46 | 1700 | 362
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 47 | 154934 | G4T3170 | 44650217 | Pirbright Jn to Farnborough | 11 | 1100 | BML1 | Weekend |  | 2020-02-15 01:00 | 2020-02-17 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 31 | 276 | 31 | 1382 | 1106
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 47 | 154335 | A2459090 | 132001SF | Thirsk | 14 | 1200 | ECM5 | Weekend | W2019/0000000 | 2020-02-15 01:00 | 2020-02-15 17:00 | 0 day(s) 16:00 Hrs | CORE: CAT14: Formation, Reballast, Resleeper - Rerail : Trax: 240yds (Not in PPS) | 25 | 400 | 25 | 640 | 240 | PLN-1920-011 (Not in PPS) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 47 | 154335 | A2473050 | 133044SF | Danby | 11 | 3100 | MBW2 | Weekend | W2019/0000000 | 2020-02-15 01:00 | 2020-02-16 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT11:Rerail, Resleeper, Reballast - Trax: 440yds (Not in PPS) | 20 | 1320 | 21 | 0 | 440 | (Not in PPS) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 47 | 154335 | A2473060 | 133044SF | Danby | 4 | 3100 | MBW2 | Weekend | W2019/0000000 | 2020-02-15 01:00 | 2020-02-16 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT04: Steel Sleeper Relay and Rerail : 847yds (Not in PPS) | 21 | 0 | 21 | 847 | 847 | (Not in PPS) | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 47 | 158412 | A2468120 | 24308999 | Station Road Bradbury | 15aa | 1100 | RRN2 | Weekend |  | 2020-02-15 22:00 | 2020-02-16 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Station Road Bradbury - CAT15aa - 440yds | 9 | 850 | 9 | 1290 | 440
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 47 | 154146 | A32600 | 51240619 | Taplow | 2 | 1200 | MLN1 | Weekend |  | 2020-02-15 23:00 | 2020-02-16 15:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW Rerail, Both Rails | 22 | 689 | 22 | 943 | 254
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 47 | 154146 | WES42130 | 51110110 | Paddington Platform 10 | 2 | 3610 | MLN1 | Weekend | W2019/0000000 | 2020-02-15 23:00 | 2020-02-17 02:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 0 | 165 | 0 | 191 | 26
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 47 | 154146 | WES57370 | 51110110 | Paddington Platform 10 | 14 | 3610 | MLN1 | Weekend | W2019/0000000 | 2020-02-15 23:00 | 2020-02-17 02:00 | 1 day(s) 03:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 0 | 191 | 0 | 464 | 273
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 47 | 154338 | A15420 | 121158 | Letchworth Up | 11 | 1100 | SBR | Weekend |  | 2020-02-15 23:00 | 2020-02-17 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 301yds | 34 | 1659 | 35 | 200 | 301 | Volume amended to Cat 11 - 603yds & Cat 2 - 8yds vice Cat 11 - 640yds (C/C ref: PLS-1920-118). Moved from Wk's 42 & 43 to Wk's 46 & 47 - C/C ref: PLS-1920-125 | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 47 | 154343 | A254410 | 32101019 | Dalry Station Up | 11 | 1100 | AYR3 | Weekend |  | 2020-02-16 00:01 | 2020-02-17 05:01 | 1 day(s) 05:00 Hrs | CORE: Dalry Station Up [Week 47] Cat 11:635 yds | 21 | 1594 | 22 | 649 | 815 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 47 | 154343 | A287410 | 31300218 | Coaltown | 9 | 1100 | ECN2 | Weekend |  | 2020-02-16 00:01 | 2020-02-17 05:01 | 1 day(s) 05:00 Hrs | CORE: Coaltown [Week 47] Cat 09:367 yds | 31 | 1440 | 32 | 47 | 367
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 47 | 154339 | A2903780 | TSR22401315 | Swinton | 11 | 1100 | WBS1 | Weekend |  | 2020-02-16 01:00 | 2020-02-17 05:00 | 1 day(s) 04:00 Hrs | CORE: 2 of 2: Cat 11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 225yds | 5 | 135 | 5 | 360 | 225 | CC Ref - 1920-042
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 48 | 154146 | A34680 | 5122019 | Tilehurst Re Rail SF | 2 | 2200 | MLN1 | Weekend | W2019/0000000 | 2020-02-22 01:00 | 2020-02-24 07:00 | 2 day(s) 06:00 Hrs | CORE: 1st CW Rerail Both Rails | 38 | 775 | 39 | 822 | 1807
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 48 | 154934 | A9120 | WM1005df3 | Raynes Park | 11 | 1200 | BML1 | Weekend |  | 2020-02-22 01:00 | 2020-02-24 04:00 | 2 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail, Trax. Part 1 of 2 | 8 | 1448 | 8 | 1546 | 98
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 48 | 154934 | A9390 | WM1005df3 | Raynes Park | 11 | 1200 | BML1 | Weekend |  | 2020-02-22 01:00 | 2020-02-24 04:00 | 2 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail, , Trax. Part 2 of 2 | 8 | 821 | 8 | 920 | 99
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 48 | 154934 | G4T31280 | WM1005df3 | Raynes Park | 11 | 1200 | BML1 | Weekend |  | 2020-02-22 01:00 | 2020-02-24 04:00 | 2 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail, Trax. Part 1 of 2 | 8 | 1222 | 8 | 1434 | 212
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 48 | 154934 | G4T31290 | WM1005df3 | Raynes Park | 14 | 1200 | BML1 | Weekend |  | 2020-02-22 01:00 | 2020-02-24 04:00 | 2 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail, Formation, Trax. Part 2 of 2 | 8 | 920 | 8 | 1222 | 302
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 48 | 154934 | G4T32140 | WM1005df3 | Raynes Park | 2 | 1200 | BML1 | Weekend |  | 2020-02-22 01:00 | 2020-02-24 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 CORE: Rerail - both rails. | 8 | 1434 | 8 | 1448 | 14
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 48 | 154335 | A2473070 | 133044SF | Danby | 43A | 3100 | MBW2 | Weekend | W2019/0000000 | 2020-02-22 01:00 | 2020-02-23 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT43: Crop & weld-up rails : 58yds (Not in PPS) | 21 | 847 | 21 | 905 | 58 | (Not in PPS) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 48 | 154335 | A2473080 | 133044SF | Danby | 4 | 3100 | MBW2 | Weekend | W2019/0000000 | 2020-02-22 01:00 | 2020-02-23 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT04: Steel Sleeper Relay and Rerail : 530yds (Not in PPS) | 21 | 905 | 21 | 1435 | 530 | (Not in PPS) | APC
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 48 | 154335 | A2484730 | 132001SF | Thirsk | 14 | 1200 | ECM5 | Weekend | W2019/0000000 | 2020-02-22 01:00 | 2020-02-22 17:00 | 0 day(s) 16:00 Hrs | CORE: CAT14: Formation, Reballast, Resleeper - Rerail : Trax: 240yds (Not in PPS) | 25 | 640 | 25 | 880 | 240 | PLN-1920-011 (Not in PPS) | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 48 | 154341 | A393730 | 23100819B | COT Loughton-1 | 14 | 1200 | LEC1 | Weekend |  | 2020-02-22 20:00 | 2020-02-23 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 168yds | 49 | 152 | 49 | 320 | 168
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 48 | 154341 | A397090 | 23209099 | Jackson's | 14 | 1100 | LEC2 | Weekend |  | 2020-02-22 22:00 | 2020-02-23 09:00 | 0 day(s) 11:00 Hrs | CORE: 3 of 7: Jackson's - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 123 | 25 | 123 | 172 | 147
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 48 | 158412 | A2467080 | 23108499 | COT Bletchley Park | 15aa | 1200 | LEC1 | Weekend |  | 2020-02-22 22:00 | 2020-02-23 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT Bletchley Park - CAT15aa - 140yds | 46 | 1650 | 47 | 30 | 140
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 48 | 154338 | A14320 | 121153 | Alexandra Palace Dn Slow | 11 | 2200 | ECM1 | Weekend |  | 2020-02-22 23:00 | 2020-02-24 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 260yds | 5 | 893 | 5 | 1153 | 260 | CC PLS-1920-035 received 17/05/2017 - Mileages amended from 5m858y-5m1672y to 5m885y-5m893y (from 814Ly to 8Ly) and ROW code changed from CAT 11 to CAT 02. Moved from Wk's 47,48 & 49 to Wk's 48, 49 & 50 as per C/C ref: PLS-1920-126
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 48 | 154338 | A3410 | 121153 | Alexandra Palace Dn Slow | 11 | 2200 | ECM1 | Weekend |  | 2020-02-22 23:00 | 2020-02-24 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 02: Rerail - Both Rails - 8yds | 5 | 885 | 5 | 893 | 8 | CC PLS-1920-035 received 17/05/2017 - Mileages amended from 5m858y-5m1672y to 5m885y-5m893y (from 814Ly to 8Ly) and ROW code changed from CAT 11 to CAT 02. Moved from Wk's 47,48 & 49 to Wk's 48, 49 & 50 as per C/C ref: PLS-1920-126
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 48 | 154343 | A2861730 | 32101019 | Dalry Station Up | 11 | 1100 | AYR3 | Weekend |  | 2020-02-23 00:01 | 2020-02-24 05:01 | 1 day(s) 05:00 Hrs | CORE: Dalry Station Up [Week 48] Cat 11:212 yds | 22 | 918 | 22 | 1130 | 212 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 48 | 154343 | A291670 | 32101019 | Dalry Station Up | 14 | 1100 | AYR3 | Weekend |  | 2020-02-23 00:01 | 2020-02-24 05:01 | 1 day(s) 05:00 Hrs | CORE: Dalry Station Up [Week 48] Cat 14:269 yds | 22 | 649 | 22 | 918 | 269 |  | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 48 | 154343 | A291680 | 31300218 | Coaltown | 11 | 1100 | ECN2 | Weekend |  | 2020-02-23 00:01 | 2020-02-24 05:01 | 1 day(s) 05:00 Hrs | CORE: Coaltown [Week 48] Cat 11:572 yds | 32 | 47 | 32 | 619 | 572
N/A | Plain Line | TRACK.PL | London North West | Carillion Rail | Preston | 19/20 | 48 | 154339 | A2846510 | COT22400113 | Windsor Bridge | 14 | 3100 | MVE1 | Weekend |  | 2020-02-23 01:00 | 2020-02-24 05:00 | 1 day(s) 04:00 Hrs | CORE: 1 of 1: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 153yds | 1 | 869 | 1 | 1022 | 153
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 49 | 154335 | A2473090 | 133044SF | Danby | 2 | 3100 | MBW2 | Weekend | W2019/0000000 | 2020-02-29 01:00 | 2020-03-01 09:00 | 1 day(s) 08:00 Hrs | CORE: CAT02: Rerail - Both Rails : 28yds (Not in PPS) | 21 | 1435 | 21 | 1463 | 28 | (Not in PPS) | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 49 | 154341 | A393740 | 23100819B | COT Loughton-1 | 14 | 1200 | LEC1 | Weekend |  | 2020-02-29 20:00 | 2020-03-01 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 169yds | 49 | 320 | 49 | 489 | 169
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 49 | 154341 | A397100 | 23209099 | Jackson's | 14 | 1100 | LEC2 | Weekend |  | 2020-02-29 22:00 | 2020-03-01 09:00 | 0 day(s) 11:00 Hrs | CORE: 4 of 7: Jackson's - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 123 | 172 | 123 | 319 | 147
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 49 | 154146 | A20850 | 51300119 | Swindon East up Reception | 11 | 1300 | MLN1 | Weekend | W2019/0000000 | 2020-02-29 23:00 | 2020-03-02 02:00 | 1 day(s) 03:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 76 | 704 | 76 | 1155 | 451
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 49 | 154146 | A9410 | 51140919 | Hayes & Harlington | 2 | 1100 | MLN1 | Weekend | W2019/0000000 | 2020-02-29 23:00 | 2020-03-01 15:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 - DR 0130 Sun - 0730 Sun | 10 | 1232 | 10 | 1562 | 330
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 49 | 154338 | A15480 | 121153 | Alexandra Palace Dn Slow | 11 | 2200 | ECM1 | Weekend |  | 2020-02-29 23:00 | 2020-03-02 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 260yds | 5 | 1153 | 5 | 1413 | 260 | CC PLS-1920-035 received 17/05/2017 - Mileages amended from 5m858y-5m1672y to 5m885y-5m893y (from 814Ly to 8Ly) and ROW code changed from CAT 11 to CAT 02. Moved from Wk's 47,48 & 49 to Wk's 48, 49 & 50 as per C/C ref: PLS-1920-126
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 49 | 154343 | A2863840 | 32100220 | Kilwinning Platform 3 | 14 | 1100 | AYR4 | Weekend |  | 2020-03-01 00:01 | 2020-03-02 05:01 | 1 day(s) 05:00 Hrs | CORE: Kilwinning Platform 3 [Week 49] Cat 14:325 yds | 25 | 1661 | 26 | 226 | 325
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 49 | 154343 | A291710 | 31100119 | Almond Viaduct | 11 | 1100 | ECN2 | Weekend |  | 2020-03-01 00:01 | 2020-03-02 05:01 | 1 day(s) 05:00 Hrs | CORE: Almond Viaduct EGIP MRC [Week 49] Cat 11:452 yds | 6 | 1547 | 7 | 239 | 452
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 50 | 154930 | A10770 | 42400219 | Westcombe Park to Charlton Dn | 11 | 2100 | NKL | Weekend | W2019/000000 | 2020-03-07 01:00 | 2020-03-09 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 6 | 1534 | 7 | 146 | 372
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 50 | 154930 | A936970 | 42100416Ddf3 | Allotment Drainage Down (19/20) | 15b | 2100 | SBJ |  |  | 2020-03-07 01:00 | 2020-03-07 17:00 | 0 day(s) 16:00 Hrs | CORE: Drain (Unassociated With Track Renewal) Cat:15b | 42 | 892 | 42 | 1100 | 208
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 50 | 154930 | G4T123140 | 42400219 | Westcombe Park to Charlton Dn | 2 | 2100 | NKL | Weekend | W2019/000000 | 2020-03-07 01:00 | 2020-03-09 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 7 | 146 | 7 | 158 | 12
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 50 | 154930 | G4T123280 | 42400219 | Westcombe Park to Charlton Dn | 2 | 2100 | NKL | Weekend | W2019/000000 | 2020-03-07 01:00 | 2020-03-09 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 6 | 1523 | 6 | 1534 | 11
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 50 | 154934 | A1370 | 44600619 | Witley stn Down | 14 | 2100 | WPH1 | Weekend |  | 2020-03-07 01:00 | 2020-03-09 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) | 38 | 600 | 38 | 946 | 346
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 50 | 154934 | G4T26050 | 44600619 | Witley stn Down | 11 | 2100 | WPH1 | Weekend |  | 2020-03-07 01:00 | 2020-03-09 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 37 | 1324 | 38 | 600 | 1036
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 50 | 154335 | A2455090 | 125231 | Grimsby Marsh West | 11 | 2100 | MAC3 | Weekend | W2019/0000000 | 2020-03-07 01:00 | 2020-03-08 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 510yds (Not in PPS) | 107 | 389 | 107 | 899 | 510 | PLN-1920-045 (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 50 | 154335 | A2489240 | 132028 | Sessay | 11 | 2100 | ECM5 | Weekend | W2019/0000000 | 2020-03-07 01:00 | 2020-03-08 01:00 | 1 day(s) 00:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 155yds | 18 | 866 | 18 | 1021 | 155 | PLN-1920-098 | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 50 | 154146 | A25010 | 51100219 | Westbourne Park | 7 | 3101 | MLN1 | Weekend | W2019/0000000 | 2020-03-07 23:00 | 2020-03-09 02:00 | 1 day(s) 03:00 Hrs | CORE: 1/2 Reballast - Traxcavation Cat: 07 | 1 | 110 | 1 | 330 | 220
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 50 | 154146 | A35830 | 51300119 | Swindon East up Reception | 11 | 1300 | MLN1 | Weekend | W2019/0000000 | 2020-03-07 23:00 | 2020-03-09 02:00 | 1 day(s) 03:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 76 | 1155 | 76 | 1606 | 451
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 50 | 154146 | A35840 | 51100219 | Westbourne Park | 7 | 3101 | MLN1 | Weekend | W2019/0000000 | 2020-03-07 23:00 | 2020-03-09 02:00 | 1 day(s) 03:00 Hrs | CORE: 2/2 Reballast - Traxcavation Cat: 07 | 1 | 330 | 1 | 550 | 220
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 50 | 154338 | A15490 | 121153 | Alexandra Palace Dn Slow | 11 | 2200 | ECM1 | Weekend |  | 2020-03-07 23:00 | 2020-03-09 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 259yds | 5 | 1413 | 5 | 1672 | 259 | CC PLS-1920-035 received 17/05/2017 - Mileages amended from 5m858y-5m1672y to 5m885y-5m893y (from 814Ly to 8Ly) and ROW code changed from CAT 11 to CAT 02. Moved from Wk's 47,48 & 49 to Wk's 48, 49 & 50 as per C/C ref: PLS-1920-126
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 50 | 154343 | A255410 | 32100220a | Kilwinning Platform 4 | 14 | 1100 | AYR4 | Weekend |  | 2020-03-08 00:01 | 2020-03-08 16:01 | 0 day(s) 16:00 Hrs | CORE: Kilwinning Platform 4 [Week 50] Cat 14:427 yds | 25 | 1596 | 26 | 263 | 427
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 50 | 154343 | A291730 | 31100119 | Almond Viaduct | 11 | 1100 | ECN2 | Weekend |  | 2020-03-08 00:01 | 2020-03-09 05:01 | 1 day(s) 05:00 Hrs | CORE: Almond Viaduct EGIP MRC [Week 50] Cat 11:452 yds | 7 | 239 | 7 | 691 | 452
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 51 | 154930 | G4T123130 | 42400219 | Westcombe Park to Charlton Dn | 11 | 2100 | NKL | Weekend | W2019/000000 | 2020-03-14 01:00 | 2020-03-16 05:00 | 2 day(s) 04:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 7 | 158 | 7 | 713 | 555
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 51 | 154934 | G4T27090 | 44401115Bdf2 | Dog Kennel | 11 | 1100 | WPH1 | Weekend |  | 2020-03-14 01:00 | 2020-03-16 04:00 | 2 day(s) 03:00 Hrs | CORE: Reballast (250mm), Resleeper, Rerail, Trax Cat 11 | 40 | 1474 | 41 | 550 | 836
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 51 | 154335 | A2484710 | 125231 | Grimsby Marsh West | 11 | 2100 | MAC3 | Weekend | W2019/0000000 | 2020-03-14 01:00 | 2020-03-15 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 510yds (Not in PPS) | 107 | 899 | 107 | 1409 | 510 | PLN-1920-045 (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 51 | 154335 | A2490100 | 132028 | Sessay | 11 | 2100 | ECM5 | Weekend | W2019/0000000 | 2020-03-14 01:00 | 2020-03-15 01:00 | 1 day(s) 00:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 154yds | 18 | 1021 | 18 | 1176 | 154 | PLN-1920-098 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 51 | 154930 | G2090 | 42400216sf1 | Brockley to Honour Oak Park Up | 2 | 1100 | LBW | Weekend | W2019/000000 | 2020-03-14 01:05 | 2020-03-16 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 4 | 868 | 4 | 880 | 12
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 51 | 154930 | G2100 | 42400216sf1 | Brockley to Honour Oak Park Up | 2 | 1100 | LBW | Weekend | W2019/000000 | 2020-03-14 01:05 | 2020-03-16 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 5 | 64 | 5 | 76 | 12
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 51 | 154930 | G4T55210 | 42400216sf1 | Brockley to Honour Oak Park Up | 11 | 1100 | LBW | Weekend | W2019/000000 | 2020-03-14 01:05 | 2020-03-16 04:00 | 2 day(s) 02:55 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 880 | 5 | 64 | 944
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 51 | 154929 | G4T395040 | 41600716sf1df1 | Broxbourne Up (Shortfall) | 2 | 1100 | BGK | Weekend |  | 2020-03-14 01:55 | 2020-03-16 04:00 | 2 day(s) 02:05 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 17 | 1077 | 17 | 1080 | 3
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 51 | 154929 | G4T395880 | 41600716sf1df1 | Broxbourne Up (Shortfall) | 11 | 1100 | BGK | Weekend |  | 2020-03-14 01:55 | 2020-03-16 04:00 | 2 day(s) 02:05 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat:11 | 17 | 1080 | 17 | 1355 | 275
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 51 | 154341 | A394820 | 23100819B | COT Loughton-1 | 14 | 1200 | LEC1 | Weekend |  | 2020-03-14 20:00 | 2020-03-15 12:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 4 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 169yds | 49 | 489 | 49 | 658 | 169
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 51 | 154341 | A397110 | 23209099 | Jackson's | 14 | 1100 | LEC2 | Weekend |  | 2020-03-14 22:00 | 2020-03-15 09:00 | 0 day(s) 11:00 Hrs | CORE: 5 of 7: Jackson's - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 123 | 319 | 123 | 466 | 147
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 51 | 154146 | A30520 | 51130314 | Plassers | 11 | 2100 | WEL1 | Weekend | W2019/0000000 | 2020-03-14 23:00 | 2020-03-15 15:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW Rerail, Resleeper, Reballat-Trax | 6 | 1672 | 7 | 22 | 110
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 51 | 154338 | A4410 | 121154 | Alexandra Palace Up Slow-1 | 11 | 1200 | ECM1 | Weekend |  | 2020-03-14 23:00 | 2020-03-16 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 268yds | 5 | 863 | 5 | 1131 | 268 | CC received 17/05/2017 - Mileages amended from 5m858y-5m1672y to 5m863y-5m1667y (from 814Ly to 804Ly). Job moved weeks from 50, 51 & 52 to 51, 52 & 53 as per C/C ref: PLS-1920-128
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 51 | 154343 | A256410 | FD31300116 | Inverkeithing Tunnel Down | 11 | 2100 | ECN2 | Weekend |  | 2020-03-15 00:01 | 2020-03-15 16:01 | 0 day(s) 16:00 Hrs | CORE: Inverkeithing Tunnel Down [Week 51] Cat 11:604 yds | 12 | 1039 | 12 | 1643 | 604
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 51 | 154343 | A2865970 | 32100417 | Bogside 1718 Falldown | 16 | 1100 | AYR4 | Weekend |  | 2020-03-15 00:01 | 2020-03-16 05:01 | 1 day(s) 05:00 Hrs | CORE: Bogside 1718 Falldown [Week 51] Cat 16:689 yds | 27 | 800 | 27 | 1515 | 758
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 52 | 154929 | G4T392120 | 41500119 | Bow Up Electric 1 | 11 | 1152 | LTN1 | Weekend | W2019/0000000 | 2020-03-21 00:01 | 2020-03-23 04:01 | 2 day(s) 04:00 Hrs | CORE: 2/4 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 1 | 913 | 1 | 1452 | 539 | Job moved to UND. CC ref EA-1920-44 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 52 | 154929 | G4T392130 | 41500119 | Bow Up Electric 1 | 11 | 1152 | LTN1 | Weekend | W2019/0000000 | 2020-03-21 00:01 | 2020-03-23 04:01 | 2 day(s) 04:00 Hrs | CORE: 3/4 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 1 | 1452 | 2 | 231 | 539 | Job moved to UND. CC ref EA-1920-44 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 52 | 154929 | G4T392140 | 41500119 | Bow Up Electric 1 | 11 | 1152 | LTN1 | Weekend | W2019/0000000 | 2020-03-21 00:01 | 2020-03-23 04:01 | 2 day(s) 04:00 Hrs | CORE: 4/4 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 2 | 231 | 2 | 770 | 539 | Job moved to UND. CC ref EA-1920-44 refers
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A13890 | 42500319 | Bickley Down Fast | 11 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 00:30 | 2020-03-23 04:30 | 2 day(s) 04:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 12 | 289 | 12 | 816 | 527
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A19090 | 42300219 | Birchington Dn | 11 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 00:30 | 2020-03-21 05:40 | 0 day(s) 05:10 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 69 | 1672 | 70 | 968 | 1056 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G2440 | 42500319 | Bickley Down Fast | 2 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 00:30 | 2020-03-23 04:30 | 2 day(s) 04:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 12 | 816 | 12 | 828 | 12
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G2490 | 42300219 | Birchington Dn | 2 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 00:30 | 2020-03-21 05:40 | 0 day(s) 05:10 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 69 | 1658 | 69 | 1672 | 14 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G2500 | 42300219 | Birchington Dn | 2 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 00:30 | 2020-03-21 05:40 | 0 day(s) 05:10 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 70 | 968 | 70 | 981 | 13 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A14930 | 42500419 | Farningham Road to Fawkham Jcn Up | 11 | 1100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 20 | 1535 | 22 | 392 | 2377 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A17010 | 42300819 | Whitstable Up | 14 | 1100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 59 | 220 | 59 | 1535 | 1315
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A20130 | 42300919 | Westgate to Margate Dn | 11 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 72 | 1408 | 73 | 1117 | 1469 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A21170 | 42200219 | Grove Park to Chislehurst Tnl Up Fast | 11 | 1100 | XTD | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 8 | 930 | 8 | 1311 | 381 | KENT-1920-53 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A22210 | 42200319 | Grove Park to Chislehurst Tnl Dn Fast | 11 | 2100 | XTD | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 8 | 982 | 8 | 1208 | 226 | KENT-1920-01
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A27540 | 42300619 | Dumpton Park | 11 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 78 | 380 | 78 | 800 | 420 | KENT-1920-32 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A29540 | 42200219 | Grove Park to Chislehurst Tnl Up Fast | 14 | 1100 | XTD | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax Cat:14 | 8 | 1629 | 9 | 220 | 351 | KENT-1920-53 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A29560 | 42200319 | Grove Park to Chislehurst Tnl Dn Fast | 11 | 2100 | XTD | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 8 | 1446 | 9 | 175 | 489 | KENT-1920-01
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T116950 | 42400116 | Honor Oak Park to Forest Hill Dn | 11 | 2100 | LBW | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 1408 | 5 | 828 | 1180 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123170 | 42300819 | Whitstable Up | 2 | 1100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 59 | 207 | 59 | 220 | 13
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123300 | 42200219 | Grove Park to Chislehurst Tnl Up Fast | 2 | 1100 | XTD | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 9 | 220 | 9 | 234 | 14 | KENT-1920-53 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123310 | 42300619 | Dumpton Park | 2 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 78 | 373 | 78 | 380 | 7 | KENT-1920-32 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123320 | 42300619 | Dumpton Park | 2 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 78 | 800 | 78 | 807 | 7 | KENT-1920-32 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123330 | 42300819 | Whitstable Up | 2 | 1100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 59 | 1540 | 59 | 1556 | 16
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123340 | 42300919 | Westgate to Margate Dn | 2 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 72 | 1392 | 72 | 1408 | 16 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123350 | 42300919 | Westgate to Margate Dn | 2 | 2100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 73 | 1117 | 73 | 1132 | 15 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123360 | 42400116 | Honor Oak Park to Forest Hill Dn | 2 | 2100 | LBW | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 4 | 1396 | 4 | 1408 | 12 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123370 | 42400116 | Honor Oak Park to Forest Hill Dn | 2 | 2100 | LBW | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 5 | 828 | 5 | 842 | 14 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123400 | 42500419 | Farningham Road to Fawkham Jcn Up | 2 | 1100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 20 | 1520 | 20 | 1535 | 15 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123410 | 42500419 | Farningham Road to Fawkham Jcn Up | 2 | 1100 | VIR | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 22 | 392 | 22 | 414 | 22 |  | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123520 | 42500121 | Chislehurst to Petts Wood Dn | 14 | 2100 | XTD | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-21 09:00 | 0 day(s) 08:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax Cat:14 | 11 | 1590 | 12 | 258 | 428
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 52 | 154931 | A3160 | 43300818df1 | Redhill to Reigate | 2 | 1100 | RSJ | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 22 | 1373 | 22 | 1395 | 22 | SUS-1929-26 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 52 | 154931 | A3170 | 43300818df1 | Redhill to Reigate | 11 | 1100 | RSJ | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 22 | 1395 | 23 | 32 | 397 | SUS-1929-26 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 52 | 154931 | G1030 | 43401318df1 | Haywards Hth Tnl Sth to High Bridge | 11 | 2100 | VTB3 | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11(T) | 38 | 620 | 38 | 1320 | 700 | SUS-1819-53 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 52 | 154931 | G4T130450 | 43300818df1 | Redhill to Reigate | 11 | 1100 | RSJ | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 22 | 1218 | 22 | 1373 | 155 | SUS-1929-26 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 52 | 154931 | G4T169700 | 43300818df1 | Redhill to Reigate | 2 | 1100 | RSJ | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 22 | 1204 | 22 | 1218 | 14 | SUS-1929-26 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 52 | 154931 | G4T169710 | 43300818df1 | Redhill to Reigate | 2 | 1100 | RSJ | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 23 | 32 | 23 | 44 | 12 | SUS-1929-26 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 52 | 154931 | G4T169740 | 43401318df1 | Haywards Hth Tnl Sth to High Bridge | 2 | 2100 | VTB3 | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 38 | 372 | 38 | 394 | 22 | SUS-1819-53 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 52 | 154931 | G4T169750 | 43401318df1 | Haywards Hth Tnl Sth to High Bridge | 2 | 2100 | VTB3 | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 38 | 1320 | 38 | 1336 | 16 | SUS-1819-53 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 19/20 | 52 | 154931 | G4T77530 | 43401318df1 | Haywards Hth Tnl Sth to High Bridge | 14 | 2100 | VTB3 | Weekend | W2019/000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 38 | 394 | 38 | 620 | 226 | SUS-1819-53 | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 52 | 154929 | A8690 | 41500119 | Bow Up Electric 1 | 11 | 1152 | LTN1 | Weekend | W2019/0000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/4 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 1 | 374 | 1 | 913 | 539 | Job moved to UND. CC ref EA-1920-44 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 52 | 154929 | G4T387810 | 41501719 | Stratford Up Main 2 | 2 | 1100 | LTN1 | Weekend | W2019/0000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 3 | 802 | 3 | 811 | 9 | Job moved to UND. CC ref EA-1920-44 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 52 | 154929 | G4T387820 | 41501719 | Stratford Up Main 2 | 2 | 1100 | LTN1 | Weekend | W2019/0000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 3 | 1104 | 3 | 1109 | 5 | Job moved to UND. CC ref EA-1920-44 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 19/20 | 52 | 154929 | G4T388670 | 41501719 | Stratford Up Main 2 | 11 | 1100 | LTN1 | Weekend | W2019/0000000 | 2020-03-21 01:00 | 2020-03-23 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 811 | 3 | 1104 | 293 | Job moved to UND. CC ref EA-1920-44 refers
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 52 | 154341 | A46550 | 24100619 | COT Woodside Cottage Down | 14 | 2100 | NAJ3 | Weekend |  | 2020-03-21 01:00 | 2020-03-22 05:00 | 1 day(s) 04:00 Hrs | CORE: 1 of 1: COT Woodside Cottage Down - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 481yds | 2 | 174 | 2 | 655 | 481
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 19/20 | 52 | 154934 | G4T25010 | 44402310SF1 | Shutters - Haslemere | 11 | 1100 | WPH1 | Weekend |  | 2020-03-21 01:00 | 2020-03-23 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail, Resleeper, Reballast - Trax | 41 | 550 | 41 | 1300 | 750
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 52 | 154335 | A2475160 | 125231 | Grimsby Marsh West | 11 | 2100 | MAC3 | Weekend | W2019/0000000 | 2020-03-21 01:00 | 2020-03-22 06:00 | 1 day(s) 05:00 Hrs | CORE: CAT11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 382yds (Not in PPS) | 107 | 1577 | 108 | 199 | 382 | PLN-1920-045 (Not in PPS)
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 52 | 154335 | A2489250 | 132028 | Sessay | 11 | 2100 | ECM5 | Weekend | W2019/0000000 | 2020-03-21 01:00 | 2020-03-22 01:00 | 1 day(s) 00:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 154yds | 18 | 1176 | 18 | 1329 | 154 | PLN-1920-098 | APC
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 52 | 154341 | A397120 | 23209099 | Jackson's | 14 | 1100 | LEC2 | Weekend |  | 2020-03-21 22:00 | 2020-03-22 09:00 | 0 day(s) 11:00 Hrs | CORE: 6 of 7: Jackson's - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 123 | 466 | 123 | 613 | 147
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 52 | 158412 | A2465000 | 24211099 | Tyseley Drainage | 15aa | 1100 | TSB | Weekend |  | 2020-03-21 22:00 | 2020-03-22 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Tyseley Drainage - CAT15aa - 387yds | 0 | 83 | 0 | 470 | 387
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 52 | 154146 | A3170 | 52101310 | Defford Down Main | 12 | 2100 | BAG2 | Weekend | W2019/0000000 | 2020-03-21 23:00 | 2020-03-23 02:00 | 1 day(s) 03:00 Hrs | CORE: 1/2 Reballast, Formation - Trax Cat: 12 | 73 | 132 | 73 | 423 | 291
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 52 | 154338 | A15500 | 121154 | Alexandra Palace Up Slow-1 | 11 | 1200 | ECM1 | Weekend |  | 2020-03-21 23:00 | 2020-03-23 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 268yds | 5 | 1131 | 5 | 1399 | 268 | CC received 17/05/2017 - Mileages amended from 5m858y-5m1672y to 5m863y-5m1667y (from 814Ly to 804Ly). Job moved weeks from 50, 51 & 52 to 51, 52 & 53 as per C/C ref: PLS-1920-128
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 52 | 154343 | A249410 | 32101318 | West Kilbride Station South | 7 | 1300 | LGS2 | Weekend |  | 2020-03-22 00:01 | 2020-03-23 05:01 | 1 day(s) 05:00 Hrs | CORE: West Kilbride Station South [Week 52] Cat 07:583 yds | 34 | 951 | 34 | 1534 | 583
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 52 | 154343 | A291740 | 31300220 | Bennochy | 11 | 1100 | ECN2 | Weekend |  | 2020-03-22 00:01 | 2020-03-23 05:01 | 1 day(s) 05:00 Hrs | CORE: Bennochy [Week 52] Cat 11:495 yds | 26 | 173 | 26 | 668 | 495
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | A8690 | 42200216sf1 | Bexley to Albany Park Up | 11 | 1100 | HDR | Weekend | W2019/000000 | 2020-03-27 01:25 | 2020-03-27 06:45 | 0 day(s) 05:20 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 12 | 1629 | 13 | 466 | 597 | KENT-1920-26 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123200 | 42200216sf1 | Bexley to Albany Park Up | 2 | 1100 | HDR | Weekend | W2019/000000 | 2020-03-27 01:25 | 2020-03-27 06:45 | 0 day(s) 05:20 Hrs | CORE: Rerail - Both Rails Cat:02 | 12 | 1619 | 12 | 1629 | 10 | KENT-1920-26 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 52 | 154930 | G4T123210 | 42200216sf1 | Bexley to Albany Park Up | 2 | 1100 | HDR | Weekend | W2019/000000 | 2020-03-27 01:25 | 2020-03-27 06:45 | 0 day(s) 05:20 Hrs | CORE: Rerail - Both Rails Cat:02 | 13 | 466 | 13 | 476 | 10 | KENT-1920-26 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 1 | 154930 | A7650 | 42400717 | New Cross Gate to Brockley Up Slow | 11 | 1200 | LBW | Weekend | W2019/000000 | 2020-03-28 00:30 | 2020-03-30 04:30 | 2 day(s) 04:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 2 | 1732 | 3 | 805 | 833
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 19/20 | 1 | 154930 | A6610 | 42200119 | Up Crayford Spur | 11 | 1100 | CRA | Weekend | W2019/000000 | 2020-03-28 01:00 | 2020-03-28 05:00 | 0 day(s) 04:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 16 | 300 | 16 | 824 | 524 |  | APC
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 1 | 154146 | A4210 | 51130214 | Drayton Green | 11 | 1100 | WEL1 | Weekend | W2019/0000000 | 2020-03-28 01:00 | 2020-03-28 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 6 | 1672 | 7 | 44 | 131
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 1 | 154341 | A397130 | 23209099 | Jackson's | 14 | 1100 | LEC2 | Weekend |  | 2020-03-28 22:00 | 2020-03-29 09:00 | 0 day(s) 11:00 Hrs | CORE: 7 of 7: Jackson's - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 123 | 613 | 123 | 760 | 147
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 19/20 | 1 | 158412 | A2461880 | 23512699 | Duston West | 15aa | 1100 | HNR | Weekend |  | 2020-03-28 22:00 | 2020-03-29 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Duston West - CAT15aa - 290yds | 64 | 1170 | 64 | 1460 | 290
N/A | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 19/20 | 1 | 154146 | A35850 | 52101310 | Defford Down Main | 12 | 2100 | BAG2 | Weekend | W2019/0000000 | 2020-03-28 23:00 | 2020-03-30 02:00 | 1 day(s) 03:00 Hrs | CORE: 2/2 Reballast, Formation - Trax Cat: 12 | 73 | 423 | 73 | 715 | 292
South, Mrs Amanda Jayne (Amanda) | Plain Line | N/A | London North East | Carillion Rail | Peterborough | 19/20 | 1 | 154338 | A15510 | 121154 | Alexandra Palace Up Slow-1 | 11 | 1200 | ECM1 | Weekend |  | 2020-03-28 23:00 | 2020-03-30 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11: Reballast, Resleeper, Rerail - Trax - 268yds | 5 | 1399 | 5 | 1667 | 268 | CC received 17/05/2017 - Mileages amended from 5m858y-5m1672y to 5m863y-5m1667y (from 814Ly to 804Ly). Job moved weeks from 50, 51 & 52 to 51, 52 & 53 as per C/C ref: PLS-1920-128
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 1 | 154343 | A288410 | 31300321 | Orr Mills Curve | 16 | 2100 | ECN2 | Weekend |  | 2020-03-29 00:01 | 2020-03-30 05:01 | 1 day(s) 05:00 Hrs | CORE: Orr Mills Curve [Week 53] Cat 16:530 yds | 29 | 1149 | 29 | 1679 | 530
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 1 | 154343 | A291700 | 31300321 | Orr Mills Curve | 16 | 2100 | ECN2 | Weekend |  | 2020-03-29 00:01 | 2020-03-30 05:01 | 1 day(s) 05:00 Hrs | CORE: Orr Mills Curve [Week 53] Cat 16:536 yds | 29 | 1679 | 30 | 455 | 536
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 1 | 154335 | A2468090 | GC036 | Whitchester Tunnel | 11 | 2100 | NEC2 | Weekend | W2019/0000000 | 2020-03-30 01:00 | 2020-03-30 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/2: CAT 11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 472yds | 35 | 1379 | 36 | 91 | 472 | Undated on JW spreadsheet dated 05/01/18
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 1 | 154335 | A2469090 | GC037 | Whitchester Tunnel-1 | 11 | 1100 | NEC2 | Weekend | W2019/0000000 | 2020-03-30 01:00 | 2020-03-30 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1: CAT 11: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) : 472yds | 35 | 1379 | 36 | 91 | 472 | Undated on JW spreadsheet dated 05/01/18
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Carillion Rail | Doncaster | 19/20 | 1 | 154335 | A2473000 | GC036 | Whitchester Tunnel | 15aa | 2100 | NEC2 | Weekend | W2019/0000000 | 2020-03-30 01:00 | 2020-03-30 17:00 | 0 day(s) 16:00 Hrs | CORE: 2/2: CAT 15A: Drain (Associated with Track Renewal) : 385yds (352m) | 35 | 1379 | 36 | 4 | 385 | Undated on JW spreadsheet dated 05/01/18
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 19/20 | 1 | 154343 | A282410 | FD32300111c | Kirkland Glen | 11 | 1300 | LGS2 | Midweek Nights |  | 2020-03-31 00:01 | 2020-03-31 08:01 | 0 day(s) 08:00 Hrs | CORE: Kirkland Glen [Week 53] Cat 11:146 yds | 32 | 622 | 32 | 658 | 36 |  | APC
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 1 | 157045 | A21710 | COT21401599 | Oubeck | 14 | 1100 | CGJ6 | Weekend |  | 2020-04-04 20:00 | 2020-04-05 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 4: Oubeck - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 169yds | 18 | 329 | 18 | 498 | 169
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 1 | 157046 | A53760 | 23600120 | Atherstone South | 12 | 2100 | LEC2 | Weekend |  | 2020-04-04 22:00 | 2020-04-05 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: Atherstone South - Reballast, Formaion -Trax - CAT12 - 150yds | 101 | 750 | 101 | 900 | 150
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 1 | 157046 | A55820 | 23500620 | Courteenhall Road | 12 | 2100 | LEC1 | Weekend |  | 2020-04-04 22:00 | 2020-04-05 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Courteenhall Road - Reballast, Formaion -Trax - CAT12 - 100yds | 61 | 640 | 61 | 740 | 100
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 1 | 157680 | A85190 | 323031186 | Leggatfoot North | 14 | 2100 | WCM1 | Weekend |  | 2020-04-05 00:01 | 2020-04-05 10:01 | 0 day(s) 10:00 Hrs | Kirtle Viaduct Falldown | 69 | 1540 | 70 | 220 | 440
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 2 | 157045 | A12530 | COT22700319a | Golborne -1 | 14 | 2100 | CGJ5 | Weekend |  | 2020-04-11 20:00 | 2020-04-12 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Goldborne -1 - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 484yds | 1 | 1036 | 1 | 1520 | 484
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 2 | 157046 | A30070 | 23100215 | Linslade Tunnel | 11 | 2100 | LEC1 | Weekend |  | 2020-04-11 22:00 | 2020-04-12 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT Linslade Tunnel - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - CAT11 - 484yds | 40 | 1278 | 41 | 2 | 484
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 2 | 157046 | A60970 | 23500920 | SLF Pinley South Up | 2 | 1100 | RBS1 | Weekend |  | 2020-04-11 22:00 | 2020-04-12 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: SLF Pinley South Up - Rerail (Both Rails) - CAT02 - 1259yds | 91 | 1152 | 92 | 651 | 1259
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 2 | 157046 | A62000 | 24301022 | SLF Pinley | 2 | 1100 | RBS1 | Weekend |  | 2020-04-11 22:00 | 2020-04-12 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: SLF Pinley - Rerail (Both Rails) - CAT02 - 1550yds | 92 | 1430 | 93 | 1220 | 1550
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 2 | 159796 | A3270 | 114590 | Wellingborough | 14 | 2100 | SPC3 | Weekend | W2020/0000000 | 2020-04-11 23:00 | 2020-04-13 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 256yds | 65 | 1236 | 65 | 1492 | 256 | C/C ref: PLS-2021-008 to bring in to 20/21 workbank. | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 2 | 159796 | A35420 | 114590 | Wellingborough | 2 | 2100 | SPC3 | Weekend | W2020/0000000 | 2020-04-11 23:00 | 2020-04-13 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail - 6yds | 65 | 1492 | 65 | 1498 | 6 | C/C ref: PLS-2021-008 to bring in to 20/21 workbank. | APC
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 2 | 159796 | A6390 | 114022 | St Albans Station | 11 | 1100 | SPC1 | Weekend | W2020/0000000 | 2020-04-11 23:00 | 2020-04-13 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 255yds | 19 | 1185 | 19 | 1440 | 255 | C/C ref: PLS-2021-015 to bring in to 20/21 workbank. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 2 | 157680 | A63200 | FD32202217 | Carluke Station 09/10 falldown | 11 | 1100 | WCM1 | Weekend |  | 2020-04-12 00:01 | 2020-04-12 16:01 | 0 day(s) 16:00 Hrs | Douglas Bidge | 81 | 850 | 82 | 68 | 978
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 3 | 157045 | A2452380 | COT21401599 | Oubeck | 14 | 1100 | CGJ6 | Weekend |  | 2020-04-18 20:00 | 2020-04-19 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 4: Oubeck - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 168yds | 18 | 498 | 18 | 666 | 168
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 3 | 157046 | A347610 | 23600120 | Atherstone South | 12 | 2100 | LEC2 | Weekend |  | 2020-04-18 22:00 | 2020-04-19 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: Atherstone South - Reballast, Formaion -Trax - CAT12 - 150yds | 101 | 900 | 101 | 1050 | 150
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 3 | 159796 | A10450 | 114596 | Kentish Town Junction | 11 | 1100 | MCL | Weekend |  | 2020-04-18 23:00 | 2020-04-20 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11 - Reballast, Resleeper, Rerail - Trax - 351yds | 3 | 1019 | 3 | 1370 | 351 | East Mids 2019-20 IP Plain Line Complete Trax Workbank - extract from RAMP on 26-09-2016. LP CC PLS-1920-044 Amend principal treatments to CAT 14 3m - 1019y to 3m - 1307 & 3m 1503y - 4m 3y. Amended to Cat 11 vice Cat 14 - approved c/c ref: PLS-1920-080
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 3 | 159796 | A37360 | 114596 | Kentish Town Junction | 11 | 1100 | MCL | Weekend |  | 2020-04-18 23:00 | 2020-04-20 05:00 | 1 day(s) 06:00 Hrs | CORE: CAT 11 - Reballast, Resleeper, Rerail - Trax - 260yds | 3 | 1503 | 4 | 3 | 260 | East Mids 2019-20 IP Plain Line Complete Trax Workbank - extract from RAMP on 26-09-2016. LP CC PLS-1920-044 Amend principal treatments to CAT 14 3m - 1019y to 3m - 1307 & 3m 1503y - 4m 3y. Amended to Cat 11 vice Cat 14 - approved c/c ref: PLS-1920-080
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 3 | 157680 | A62150 | 32201623 | Braidwood | 14 | 1100 | WCM1 | Weekend |  | 2020-04-19 00:01 | 2020-04-19 16:01 | 0 day(s) 16:00 Hrs | Douglas Bidge | 80 | 1320 | 81 | 220 | 660
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 4 | 157045 | A2452390 | COT21401599 | Oubeck | 14 | 1100 | CGJ6 | Weekend |  | 2020-04-25 20:00 | 2020-04-26 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 4: Oubeck - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 168yds | 18 | 666 | 18 | 834 | 168
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 4 | 157046 | A10490 | 23402320 | COT Old Oak Common Lane | 14 | 3102 | WAW | Weekend |  | 2020-04-25 22:00 | 2020-04-26 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: COT Old Oak Common Lane - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 357yds | 6 | 1157 | 6 | 1514 | 357
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 4 | 157046 | A347620 | 23600120 | Atherstone South | 12 | 2100 | LEC2 | Weekend |  | 2020-04-25 22:00 | 2020-04-26 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: Atherstone South - Reballast, Formaion -Trax - CAT12 - 150yds | 101 | 1050 | 101 | 1200 | 150
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 4 | 157680 | A2190 | FD32200216 | Cowthat North 16/17 Shortfall | 11 | 2100 | WCM1 | Weekend |  | 2020-04-26 00:01 | 2020-04-27 03:01 | 1 day(s) 03:00 Hrs | Cowthat North 16/17 Shortfall | 19 | 1435 | 19 | 1712 | 277
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 4 | 157680 | A32690 | FD32303217 | Eglinton Street North Up Fast | 7 | 1100 | WCM2 | Weekend |  | 2020-04-26 00:01 | 2020-04-27 03:01 | 1 day(s) 03:00 Hrs | Eglinton Street North Up Fast | 101 | 535 | 101 | 649 | 114
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 4 | 156707 | A22930 | 44402115*sf1 | Shalford | 11 | 2100 | RSJ | Weekend |  | 2020-04-26 01:25 | 2020-04-27 04:30 | 1 day(s) 03:05 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 41 | 128 | 41 | 704 | 576
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 5 | 157045 | A13550 | COT22700319 | Goldborne | 14 | 2100 | CGJ5 | Weekend |  | 2020-05-02 20:00 | 2020-05-03 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Goldborne - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 428yds | 2 | 202 | 2 | 630 | 428
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 5 | 157046 | A346610 | 23400517 | North Wembley | 12 | 2100 | LEC1 | Weekend |  | 2020-05-02 22:20 | 2020-05-06 01:20 | 3 day(s) 03:00 Hrs | CORE: 1 of 1 Reballast, Formation - Trax - Cat12 - 806yds | 8 | 1100 | 9 | 146 | 806
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 5 | 157680 | A6440 | 31200519 | Linhouse Viaduct | 11 | 1100 | ECA2 | Weekend |  | 2020-05-03 00:01 | 2020-05-04 03:01 | 1 day(s) 03:00 Hrs | Linhouse Viaduct | 88 | 500 | 88 | 993 | 493
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 5 | 157680 | A8540 | FD32200917a | Davy's Bridge 17/18 Falldown | 11 | 2100 | WCM1 | Weekend |  | 2020-05-03 00:01 | 2020-05-05 06:01 | 2 day(s) 06:00 Hrs | Davy's Bridge 17/18 Falldown | 43 | 875 | 43 | 1459 | 584
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 6 | 156707 | A21890 | 44500711 | Petersfinger DM | 11 | 2100 | RTJ2 | Weekend |  | 2020-05-09 01:10 | 2020-05-11 04:00 | 2 day(s) 02:50 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 94 | 875 | 94 | 1650 | 775
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 6 | 157045 | A2452370 | COT21401599 | Oubeck | 14 | 1100 | CGJ6 | Weekend |  | 2020-05-09 20:00 | 2020-05-10 12:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 4: Oubeck - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 169yds | 18 | 834 | 18 | 1003 | 169
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 6 | 157046 | A353170 | 23400215 | Primrose Hill Tunnel | 14 | 2100 | LEC1 | Weekend |  | 2020-05-09 22:00 | 2020-05-10 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 4: Formation, Reballast, Resleeper, Rerail - Trax - CAT14 - 293yds | 1 | 1189 | 1 | 1482 | 293
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 6 | 157680 | A3280 | FD32200717B | Douglas Bridge | 11 | 2100 | WCM1 | Weekend |  | 2020-05-10 00:01 | 2020-05-11 03:01 | 1 day(s) 03:00 Hrs | Douglas Bidge | 26 | 883 | 26 | 1265 | 382
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 6 | 157680 | A7300 | 31200519 | Linhouse Viaduct | 11 | 1100 | ECA2 | Weekend |  | 2020-05-10 00:01 | 2020-05-11 03:01 | 1 day(s) 03:00 Hrs | Linhouse Viaduct | 88 | 993 | 88 | 1486 | 493
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 7 | 157045 | A2451310 | 21501417 | Woodacre | 13 | 1100 | CGJ6 | Weekend |  | 2020-05-16 20:00 | 2020-05-17 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Woodacre - Resleeper, Reballast, Formation - Trax - CAT13 - 207yds | 10 | 1320 | 10 | 1527 | 207
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 7 | 157046 | A354030 | 23400215 | Primrose Hill Tunnel | 14 | 2100 | LEC1 | Weekend |  | 2020-05-16 22:00 | 2020-05-17 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 4: Formation, Reballast, Resleeper, Rerail - Trax - CAT14 - 293yds | 1 | 1482 | 2 | 15 | 293
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 7 | 157680 | A64250 | FD110138a | Cobbinshaw 09/10 falldown | 14 | 2100 | ECA2 | Weekend |  | 2020-05-17 00:01 | 2020-05-18 03:01 | 1 day(s) 03:00 Hrs | Douglas Bidge | 82 | 1687 | 83 | 280 | 353
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 7 | 157680 | A6450 | 31200519 | Linhouse Viaduct | 11 | 1100 | ECA2 | Weekend |  | 2020-05-17 00:01 | 2020-05-18 03:01 | 1 day(s) 03:00 Hrs | Linhouse Viaduct | 88 | 1486 | 89 | 220 | 494
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 8 | 157045 | A10430 | GAC22202199 | Preston Brook Tunnel Up | 11 | 1100 | CGJ1 | Weekend |  | 2020-05-23 20:00 | 2020-05-24 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Preston Brook Tunnel Up - Rerail, Resleeper, Reballast - Trax - CAT11 - 460yds | 175 | 1600 | 176 | 300 | 460
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 8 | 157046 | A28000 | 23101620 | Leighton Buzzard Down Fast | 14 | 2100 | LEC1 | Weekend |  | 2020-05-23 22:00 | 2020-05-24 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Leighton Buzzard Down Fast - Formation, Reballast, Resleeper, Rerail - Trax - CAT14 - 710yds | 39 | 1697 | 40 | 647 | 710
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 8 | 159796 | A7430 | 114457 | Luton | 14 | 1100 | SPC1 | Weekend |  | 2020-05-23 23:00 | 2020-05-25 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 264yds | 30 | 259 | 30 | 523 | 264 | C/C ref: PLS-2021-014 to bring in to 2021 workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 8 | 159796 | A7440 | 114457 | Luton | 2 | 1100 | SPC1 | Weekend |  | 2020-05-23 23:00 | 2020-05-25 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail - Both rails - 7yds | 30 | 542 | 30 | 549 | 7 | C/C ref: PLS-2021-014 to bring in to 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 8 | 157680 | A23240 | FD32201510B | Kirtle Viaduct Falldown | 12 | 2100 | WCM1 | Weekend |  | 2020-05-24 00:01 | 2020-05-24 10:01 | 0 day(s) 10:00 Hrs | Kirtle Viaduct Falldown | 15 | 947 | 15 | 1402 | 95
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 8 | 157680 | A5390 | 32200923 | Tank | 14 | 1100 | WCM1 | Weekend |  | 2020-05-24 00:01 | 2020-05-26 06:01 | 2 day(s) 06:00 Hrs | Tank | 48 | 1330 | 49 | 330 | 760
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 9 | 157045 | A2453560 | 21400918 | Bolton le Sands | 11 | 1100 | CGJ7 | Weekend |  | 2020-05-30 20:00 | 2020-05-31 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: Bolton Le Sands - Rerail, Resleeper, Reballast - Trax - CAT11 - 108yds | 4 | 665 | 4 | 773 | 108
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 9 | 157046 | A353180 | 23400215 | Primrose Hill Tunnel | 14 | 2100 | LEC1 | Weekend |  | 2020-05-30 22:00 | 2020-05-31 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 4: Formation, Reballast, Resleeper, Rerail - Trax - CAT14 - 293yds | 2 | 15 | 2 | 308 | 293
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 9 | 159796 | A55300 | 114457 | Luton | 11 | 1100 | SPC1 | Weekend |  | 2020-05-30 23:00 | 2020-06-01 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 19yds | 30 | 523 | 30 | 542 | 19 | C/C ref: PLS-2021-014 to bring in to 2021 workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 9 | 159796 | A8290 | 114457 | Luton | 11 | 1100 | SPC1 | Weekend |  | 2020-05-30 23:00 | 2020-06-01 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 164yds | 30 | 95 | 30 | 259 | 164 | C/C ref: PLS-2021-014 to bring in to 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 9 | 157680 | A66350 | FD32201216b | Hairy Dan's | 11 | 2100 | WCM1 | Weekend |  | 2020-05-31 00:01 | 2020-06-01 03:01 | 1 day(s) 03:00 Hrs | Douglas Bidge | 62 | 630 | 62 | 895 | 265
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 10 | 157045 | A2454490 | 21400918 | Bolton le Sands | 11 | 1100 | CGJ7 | Weekend |  | 2020-06-06 20:00 | 2020-06-07 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: Bolton Le Sands - Rerail, Resleeper, Reballast - Trax - CAT11 - 107yds | 4 | 773 | 4 | 880 | 107
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 10 | 157046 | A355160 | 23400215 | Primrose Hill Tunnel | 14 | 2100 | LEC1 | Weekend |  | 2020-06-06 22:00 | 2020-06-07 14:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 4: Formation, Reballast, Resleeper, Rerail - Trax - CAT14 - 292yds | 2 | 308 | 2 | 600 | 292
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 10 | 159796 | A8470 | 114438 | Luton South | 13 | 1100 | SPC1 | Weekend |  | 2020-06-06 23:00 | 2020-06-08 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 13 - Formation, Reballast, Resleeper - Trax - 230yds | 29 | 400 | 29 | 630 | 230 | C/C ref: PLS-2021-013 to bring in to 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 10 | 157680 | A67400 | FD3220816 | Lockerbie 14/15 falldown | 11 | 1100 | WCM1 | Weekend |  | 2020-06-07 00:01 | 2020-06-08 03:01 | 1 day(s) 03:00 Hrs | Douglas Bidge | 26 | 355 | 26 | 1240 | 885
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 10 | 157680 | A9590 | FD32201518 | Hoover 16/17 Shortfall | 11 | 2100 | WCM2 | Weekend |  | 2020-06-07 00:01 | 2020-06-08 05:01 | 1 day(s) 05:00 Hrs | Hoover 16/17 Shortfall | 96 | 1315 | 97 | 65 | 510
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 11 | 156707 | A16690 | 44350316 | Feltham Jcn - River Crane | 14 | 1100 | RDG1 | Weekend |  | 2020-06-13 01:00 | 2020-06-15 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 13 | 807 | 13 | 1161 | 354
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 11 | 156707 | A17550 | 44350316 | Feltham Jcn - River Crane | 11 | 1100 | RDG1 | Weekend |  | 2020-06-13 01:00 | 2020-06-15 04:00 | 2 day(s) 03:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 13 | 1161 | 13 | 1606 | 445
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 11 | 157045 | A2455630 | COT21500719 | Gravel Hole | 14 | 2100 | CGJ6 | Weekend |  | 2020-06-13 20:00 | 2020-06-14 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Gravel Hole - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 138yds | 14 | 280 | 14 | 418 | 138
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 11 | 157046 | A350900 | 24304299 | Rolf Street | 12 | 2100 | RBS2 | Weekend |  | 2020-06-13 22:00 | 2020-06-14 14:00 | 0 day(s) 16:00 Hrs | CORE: 1of 1: Reballast, Formaion -Trax - CAT12 - 190yds | 3 | 500 | 3 | 751 | 251
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 11 | 157046 | A39340 | 24101319 | COT Princess Risborough Station | 11 | 2100 | NAJ2 | Weekend |  | 2020-06-13 22:00 | 2020-06-14 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT Princess Risborough Station - Reballast, Resleeper, Rerail - Trax - CAT11 - 351yds | 24 | 228 | 24 | 1041 | 813
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 11 | 159796 | A9330 | 114438 | Luton South | 13 | 1100 | SPC1 | Weekend |  | 2020-06-13 23:00 | 2020-06-15 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 13 - Formation, Reballast, Resleeper - Trax - 230yds | 29 | 630 | 29 | 860 | 230 | C/C ref: PLS-2021-013 to bring in to 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 11 | 157680 | A10450 | FD32201518 | Hoover 16/17 Shortfall | 11 | 2100 | WCM2 | Weekend |  | 2020-06-14 00:01 | 2020-06-15 05:01 | 1 day(s) 05:00 Hrs | Hoover 16/17 Shortfall | 97 | 725 | 97 | 937 | 212
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 12 | 156707 | A27090 | 44202915sf1 | Tapnage | 11 | 3400 | ETF | Weekend |  | 2020-06-20 01:00 | 2020-06-22 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 81 | 699 | 81 | 940 | 241
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 12 | 157045 | A2454590 | COT22100213 | Frodsham Viaduct | 2 | 2100 | CHW1 | Weekend |  | 2020-06-20 20:00 | 2020-06-21 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Frodsham Viaduct - Rerail - Both Rails - CAT02 - 2yds | 10 | 968 | 10 | 970 | 2
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 12 | 157045 | A2455520 | COT22100213 | Frodsham Viaduct | 11 | 2100 | CHW1 | Weekend |  | 2020-06-20 20:00 | 2020-06-21 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Frodsham Viaduct - Rerail, Resleeper, Reballast - Trax - CAT11 - 487yds | 10 | 970 | 10 | 1457 | 487
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 12 | 157045 | A2455530 | COT22100213 | Frodsham Viaduct | 2 | 2100 | CHW1 | Weekend |  | 2020-06-20 20:00 | 2020-06-21 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Frodsham Viaduct - Rerail - Both Rails- CAT02 - 16yds | 10 | 1457 | 10 | 1473 | 16
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 12 | 157046 | A352850 | 24102119 | COT Blackstone Farm | 11 | 1100 | NAJ3 | Weekend |  | 2020-06-20 22:00 | 2020-06-21 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: COT Blackstone Farm Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - CAT11 - 50yds | 6 | 450 | 6 | 500 | 50
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 12 | 157046 | A352860 | 24102119 | COT Blackstone Farm | 14 | 1100 | NAJ3 | Weekend |  | 2020-06-20 22:00 | 2020-06-21 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: COT Blackstone Farm - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 250yds | 6 | 500 | 6 | 750 | 250
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 12 | 157046 | A7400 | 24102119 | COT Blackstone Farm | 14 | 1100 | NAJ3 | Weekend |  | 2020-06-20 22:00 | 2020-06-21 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: COT Blackstone Farm - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 230yds | 6 | 220 | 6 | 450 | 230
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 12 | 157680 | A68450 | 32203118C | Dryffe Water Viaduct 1617 Falldown | 11 | 2100 | WCM1 | Weekend |  | 2020-06-21 00:01 | 2020-06-22 03:01 | 1 day(s) 03:00 Hrs | Douglas Bidge | 27 | 1218 | 27 | 1757 | 539
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 12 | 157680 | A69500 | 32200519 | Yeskitts | 11 | 2100 | WCM1 | Weekend |  | 2020-06-21 00:01 | 2020-06-22 03:01 | 1 day(s) 03:00 Hrs | Douglas Bidge | 21 | 240 | 21 | 1210 | 970
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 13 | 156707 | A27950 | 44202915sf1 | Tapnage | 11 | 3400 | ETF | Weekend |  | 2020-06-27 01:00 | 2020-06-29 04:00 | 2 day(s) 03:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 81 | 940 | 82 | 486 | 1306
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 13 | 157045 | A17630 | 22201610 | Acton Bridge | 11 | 2100 | CGJ1 | Weekend |  | 2020-06-27 20:00 | 2020-06-28 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: Acton Bridge - Rerail, Resleeper, Reballast - Trax - CAT11 - 153yds | 172 | 1350 | 172 | 1503 | 153
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 13 | 157046 | A3280 | 23201013 | Amington | 12 | 1100 | LEC2 | Weekend |  | 2020-06-27 22:00 | 2020-06-28 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 4: Amington - Reballast, Formaion -Trax - CAT12 - 135yds | 108 | 780 | 108 | 915 | 135
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 13 | 157046 | A44490 | 24102619 | COT Woodside Cottage Up | 12 | 1100 | NAJ3 | Weekend |  | 2020-06-27 22:00 | 2020-06-28 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: COT Woodside Cottage Up - Reballast, Formaion -Trax - CAT12 - 550yds | 2 | 460 | 2 | 1010 | 550
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 14 | 157045 | A2452260 | 22201610 | Acton Bridge | 11 | 2100 | CGJ1 | Weekend |  | 2020-07-04 20:00 | 2020-07-05 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: Acton Bridge - Rerail, Resleeper, Reballast - Trax - CAT11 - 153yds | 172 | 1503 | 172 | 1656 | 153
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 14 | 157046 | A347560 | 23201013 | Amington | 12 | 1100 | LEC2 | Weekend |  | 2020-07-04 22:00 | 2020-07-05 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 4: Amington - Reballast, Formaion -Trax - CAT12 - 135yds | 108 | 915 | 108 | 1050 | 135
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 14 | 157046 | A353070 | 24300120 | Holiday Street Tunnel | 14 | 1100 | BAG1 | Weekend |  | 2020-07-04 22:00 | 2020-07-05 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: Holiday Street Tunnel - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 465yds | 42 | 1065 | 42 | 1530 | 465
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 14 | 159796 | A32390 | 114589 | Rushton | 12 | 2100 | SPC3 | Weekend | W2020/0000000 | 2020-07-04 23:00 | 2020-07-06 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 12 - Formation, Reballast - Traxcavate - 220yds | 77 | 220 | 77 | 440 | 220 | C/C ref: PLS-2021-012 to bring in to 20/21 workbank. | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 14 | 157680 | A29540 | FD32201217 | Abington South 17/18 Falldown | 11 | 1100 | WCM1 | Weekend |  | 2020-07-05 00:01 | 2020-07-05 10:01 | 0 day(s) 10:00 Hrs | Abington South 17/18 Falldown | 57 | 479 | 57 | 555 | 76
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 14 | 157680 | A70550 | 32200514 | Carfin Station | 11 | 2100 | EGS2 | Weekend |  | 2020-07-05 00:01 | 2020-07-06 05:01 | 1 day(s) 05:00 Hrs | Kirtle Viaduct Falldown | 1 | 1310 | 2 | 97 | 547
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 14 | 157680 | A71410 | 32200514 | Carfin Station | 16 | 2100 | EGS2 | Weekend |  | 2020-07-05 00:01 | 2020-07-06 05:01 | 1 day(s) 05:00 Hrs | Kirtle Viaduct Falldown | 1 | 1175 | 1 | 1310 | 135
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 15 | 157045 | A2452270 | 22201610 | Acton Bridge | 11 | 2100 | CGJ1 | Weekend |  | 2020-07-11 20:00 | 2020-07-12 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: Acton Bridge - Rerail, Resleeper, Reballast - Trax - CAT11 - 154yds | 172 | 1656 | 173 | 50 | 154
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 15 | 157046 | A23880 | 24300120 | Holiday Street Tunnel | 14 | 1100 | BAG1 | Weekend |  | 2020-07-11 22:00 | 2020-07-12 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: Holiday Street Tunnel - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 465yds | 42 | 1530 | 43 | 235 | 465
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 15 | 159796 | A34470 | 114553 | Sharnbrook | 11 | 1100 | SPC2 | Weekend | W2020/0000000 | 2020-07-11 23:00 | 2020-07-13 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 315yds | 56 | 559 | 56 | 874 | 315
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 15 | 159796 | A35430 | 114553 | Sharnbrook | 2 | 1100 | SPC2 | Weekend | W2020/0000000 | 2020-07-11 23:00 | 2020-07-13 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail - 20yds | 56 | 874 | 56 | 894 | 20
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 15 | 157680 | A30400 | FD32201217 | Abington South 17/18 Falldown | 11 | 1100 | WCM1 | Weekend |  | 2020-07-12 00:01 | 2020-07-12 10:01 | 0 day(s) 10:00 Hrs | Abington South 17/18 Falldown | 57 | 555 | 57 | 631 | 76
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 15 | 157680 | A71600 | 31201418 | West Calder Station Up | 11 | 1100 | EGS2 | Weekend |  | 2020-07-12 00:01 | 2020-07-13 05:01 | 1 day(s) 05:00 Hrs | Kirtle Viaduct Falldown | 18 | 552 | 18 | 765 | 213
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 16 | 156707 | A25010 | 44101710df1 | Stoneleigh | 11 | 2100 | RPE | Weekend |  | 2020-07-18 01:00 | 2020-07-20 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 11 | 1419 | 12 | 238 | 579
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 16 | 157045 | A18650 | 22200718 | Winsford | 11 | 1100 | CGJ1 | Weekend |  | 2020-07-18 20:00 | 2020-07-19 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: Winsford - Rerail, Resleeper, Reballast - Trax - CAT11 - 111yds | 166 | 0 | 166 | 111 | 111
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 16 | 157046 | A14610 | 23302820 | Watford Junction Down | 14 | 2100 | LEC1 | Weekend |  | 2020-07-18 22:00 | 2020-07-19 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: Watford Junction Down - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 17 | 580 | 17 | 727 | 147
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 16 | 157046 | A20790 | 23500520 | East Haddon Hill | 12 | 1100 | HNR | Weekend |  | 2020-07-18 22:00 | 2020-07-19 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: East Haddon Hill - Reballast, Formaion -Trax - CAT12 - 335yds | 73 | 140 | 73 | 475 | 335
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 16 | 157046 | A347570 | 23201013 | Amington | 12 | 1100 | LEC2 | Weekend |  | 2020-07-18 22:00 | 2020-07-19 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 4: Amington - Reballast, Formaion -Trax - CAT12 - 135yds | 108 | 1050 | 108 | 1185 | 135
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 16 | 159796 | A30310 | 30190 | Finchley Road | 7 | 2100 | SPC1 | Weekend |  | 2020-07-18 23:00 | 2020-07-20 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 07 - Reballast - Trax - 223yds | 3 | 621 | 3 | 844 | 223 | C/C ref: PLS-2021-009 to enter 20/21 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 16 | 157680 | A10640 | FD32200118a | Auldgirth 18/19 Falldown a | 11 | 1100 | GSW | Weekend |  | 2020-07-19 | 2020-07-20 20:00 | 1 day(s) 20:00 Hrs | Auldgirth 18/19 Falldown a | 84 | 1156 | 85 | 614 | 1218
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 16 | 157680 | A57890 | FD32200118b | Auldgirth 18/19 Falldown b | 11 | 1100 | GSW | Weekend |  | 2020-07-19 00:01 | 2020-07-20 20:01 | 1 day(s) 20:00 Hrs | Auldgirth 18/19 Falldown b | 85 | 614 | 85 | 72 | 1218
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 16 | 157680 | A72650 | 32200117 | New Cumnock North 17/18 falldown | 14 | 1100 | GSW | Weekend |  | 2020-07-19 00:01 | 2020-07-20 05:01 | 1 day(s) 05:00 Hrs | Kirtle Viaduct Falldown | 54 | 54 | 54 | 695 | 641
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 16 | 157680 | A73700 | 321011117 | Ballochmyle 17/18 falldown | 11 | 1100 | GSW | Weekend |  | 2020-07-19 00:01 | 2020-07-20 06:01 | 1 day(s) 06:00 Hrs | Kirtle Viaduct Falldown | 43 | 1583 | 44 | 548 | 725
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 17 | 157045 | A2452400 | 22200718 | Winsford | 11 | 1100 | CGJ1 | Weekend |  | 2020-07-25 20:00 | 2020-07-26 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: Winsford - Rerail, Resleeper, Reballast - Trax - CAT11 - 112yds | 166 | 111 | 166 | 223 | 112
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 17 | 157046 | A347580 | 23201013 | Amington | 12 | 1100 | LEC2 | Weekend |  | 2020-07-25 22:00 | 2020-07-26 14:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 4: Amington - Reballast, Formaion -Trax - CAT12 - 135yds | 108 | 1185 | 108 | 1320 | 135
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 17 | 157046 | A352880 | 23302820 | Watford Junction Down | 14 | 2100 | LEC1 | Weekend |  | 2020-07-25 22:00 | 2020-07-26 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: Watford Junction Down - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 17 | 727 | 17 | 874 | 147
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 17 | 159796 | A31170 | 30190 | Finchley Road | 7 | 2100 | SPC1 | Weekend |  | 2020-07-25 23:00 | 2020-07-27 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 07 - Reballast - Trax - 223yds | 3 | 844 | 3 | 1067 | 223 | C/C ref: PLS-2021-009 to enter 20/21 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 17 | 157680 | A11690 | FD32300517 | Queenspark 16/17 Falldown | 11 | 2100 | CTC | Weekend |  | 2020-07-26 00:01 | 2020-07-26 16:01 | 0 day(s) 16:00 Hrs | Queenspark 16/17 Falldown | 0 | 512 | 0 | 842 | 330
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 18 | 157045 | A2452410 | 22200718 | Winsford | 11 | 1100 | CGJ1 | Weekend |  | 2020-08-01 20:00 | 2020-08-02 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: Winsford - Rerail, Resleeper, Reballast - Trax - CAT11 - 112yds | 166 | 223 | 166 | 335 | 112
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 18 | 157046 | A352890 | 23302820 | Watford Junction Down | 14 | 2100 | LEC1 | Weekend |  | 2020-08-01 22:00 | 2020-08-02 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: Watford Junction Down - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 17 | 874 | 17 | 1020 | 146
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 19 | 156707 | A5250 | 44100110 | Ashstead Up Platform | 11 | 1100 | BTH3 | Weekend |  | 2020-08-08 01:00 | 2020-08-10 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 16 | 264 | 16 | 793 | 529
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 19 | 157046 | A43460 | 23400319 | COT South Hampsted | 14 | 1100 | CWJ | Weekend |  | 2020-08-08 22:00 | 2020-08-09 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: COT South Hampsted - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 393yds | 2 | 812 | 2 | 1205 | 393
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 19 | 157680 | A12740 | FD32202517 | Kirkhill 17/18 Falldown | 11 | 1100 | KHL | Weekend |  | 2020-08-09 00:01 | 2020-08-10 05:01 | 1 day(s) 05:00 Hrs | Kirkhill 17/18 Falldown | 96 | 1008 | 96 | 1324 | 316
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 19 | 157680 | A81990 | FD32202517 | Kirkhill 17/18 Falldown | 2 | 1100 | KHL | Weekend |  | 2020-08-09 00:01 | 2020-08-10 05:01 | 1 day(s) 05:00 Hrs | Kirkhill 17/18 Falldown | 96 | 955 | 96 | 1008 | 13
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 20 | 157045 | A19670 | 22200119 | Winsford SB | 14 | 1100 | CGJ1 | Weekend |  | 2020-08-15 20:00 | 2020-08-16 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: Winsford SB - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 126yds | 166 | 860 | 166 | 986 | 126
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 20 | 157046 | A312290 | 23100719 | COT Bletchley Flyover | 12 | 1200 | LEC1 | Weekend |  | 2020-08-15 20:00 | 2020-08-16 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: Reballast, Formation - Trax - Cat12 - 116yds | 46 | 650 | 46 | 766 | 116
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 20 | 157046 | A48610 | 23501118s | Stowe Hill | 12 | 2100 | LEC1 | Weekend |  | 2020-08-15 22:00 | 2020-08-16 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 4: Stowe Hill - Reballast, Formaion -Trax - CAT12 - 190yds | 68 | 10 | 68 | 200 | 190
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 20 | 157046 | A5340 | DP1110285 | Kingsbury | 14 | 1100 | DBP1 | Weekend |  | 2020-08-15 22:00 | 2020-08-16 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Kingsbury - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 275yds | 28 | 920 | 28 | 1195 | 275
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 20 | 157680 | A13600 | FD32202517 | Kirkhill 17/18 Falldown | 11 | 1100 | KHL | Weekend |  | 2020-08-16 00:01 | 2020-08-17 05:01 | 1 day(s) 05:00 Hrs | Kirkhill 17/18 Falldown | 96 | 1324 | 96 | 1680 | 356
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 21 | 156707 | A18770 | 44301712 | Mickelham Tunnel | 11 | 2100 | BTH3 | Weekend |  | 2020-08-22 01:10 | 2020-08-24 04:00 | 2 day(s) 02:50 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 19 | 1076 | 19 | 1713 | 637
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 21 | 157045 | A2452420 | 22200119 | Winsford SB | 14 | 1100 | CGJ1 | Weekend |  | 2020-08-22 20:00 | 2020-08-23 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: Winsford SB - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 127yds | 166 | 986 | 166 | 1113 | 127
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 21 | 157046 | A352870 | 23100719 | COT Bletchley Flyover | 12 | 1200 | LEC1 | Weekend |  | 2020-08-22 20:00 | 2020-08-23 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: Reballast, Formation - Trax - Cat12 - 117yds | 46 | 766 | 46 | 883 | 117
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 21 | 157680 | A13790 | 31300719 | Kincardine Junction | 14 | 3400 | KNE1 | Weekend |  | 2020-08-23 00:01 | 2020-08-25 06:01 | 2 day(s) 06:00 Hrs | Kincardine Junction | 3 | 880 | 3 | 1320 | 440
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 21 | 157680 | A14840 | 31300717 | Kincardine Old Platform 17/18 | 14 | 3400 | KNE1 | Weekend |  | 2020-08-23 00:01 | 2020-08-25 06:01 | 2 day(s) 06:00 Hrs | Kincardine Old Platform 17/18 | 3 | 1600 | 4 | 465 | 625
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 22 | 157045 | A8390 | COT22500119 | Macclesfield South Up | 12 | 1100 | CMD1 | Weekend |  | 2020-08-29 20:00 | 2020-08-30 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Macclesfield South Up - Reballast, Formation - Trax - CAT12 - 320yds | 1 | 830 | 1 | 1150 | 320
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 22 | 157046 | A4310 | 34380213s | Pinley | 14 | 1100 | RBS1 | Weekend |  | 2020-08-29 22:00 | 2020-08-30 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Pinley - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 779yds | 92 | 651 | 92 | 1430 | 779
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 22 | 157680 | A61080 | 31102219 | Carntyne Up | 16 | 2100 | NEM2 | Weekend |  | 2020-08-30 00:01 | 2020-09-01 04:01 | 2 day(s) 04:00 Hrs | Magazine Burn | 1 | 1534 | 2 | 640 | 866
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 23 | 157045 | A2457670 | COT22500919 | Knutsford East | 11 | 1100 | CDM2 | Weekend |  | 2020-09-05 20:00 | 2020-09-06 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Knutsford East - Rerail, Resleeper, Reballast - Trax - CAT11 - 410yds | 13 | 1500 | 14 | 150 | 410
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 23 | 157046 | A50670 | 23100717s | Haversham Bank | 12 | 1100 | LEC1 | Weekend |  | 2020-09-05 22:00 | 2020-09-06 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 4: Haversham Bank - Reballast, Formaion -Trax - CAT12 - 130yds | 52 | 500 | 52 | 630 | 130
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 23 | 157680 | A15890 | 31500116 | Corse | 16 | 3400 | ANI1 | Weekend |  | 2020-09-06 00:01 | 2020-09-08 06:01 | 2 day(s) 06:00 Hrs | Corse | 43 | 440 | 43 | 1200 | 760
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 23 | 157680 | A77900 | 31500619 | Oyne | 4 | 3400 | ANI1 | Weekend |  | 2020-09-06 00:01 | 2020-09-08 06:01 | 2 day(s) 06:00 Hrs | Corse | 24 | 1000 | 24 | 1600 | 600
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 24 | 156707 | A17730 | 44401415 | Haslemere Loop | 14 | 1501 | WPH1 | Weekend |  | 2020-09-12 01:00 | 2020-09-14 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 42 | 1542 | 43 | 232 | 450
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 24 | 157046 | A32130 | 23603999 | Nuneaton Station | 12 | 2100 | LEC2 | Weekend |  | 2020-09-12 22:00 | 2020-09-13 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Nuneaton Station- Reballast, Formaion -Trax - CAT12 - 410yds | 96 | 1730 | 97 | 380 | 410
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 24 | 157046 | A352910 | 23501118s | Stowe Hill | 12 | 2100 | LEC1 | Weekend |  | 2020-09-12 22:00 | 2020-09-13 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 4: Stowe Hill - Reballast, Formaion -Trax - CAT12 - 190yds | 68 | 200 | 68 | 390 | 190
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 24 | 157046 | A352990 | 23500520 | East Haddon Hill | 12 | 1100 | HNR | Weekend |  | 2020-09-12 22:00 | 2020-09-13 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: East Haddon Hill - Reballast, Formaion -Trax - CAT12 - 335yds | 73 | 475 | 73 | 810 | 335
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 24 | 159796 | A31350 | 114603 | Bedford | 11 | 2100 | SPC1 | Weekend |  | 2020-09-12 23:00 | 2020-09-14 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 324yds | 49 | 1036 | 49 | 1360 | 324 | C/C ref: PLS-2021-001 to enter 2021 workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 24 | 159796 | A32210 | 114603 | Bedford | 2 | 2100 | SPC1 | Weekend |  | 2020-09-12 23:00 | 2020-09-14 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail - Both rails - 74yds | 49 | 962 | 49 | 1036 | 74 | C/C ref: PLS-2021-001 to enter 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 24 | 157680 | A16940 | FD31500216 | Avochie 17/18 Shortfall | 11 | 3400 | ANI1 | Weekend |  | 2020-09-13 00:01 | 2020-09-13 16:01 | 0 day(s) 16:00 Hrs | Avochie 17/18 Shortfall | 45 | 81 | 45 | 205 | 124
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 24 | 157680 | A76850 | 31500819 | Wantonwells | 4 | 2100 | ANI1 | Weekend |  | 2020-09-13 00:01 | 2020-09-15 06:01 | 2 day(s) 06:00 Hrs | Avochie 17/18 Shortfall | 28 | 880 | 29 | 0 | 880
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 25 | 156707 | A2130 | 44102210sf7 | West Crossings - Vauxhall DMF | 11 | 2100 | BML1 | Weekend |  | 2020-09-19 01:00 | 2020-09-21 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 0 | 971 | 0 | 1709 | 737
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 25 | 157045 | A2458690 | COT22800524 | Peak Forrest to Dove Holes | 11 | 1100 | CNB1 | Weekend |  | 2020-09-19 20:00 | 2020-09-20 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: Peak Forrest to Dove Holes - Rerail, Resleeper, Reballast - Trax - CAT11 - 376yds | 163 | 1582 | 164 | 198 | 376
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 25 | 157046 | A352900 | 23501118s | Stowe Hill | 12 | 2100 | LEC1 | Weekend |  | 2020-09-19 22:00 | 2020-09-20 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 4: Stowe Hill - Reballast, Formaion -Trax - CAT12 - 190yds | 68 | 390 | 68 | 580 | 190
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 25 | 157046 | A353050 | 23100717s | Haversham Bank | 12 | 1100 | LEC1 | Weekend |  | 2020-09-19 22:00 | 2020-09-20 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 4: Haversham Bank - Reballast, Formaion -Trax - CAT12 - 130yds | 52 | 630 | 52 | 760 | 130
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 25 | 159796 | A31360 | 114603 | Bedford | 2 | 2100 | SPC1 | Weekend |  | 2020-09-19 23:00 | 2020-09-21 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail - Both rails - 13yds | 49 | 1684 | 49 | 1697 | 13 | C/C ref: PLS-2021-001 to enter 2021 workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 25 | 159796 | A55250 | 114603 | Bedford | 11 | 2100 | SPC1 | Weekend |  | 2020-09-19 23:00 | 2020-09-21 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 324yds | 49 | 1360 | 49 | 1684 | 324 | C/C ref: PLS-2021-001 to enter 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 25 | 157680 | A21140 | FD31203117 | Ninewar South 17/18 Falldown | 14 | 1100 | ECM8 | Weekend |  | 2020-09-20 00:01 | 2020-09-22 06:01 | 2 day(s) 06:00 Hrs | Ninewar South 17/18 Falldown | 25 | 1024 | 25 | 1321 | 297
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 25 | 157680 | A82000 | FD31203117 | Ninewar South 17/18 Falldown | 12 | 1100 | ECM8 | Weekend |  | 2020-09-20 00:01 | 2020-09-22 06:01 | 2 day(s) 06:00 Hrs | Ninewar South 17/18 Falldown | 25 | 1321 | 25 | 1542 | 221
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 26 | 156707 | A3170 | CM1033df3 | Waterloo Plat 9 | 11 | 3609 | BML1 | Weekend |  | 2020-09-26 01:00 | 2020-09-28 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 0 | 127 | 0 | 269 | 142
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 26 | 156707 | A4030 | CM1033df3 | Waterloo Plat 9 | 11 | 3609 | BML1 | Weekend |  | 2020-09-26 01:00 | 2020-09-28 04:00 | 2 day(s) 03:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 0 | 269 | 0 | 410 | 141
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 26 | 157045 | A2459620 | COT22800524 | Peak Forrest to Dove Holes | 11 | 1100 | CNB1 | Weekend |  | 2020-09-26 20:00 | 2020-09-27 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: Peak Forrest to Dove Holes - Rerail, Resleeper, Reballast - Trax - CAT11 - 376yds | 164 | 198 | 164 | 574 | 376
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 26 | 157046 | A347820 | 24100321 | Broadhurst Gardens | 14 | 2100 | MCJ1 | Weekend |  | 2020-09-26 22:00 | 2020-09-27 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Formation, Reballast, Resleeper, Rerail - Trax - CAT14 - 400yds | 203 | 900 | 203 | 1300 | 400
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 26 | 157046 | A353040 | 23100717s | Haversham Bank | 12 | 1100 | LEC1 | Weekend |  | 2020-09-26 22:00 | 2020-09-27 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 4: Haversham Bank - Reballast, Formaion -Trax - CAT12 - 130yds | 52 | 760 | 52 | 890 | 130
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 26 | 157680 | A17990 | 31201121 | Mount Alban South | 11 | 1100 | ECM8 | Weekend |  | 2020-09-27 00:01 | 2020-09-29 06:01 | 2 day(s) 06:00 Hrs | Mount Alban South | 44 | 100 | 44 | 808 | 708
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 27 | 157045 | A2459630 | COT22800524 | Peak Forrest to Dove Holes | 11 | 1100 | CNB1 | Weekend |  | 2020-10-03 20:00 | 2020-10-04 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: Peak Forrest to Dove Holes - Rerail, Resleeper, Reballast - Trax - CAT11 - 376yds | 164 | 574 | 164 | 950 | 376
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 27 | 157046 | A21820 | 23302899 | Harrow & Wealdstone | 11 | 1200 | LEC1 | Weekend |  | 2020-10-03 22:00 | 2020-10-04 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 5: Harrow & Wealdstone - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - CAT11 - 160yds | 11 | 272 | 11 | 432 | 160
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 27 | 157046 | A57880 | 24201512 | Wilnecote | 14 | 2100 | DBP1 | Weekend |  | 2020-10-03 22:00 | 2020-10-04 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Wilnecote - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 445yds | 25 | 1152 | 25 | 1270 | 445
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 27 | 157680 | A78950 | 31200921 | Towerglen | 14 | 1100 | ECM8 | Weekend |  | 2020-10-04 00:01 | 2020-10-05 08:01 | 1 day(s) 08:00 Hrs | Coburns Path up | 37 | 0 | 37 | 953 | 953
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 28 | 157045 | A2459730 | COT22302619 | Rainhill | 14 | 1100 | DSE | Weekend |  | 2020-10-10 20:00 | 2020-10-11 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Rainhill - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 320yds | 8 | 1660 | 9 | 220 | 320
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 28 | 157046 | A353000 | 23302899 | Harrow & Wealdstone | 11 | 1200 | LEC1 | Weekend |  | 2020-10-10 22:00 | 2020-10-11 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 5: Harrow & Wealdstone - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - CAT11 - 160yds | 11 | 432 | 11 | 592 | 160
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 29 | 157045 | A2460750 | COT22700523 | St Helens Station | 11 | 1100 | DSE | Weekend |  | 2020-10-17 20:00 | 2020-10-18 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: St Helens Station- Rerail, Resleeper, Reballast - Trax - CAT11 - 440yds | 11 | 1320 | 12 | 0 | 440
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 29 | 157046 | A352920 | 23501118s | Stowe Hill | 12 | 2100 | LEC1 | Weekend |  | 2020-10-17 22:00 | 2020-10-18 14:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 4: Stowe Hill - Reballast, Formaion -Trax - CAT12 - 162yds | 68 | 580 | 68 | 742 | 162
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 29 | 157046 | A353010 | 23302899 | Harrow & Wealdstone | 11 | 1200 | LEC1 | Weekend |  | 2020-10-17 22:00 | 2020-10-18 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 5: Harrow & Wealdstone - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - CAT11 - 161yds | 11 | 592 | 11 | 753 | 161
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 29 | 157680 | A80000 | 31200221 | Hairlaw South | 11 | 1100 | ECM8 | Weekend |  | 2020-10-18 00:01 | 2020-10-19 08:01 | 1 day(s) 08:00 Hrs | Douglas Bidge | 13 | 880 | 13 | 1320 | 440
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 29 | 157680 | A81050 | 31200317 | Velodrome 17/18 Falldown | 11 | 1100 | ECM8 | Weekend |  | 2020-10-18 00:01 | 2020-10-19 08:01 | 1 day(s) 08:00 Hrs | Douglas Bidge | 1 | 915 | 1 | 1272 | 357
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 30 | 157045 | A2456650 | COT22700819 | Hurst Hall | 14 | 1100 | DSE | Weekend |  | 2020-10-24 20:00 | 2020-10-25 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Hurst Hall - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 480yds | 20 | 1280 | 21 | 0 | 480
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 30 | 157046 | A353020 | 23302899 | Harrow & Wealdstone | 11 | 1200 | LEC1 | Weekend |  | 2020-10-24 22:00 | 2020-10-25 14:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 5: Harrow & Wealdstone - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - CAT11 - 161yds | 11 | 753 | 11 | 914 | 161
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 30 | 157046 | A54790 | 23200518 | Tamworth Station | 12 | 2100 | LEC2 | Weekend |  | 2020-10-24 22:00 | 2020-10-25 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Tamworth Station - Reballast, Formaion -Trax - CAT12 - 355yds | 110 | 5 | 110 | 360 | 355
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 30 | 157680 | A22190 | 31200321 | Spittal North | 11 | 1100 | ECM8 | Weekend |  | 2020-10-25 00:01 | 2020-10-26 08:01 | 1 day(s) 08:00 Hrs | Spittal North | 14 | 242 | 14 | 674 | 432
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 30 | 157680 | A84160 | FD31200516 | Musselburgh Station Up 17/18 Falldown | 11 | 1100 | ECM8 | Weekend |  | 2020-10-25 00:01 | 2020-10-26 08:01 | 1 day(s) 08:00 Hrs | Douglas Bidge | 5 | 223 | 5 | 430 | 207
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 31 | 159909 | G4T122170 | 42240617df3 | Gravesend to Higham (Down) | 2 | 2100 | HDR | Weekend |  | 2020-10-31 00:30 | 2020-11-02 04:30 | 2 day(s) 04:00 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 24 | 166 | 24 | 178 | 12 | KENT-1920-34 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 31 | 159909 | G4T122180 | 42240617df3 | Gravesend to Higham (Down) | 14 | 2100 | HDR | Weekend |  | 2020-10-31 00:30 | 2020-11-02 04:30 | 2 day(s) 04:00 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 24 | 178 | 24 | 600 | 422 | KENT-1920-34 | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 31 | 156707 | A19810 | 44201118 | Millbrook (departure road) | 11 | 3300 | BML2 | Weekend |  | 2020-10-31 01:00 | 2020-11-02 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 80 | 663 | 80 | 1053 | 390
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 31 | 156707 | A30330 | 44201118 | Millbrook (departure road) | 2 | 3300 | BML2 | Weekend |  | 2020-10-31 01:00 | 2020-11-02 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 80 | 1053 | 80 | 1452 | 399
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 31 | 157045 | A2452290 | 21101519 | Bootle Beck | 4 | 1100 | CBC1 | Weekend |  | 2020-10-31 20:00 | 2020-11-01 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 4: Bootle Beck - Rerail, Resleeper (Steel) - CAT04 - 1100yds | 50 | 452 | 50 | 1552 | 1100
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 31 | 157046 | A353060 | 23100717s | Haversham Bank | 12 | 1100 | LEC1 | Weekend |  | 2020-10-31 22:00 | 2020-11-01 14:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 4: Haversham Bank - Reballast, Formaion -Trax - CAT12 - 130yds | 52 | 890 | 52 | 1020 | 130
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 31 | 157046 | A314370 | 23100619 | COT The Locks | 14 | 1100 | HNR | Weekend |  | 2020-10-31 22:20 | 2020-11-02 02:20 | 1 day(s) 04:00 Hrs | CORE: 1of 1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - Cat14 - 260yds | 83 | 300 | 83 | 560 | 260
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 31 | 159796 | A33430 | 113223 | Sutton Bonnington | 14 | 1200 | SPC5 | Weekend |  | 2020-10-31 23:00 | 2020-11-02 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 281yds | 115 | 129 | 115 | 410 | 281 | C/C ref: PLS-2021-004 to enter 2021 workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 31 | 159796 | A34290 | 113223 | Sutton Bonnington | 2 | 1200 | SPC5 | Weekend |  | 2020-10-31 23:00 | 2020-11-02 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail - Both rails - 56yds | 115 | 18 | 115 | 74 | 56 | C/C ref: PLS-2021-004 to enter 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 31 | 157680 | A23050 | 31200321 | Spittal North | 11 | 1100 | ECM8 | Weekend |  | 2020-11-01 00:01 | 2020-11-02 08:01 | 1 day(s) 08:00 Hrs | Spittal North | 14 | 674 | 14 | 1107 | 433
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 31 | 157680 | A83130 | 31200217 | Croft & Rye Falldown | 11 | 2100 | ECM8 | Weekend |  | 2020-11-01 00:01 | 2020-11-02 08:01 | 1 day(s) 08:00 Hrs | Douglas Bidge | 1 | 139 | 1 | 344 | 205
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 32 | 156707 | A20850 | 44201910df1 | New Milton - Hinton Admiral | 11 | 1100 | BML2 | Weekend |  | 2020-11-07 01:00 | 2020-11-09 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 98 | 520 | 98 | 1176 | 656
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 32 | 157045 | A2452280 | 21101519 | Bootle Beck | 4 | 1100 | CBC1 | Weekend |  | 2020-11-07 20:00 | 2020-11-08 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 4: Bootle Beck - Rerail, Resleeper (Steel) - CAT04 - 1100yds | 50 | 1552 | 51 | 892 | 1100
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 32 | 157046 | A348860 | 23502399s | Holdenby Lodge | 14 | 2100 | HNR | Weekend |  | 2020-11-07 22:00 | 2020-11-08 14:00 | 0 day(s) 16:00 Hrs | CORE: 1of 1: Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 210yds | 70 | 1110 | 70 | 1320 | 210
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 32 | 157046 | A352960 | 23400319 | COT South Hampsted | 14 | 1100 | CWJ | Weekend |  | 2020-11-07 22:00 | 2020-11-08 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: COT South Hampsted - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 393yds | 2 | 1205 | 2 | 1598 | 393
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 32 | 159796 | A33440 | 113223 | Sutton Bonnington | 14 | 1200 | SPC5 | Weekend |  | 2020-11-07 23:00 | 2020-11-09 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 281yds | 115 | 410 | 115 | 691 | 281 | C/C ref: PLS-2021-004 to enter 2021 workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 32 | 159796 | A55260 | 113223 | Sutton Bonnington | 2 | 1200 | SPC5 | Weekend |  | 2020-11-07 23:00 | 2020-11-09 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail - Both rails - 55yds | 115 | 74 | 115 | 129 | 55 | C/C ref: PLS-2021-004 to enter 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 32 | 157680 | A22200 | 31200321 | Spittal North | 11 | 1100 | ECM8 | Weekend |  | 2020-11-08 00:01 | 2020-11-09 08:01 | 1 day(s) 08:00 Hrs | Spittal North | 14 | 1107 | 14 | 1540 | 433
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 33 | 159909 | G4T123020 | 42240617df3 | Gravesend to Higham (Down) | 2 | 2100 | HDR | Weekend |  | 2020-11-14 00:30 | 2020-11-16 04:30 | 2 day(s) 04:00 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 24 | 1072 | 24 | 1084 | 12 | KENT-1920-34 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 33 | 159909 | G4T123100 | 42240617df3 | Gravesend to Higham (Down) | 14 | 2100 | HDR | Weekend |  | 2020-11-14 00:30 | 2020-11-16 04:30 | 2 day(s) 04:00 Hrs | CORE: 2/2 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 24 | 600 | 24 | 1072 | 472 | KENT-1920-34 | APC
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 33 | 156707 | A14610 | 44501415 | Dunbridge 2 | 11 | 2100 | RTJ2 | Weekend |  | 2020-11-14 01:00 | 2020-11-16 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 84 | 440 | 85 | 1 | 1321
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 33 | 157045 | A30890 | 21101519 | Bootle Beck | 4 | 1100 | CBC1 | Weekend |  | 2020-11-14 20:00 | 2020-11-15 04:00 | 0 day(s) 08:00 Hrs | CORE: 3 of 4: Bootle Beck - Rerail, Resleeper (Steel) - CAT04 - 928yds | 51 | 892 | 52 | 60 | 928
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 33 | 157046 | A354210 | 23303020 | Norcott Hill | 14 | 1100 | LEC1 | Weekend |  | 2020-11-14 22:00 | 2020-11-15 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: Formation, Reballast, Resleeper, Rerail - Trax - CAT14 - 156yds | 29 | 1380 | 29 | 1536 | 156
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 33 | 157046 | A56850 | 23270613 | Barnacle | 14 | 1200 | LEC2 | Weekend |  | 2020-11-14 22:00 | 2020-11-15 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 7: Barnacle - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 140yds | 91 | 340 | 91 | 480 | 140
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 33 | 159796 | A55270 | 113223 | Sutton Bonnington | 14 | 1200 | SPC5 | Weekend |  | 2020-11-14 23:00 | 2020-11-16 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 280yds | 115 | 691 | 115 | 971 | 280 | C/C ref: PLS-2021-004 to enter 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 33 | 157680 | A30590 | FD31101019 | Kippenross Tunnel Dn Falldown | 7 | 2100 | SCM3 | Weekend |  | 2020-11-15 00:01 | 2020-11-16 05:01 | 1 day(s) 05:00 Hrs | Kippenross Tunnel Down Falldown | 122 | 880 | 122 | 1106 | 226
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 33 | 157680 | A58980 | 31500621 | Longforgan Level Crossing | 11 | 2100 | SCM5 | Weekend |  | 2020-11-15 00:01 | 2020-11-16 05:01 | 1 day(s) 05:00 Hrs | Magazine Burn | 5 | 837 | 5 | 1109 | 272
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 34 | 157045 | A31820 | 21101519 | Bootle Beck | 4 | 1100 | CBC1 | Weekend |  | 2020-11-21 20:00 | 2020-11-22 12:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 4: Bootle Beck - Rerail, Resleeper (Steel) - CAT04 - 1437yds | 52 | 280 | 52 | 1717 | 1437
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 34 | 157046 | A347630 | 23270613 | Barnacle | 14 | 1200 | LEC2 | Weekend |  | 2020-11-21 22:00 | 2020-11-22 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 7: Barnacle - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 140yds | 91 | 480 | 91 | 620 | 140
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 34 | 157046 | A355070 | 23303020 | Norcott Hill | 14 | 1100 | LEC1 | Weekend |  | 2020-11-21 22:00 | 2020-11-22 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: Formation, Reballast, Resleeper, Rerail - Trax - CAT14 - 156yds | 29 | 1536 | 29 | 1692 | 156
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 34 | 159796 | A55280 | 113223 | Sutton Bonnington | 14 | 1200 | SPC5 | Weekend |  | 2020-11-21 23:00 | 2020-11-23 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 280yds | 115 | 971 | 115 | 1251 | 280 | C/C ref: PLS-2021-004 to enter 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 34 | 157680 | A28490 | FD90101 | Dunblane Down 17/18 Falldown | 11 | 2100 | SCM3 | Weekend |  | 2020-11-22 00:01 | 2020-11-23 05:01 | 1 day(s) 05:00 Hrs | Dunblane Down 17/18 Falldown | 123 | 740 | 123 | 1032 | 292
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 35 | 157045 | A9410 | COT21300120 | Leagate | 4 | 1100 | CBC3 | Weekend |  | 2020-11-28 20:00 | 2020-11-29 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Leagate - Rerail, Resleeper (Steel) - CAT04 - 1027yds | 12 | 1393 | 13 | 660 | 1027
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 35 | 157046 | A347640 | 23270613 | Barnacle | 14 | 1200 | LEC2 | Weekend |  | 2020-11-28 22:00 | 2020-11-29 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 7: Barnacle - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 140yds | 91 | 620 | 91 | 760 | 140
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 35 | 157046 | A353030 | 23302899 | Harrow & Wealdstone | 11 | 1200 | LEC1 | Weekend |  | 2020-11-28 22:00 | 2020-11-29 14:00 | 0 day(s) 16:00 Hrs | CORE: 5 of 5: Harrow & Wealdstone - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - CAT11 - 161yds | 11 | 914 | 11 | 1075 | 161
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 35 | 159796 | A55290 | 113223 | Sutton Bonnington | 14 | 1200 | SPC5 | Weekend |  | 2020-11-28 23:00 | 2020-11-30 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 14 - Formation, Reballast, Resleeper, Rerail - Trax - 280yds | 115 | 1251 | 115 | 1531 | 280 | C/C ref: PLS-2021-004 to enter 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 35 | 157680 | A26390 | FD31201112 | Broomhouse MRC 12/13 Falldown | 11 | 2100 | EGM1 | Weekend |  | 2020-11-29 00:01 | 2020-11-30 05:01 | 1 day(s) 05:00 Hrs | Broomhouse MRC 12/13 Falldown | 43 | 826 | 43 | 1275 | 449
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 35 | 157680 | A31640 | FD31500414 | Drumallan Falldown | 16 | 2100 | SCM4 | Weekend |  | 2020-11-29 00:01 | 2020-12-01 06:01 | 2 day(s) 06:00 Hrs | Drumallan Falldown | 127 | 1299 | 128 | 468 | 929
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 35 | 156707 | A10450 | 44601917 | Byfleet and New Haw Platform | 11 | 1200 | BML1 | Weekend |  | 2020-11-29 01:10 | 2020-11-30 04:00 | 1 day(s) 02:50 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 20 | 572 | 20 | 930 | 358
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 36 | 156707 | A12530 | 44201115sf1 | Dorchester South Platform 1 | 11 | 1100 | BML2 | Weekend |  | 2020-12-05 00:30 | 2020-12-07 05:00 | 2 day(s) 04:30 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 135 | 1387 | 135 | 1701 | 314
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 36 | 157045 | A14570 | COT22700124 | Hoscar | 11 | 2100 | WBS3 | Weekend |  | 2020-12-05 20:00 | 2020-12-06 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: Hoscar - Rerail, Resleeper, Reballast - Trax - CAT11 - 660yds | 25 | 351 | 25 | 1011 | 660
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 36 | 157046 | A347650 | 23270613 | Barnacle | 14 | 1200 | LEC2 | Weekend |  | 2020-12-05 22:00 | 2020-12-06 14:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 7: Barnacle - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 140yds | 91 | 760 | 91 | 900 | 140
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 36 | 159796 | A2190 | 112154 | Kingston | 11 | 2100 | SPC5 | Weekend |  | 2020-12-05 23:00 | 2020-12-07 15:00 | 1 day(s) 16:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 146yds | 117 | 1468 | 117 | 1614 | 146 | C/C ref: PLS-2021-010 to bring in to 2021 workbank
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 36 | 159796 | A3090 | 112154 | Kingston | 2 | 2100 | SPC5 | Weekend |  | 2020-12-05 23:00 | 2020-12-07 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 02 - Rerail - Both rails - 14yds | 117 | 1454 | 117 | 1468 | 14 | C/C ref: PLS-2021-010 to bring in to 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 36 | 157680 | A27440 | FD31501910 | Jeanfield Falldown | 12 | 1100 | SCM4 | Weekend |  | 2020-12-06 00:01 | 2020-12-07 05:01 | 1 day(s) 05:00 Hrs | Jeanfield Falldown | 140 | 140 | 140 | 303 | 163
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 36 | 157680 | A58880 | FD31501910 | Jeanfield Falldown | 14 | 1100 | SCM4 | Weekend |  | 2020-12-06 00:01 | 2020-12-07 05:01 | 1 day(s) 05:00 Hrs | Jeanfield Falldown | 140 | 303 | 140 | 424 | 121
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 36 | 157680 | A75800 | FD31201110 | Broxburn 15/16 shortfall | 11 | 2100 | EGM1 | Weekend |  | 2020-12-06 00:01 | 2020-12-07 05:01 | 1 day(s) 05:00 Hrs | Stanley Joiners Shop | 36 | 1343 | 37 | 1 | 418
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 37 | 156707 | A13570 | BK0037df3 | Dorchester South Platform 2 | 11 | 2100 | BML2 | Weekend |  | 2020-12-12 00:30 | 2020-12-14 05:00 | 2 day(s) 04:30 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 135 | 1322 | 135 | 1674 | 352
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 37 | 157045 | A2452430 | COT22700124 | Hoscar | 11 | 2100 | WBS3 | Weekend |  | 2020-12-12 20:00 | 2020-12-13 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: Hoscar - Rerail, Resleeper, Reballast - Trax - CAT11 - 660yds | 25 | 1011 | 25 | 1671 | 660
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 37 | 157046 | A347660 | 23270613 | Barnacle | 14 | 1200 | LEC2 | Weekend |  | 2020-12-12 22:00 | 2020-12-13 14:00 | 0 day(s) 16:00 Hrs | CORE: 5 of 7: Barnacle - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 140yds | 91 | 900 | 91 | 1040 | 140
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 37 | 159796 | A2200 | 112154 | Kingston | 11 | 2100 | SPC5 | Weekend |  | 2020-12-12 23:00 | 2020-12-14 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 146yds | 117 | 1614 | 118 | 0 | 146 | C/C ref: PLS-2021-010 to bring in to 2021 workbank
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 37 | 157680 | A25340 | 32402320 | Dumbarton East Station (2xUB) | 11 | 1100 | NEM6 | Weekend |  | 2020-12-13 00:01 | 2020-12-14 05:01 | 1 day(s) 05:00 Hrs | Dumbarton East Station (2xUB) | 115 | 1152 | 115 | 1262 | 110
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 37 | 157680 | A74750 | FD31400216 | Culloden | 7 | 2100 | HGL2 | Weekend |  | 2020-12-13 00:01 | 2020-12-15 06:01 | 2 day(s) 06:00 Hrs | Broomhouse MRC 12/13 Falldown | 111 | 890 | 111 | 1378 | 488
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 38 | 157045 | A2452440 | COT22700124 | Hoscar | 11 | 2100 | WBS3 | Weekend |  | 2020-12-19 20:00 | 2020-12-20 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: Hoscar - Rerail, Resleeper, Reballast - Trax - CAT11 - 489yds | 25 | 1671 | 26 | 400 | 489
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 38 | 157046 | A347670 | 23270613 | Barnacle | 14 | 1200 | LEC2 | Weekend |  | 2020-12-19 22:00 | 2020-12-20 14:00 | 0 day(s) 16:00 Hrs | CORE: 6 of 7: Barnacle - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 140yds | 91 | 1040 | 91 | 1180 | 140
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 38 | 157680 | A24290 | 31504518 | Stanley Joiners Shop | 7 | 1100 | HGL1 | Weekend |  | 2020-12-20 00:01 | 2020-12-22 06:01 | 2 day(s) 06:00 Hrs | Stanley Joiners Shop | 158 | 100 | 158 | 375 | 275
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 39 | 159909 | G4T121130 | 42400618df2 | Gravesend to Higham (Up) | 2 | 1100 | HDR | Weekend |  | 2020-12-24 23:30 | 2020-12-28 23:30 | 4 day(s) 00:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 155 | 24 | 170 | 15 | KENT-1920-33 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 39 | 159909 | G4T121970 | 42400618df2 | Gravesend to Higham (Up) | 14 | 1100 | HDR | Weekend |  | 2020-12-24 23:30 | 2020-12-28 23:30 | 4 day(s) 00:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 24 | 170 | 25 | 82 | 1672 | KENT-1920-33 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 39 | 159909 | G4T122050 | 42400618df2 | Gravesend to Higham (Up) | 2 | 1100 | HDR | Weekend |  | 2020-12-24 23:30 | 2020-12-28 23:30 | 4 day(s) 00:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 25 | 82 | 25 | 98 | 16 | KENT-1920-33 | APC
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 39 | 157045 | A24770 | 21500518 | Farrington Curve | 14 | 2100 | CGJ5 | Weekend |  | 2020-12-26 20:00 | 2020-12-27 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Farrington Curve - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 172yds | 18 | 1661 | 19 | 73 | 172
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 39 | 157046 | A347680 | 23270613 | Barnacle | 14 | 1200 | LEC2 | Weekend |  | 2020-12-26 22:00 | 2020-12-27 14:00 | 0 day(s) 16:00 Hrs | CORE: 7 of 7: Barnacle - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 140yds | 91 | 1180 | 91 | 1320 | 140
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 39 | 157046 | A354220 | 23303020 | Norcott Hill | 14 | 1100 | LEC1 | Weekend |  | 2020-12-26 22:00 | 2020-12-27 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: Formation, Reballast, Resleeper, Rerail - Trax - CAT14 - 156yds | 29 | 1692 | 30 | 88 | 156
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 39 | 157680 | A33740 | 31101618 | Norton Farm Bridge | 12 | 2100 | EGM1 | Weekend |  | 2020-12-27 00:01 | 2020-12-28 09:01 | 1 day(s) 09:00 Hrs | Norton Farm Bridge | 39 | 1309 | 39 | 1627 | 318
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 40 | 157046 | A15640 | 24100420 | Wembley Stadium | 14 | 2100 | NAJ1 | Weekend |  | 2021-01-02 22:00 | 2021-01-03 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 OF 1: Wembley Stadium - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 289yds | 4 | 1600 | 5 | 129 | 289
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 40 | 157680 | A34790 | FD32101211 | Cathcart Circle (Pollockshields East) | 11 | 1100 | CTC | Weekend |  | 2021-01-03 00:01 | 2021-01-06 06:01 | 3 day(s) 06:00 Hrs | Cathcart Circle (Pollockshaws East) | 0 | 54 | 0 | 665 | 611
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 41 | 157045 | A5330 | COT22500122 | Macclesfield South Dn | 12 | 2100 | CMD1 | Weekend |  | 2021-01-09 20:00 | 2021-01-10 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Macclesfield South Dn - Reballast, Formation - Trax - CAT12 - 370yds | 2 | 600 | 2 | 970 | 370
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 41 | 157046 | A31100 | 23100123 | Cheddington Up Fast | 12 | 1100 | LEC1 | Weekend |  | 2021-01-09 22:00 | 2021-01-10 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 5: Cheddington Up Fast - Reballast, Formation -Trax - CAT12 - 135yds | 35 | 1722 | 36 | 97 | 169
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 41 | 157680 | A36890 | 31501620 | Aberdeen Platform 6 South | 16 | 1100 | ECN5 | Weekend |  | 2021-01-10 00:01 | 2021-01-10 16:01 | 0 day(s) 16:00 Hrs | Aberdeen Platform 6 South | 240 | 1581 | 241 | 151 | 330
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 41 | 157680 | A37940 | FD32300916 | Ibrox Access East 16/17 Falldown | 14 | 2100 | AYR1 | Weekend |  | 2021-01-10 00:01 | 2021-01-10 16:01 | 0 day(s) 16:00 Hrs | Ibrox Access East 16/17 Falldown | 1 | 1327 | 2 | 228 | 661
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 41 | 157680 | A38990 | 31501520 | Aberdeen Platform 6 North | 16 | 1100 | ANI1 | Weekend |  | 2021-01-10 00:01 | 2021-01-11 05:01 | 1 day(s) 05:00 Hrs | Aberdeen Platform 6 North | 0 | 42 | 0 | 314 | 272
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 41 | 156707 | A8370 | 44601913sf1 | Brookwood Platform 2 | 11 | 2200 | BML1 | Weekend |  | 2021-01-10 01:10 | 2021-01-11 04:00 | 1 day(s) 02:50 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 27 | 1598 | 28 | 172 | 334
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 42 | 157045 | A2452340 | COT22500122 | Macclesfield South Dn | 12 | 2100 | CMD1 | Weekend |  | 2021-01-16 20:00 | 2021-01-17 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Macclesfield South Dn - Reballast, Formation - Trax - CAT12 - 370yds | 2 | 970 | 2 | 1340 | 370
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 42 | 157046 | A22850 | 23100821 | Cheddington Down Fast | 12 | 2100 | LEC1 | Weekend |  | 2021-01-16 22:00 | 2021-01-17 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: Cheddington Down Fast - Reballast, Formaion -Trax - CAT12 - 500yds | 35 | 1580 | 36 | 320 | 500
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 42 | 157680 | A35840 | 31501420 | Aberdeen Platform 7 North | 16 | 2100 | ANI1 | Weekend |  | 2021-01-17 00:01 | 2021-01-18 05:01 | 1 day(s) 05:00 Hrs | Aberdeen Platform 7 North | 0 | 42 | 0 | 314 | 272
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 43 | 156707 | A15650 | 19578df5 | Esher DS | 11 | 2200 | BML1 | Weekend |  | 2021-01-23 01:10 | 2021-01-25 04:00 | 2 day(s) 02:50 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 13 | 1746 | 14 | 952 | 966
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 43 | 157045 | A6350 | COT22500319 | North Road North | 12 | 1100 | CMD1 | Weekend |  | 2021-01-23 20:00 | 2021-01-24 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: North Road North - Reballast, Formation - Trax - CAT12 - 396yds | 2 | 1700 | 3 | 336 | 396
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 43 | 157046 | A18730 | HNR110645 | Duston West | 12 | 1100 | HNR | Weekend |  | 2021-01-23 22:00 | 2021-01-25 | 1 day(s) 02:00 Hrs | CORE: 1 OF 1: Duston West - Reballast, Formaion -Trax - CAT12 - 290yds | 64 | 1170 | 64 | 1460 | 290
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 43 | 157046 | A64060 | 24102319 | COT Walnut Tree Lane | 12 | 2100 | NAJ2 | Weekend |  | 2021-01-23 22:00 | 2021-01-24 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: COT Walnut Tree Lane - Reballast, Formaion -Trax - CAT12 -150yds | 26 | 400 | 26 | 550 | 150
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 43 | 157680 | A41090 | 32300117 | Cardonald 18/19 Falldown | 11 | 2100 | AYR1 | Weekend |  | 2021-01-24 00:01 | 2021-01-24 16:01 | 0 day(s) 16:00 Hrs | Cardonald 18/19 Falldown | 2 | 836 | 3 | 157 | 1081
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 43 | 157680 | A42140 | FD31500218A | Cocketty Up 17/18 Shortfall A | 14 | 1100 | ECN5 | Weekend |  | 2021-01-24 00:01 | 2021-01-25 05:01 | 1 day(s) 05:00 Hrs | Cocketty Up 17/18 Shortfall A | 215 | 372 | 215 | 504 | 132
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 44 | 157045 | A2452350 | COT22500319 | North Road North | 12 | 1100 | CMD1 | Weekend |  | 2021-01-30 20:00 | 2021-01-31 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: North Road North - Reballast, Formation - Trax - CAT12 - 397yds | 3 | 336 | 3 | 733 | 397
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 44 | 157046 | A352970 | 24102319 | COT Walnut Tree Lane | 12 | 2100 | NAJ2 | Weekend |  | 2021-01-30 22:00 | 2021-01-31 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: COT Walnut Tree Lane - Reballast, Formaion -Trax - CAT12 -150yds | 26 | 550 | 26 | 700 | 150
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 44 | 157046 | A352980 | 24102619 | COT Woodside Cottage Up | 12 | 1100 | NAJ3 | Weekend |  | 2021-01-30 22:00 | 2021-01-31 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: COT Woodside Cottage Up - Reballast, Formaion -Trax - CAT12 - 165yds | 2 | 1010 | 2 | 1175 | 165
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 44 | 157046 | A8430 | 24205019 | COT Coleshill Road | 14 | 1100 | NWO | Weekend |  | 2021-01-30 22:00 | 2021-01-31 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT Coleshill Road - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 695yds | 1 | 1065 | 2 | 0 | 695
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 44 | 157680 | A40040 | FD31500218B | Cocketty Up 17/18 Shortfall B | 14 | 1100 | ECN5 | Weekend |  | 2021-01-31 00:01 | 2021-02-01 05:01 | 1 day(s) 05:00 Hrs | Cocketty Up 17/18 Shortfall B | 215 | 1491 | 215 | 1756 | 265
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 45 | 156707 | A7330 | 44401313 | Bedhampton Drainage | 15b | 2100 | WPH2 | Weekend |  | 2021-02-06 00:45 | 2021-02-08 04:15 | 2 day(s) 03:30 Hrs | CORE: 1/1 PL Drainage - associated | 38 | 873 | 38 | 1134 | 261
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 45 | 157045 | A2452360 | COT22500319 | North Road North | 12 | 1100 | CMD1 | Weekend |  | 2021-02-06 20:00 | 2021-02-07 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: North Road North - Reballast, Formation - Trax - CAT12 - 397yds | 3 | 733 | 3 | 1130 | 397
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 45 | 157046 | A42430 | 23400419 | COT South Kenton | 14 | 2100 | CWJ | Weekend |  | 2021-02-06 22:00 | 2021-02-07 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: COT South Kenton - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 202yds | 9 | 150 | 9 | 352 | 202
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 45 | 157046 | A65090 | 24102019 | COT Lower Pollicott | 14 | 1200 | NAJ2 | Weekend |  | 2021-02-06 22:00 | 2021-02-07 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: COT Lower Pollicott - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 138yds | 33 | 675 | 33 | 813 | 138
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Amey | Peterborough | 20/21 | 45 | 159800 | A3270 | 121150 | Barnet Tunnel DS | 11 | 2200 | ECM1 | Weekend | W2020/0000000 | 2021-02-06 23:00 | 2021-02-08 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 356yds | 7 | 858 | 7 | 1214 | 356 | Change control ref: PLS-2021-019 to enter 20/21 workbank | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 45 | 157680 | A43190 | 31500816 | Letham Mill | 13 | 1100 | ECN4 | Weekend |  | 2021-02-07 00:01 | 2021-02-08 05:01 | 1 day(s) 05:00 Hrs | Letham Mill | 18 | 1138 | 18 | 1424 | 286
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 45 | 157680 | A44240 | FD31500816 | Letham Mill 17/18 Falldown | 14 | 1100 | ECN4 | Weekend |  | 2021-02-07 00:01 | 2021-02-08 05:01 | 1 day(s) 05:00 Hrs | Letham Mill 17/18 Falldown | 18 | 1424 | 18 | 1546 | 122
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 46 | 157045 | A2450270 | COT22600711 | Aintree | 11 | 1100 | SJO2 | Weekend |  | 2021-02-13 20:00 | 2021-02-15 | 1 day(s) 04:00 Hrs | CORE: 1 of 1: Cat11 - Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) - 660yds | 4 | 1320 | 5 | 220 | 660
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 46 | 157046 | A352950 | 24102019 | COT Lower Pollicott | 14 | 1200 | NAJ2 | Weekend |  | 2021-02-13 22:00 | 2021-02-14 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: COT Lower Pollicott - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 137yds | 33 | 813 | 33 | 950 | 137
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 46 | 157046 | A49640 | 24201412s | Baggeridge | 12 | 1100 | DBP1 | Weekend |  | 2021-02-13 22:00 | 2021-02-14 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Baggeridge - Reballast, Formaion -Trax - CAT12 - 735yds | 27 | 80 | 27 | 815 | 735
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | London North East | Amey | Peterborough | 20/21 | 46 | 159800 | A4130 | 121150 | Barnet Tunnel DS | 11 | 2200 | ECM1 | Weekend | W2020/0000000 | 2021-02-13 23:00 | 2021-02-15 05:00 | 1 day(s) 06:00 Hrs | CORE: Cat 11 - Reballast, Resleeper, Rerail - Trax - 356yds | 7 | 1214 | 7 | 1570 | 356 | Change control ref: PLS-2021-019 to enter 20/21 workbank | APC
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 46 | 157680 | A45100 | FD31500816 | Letham Mill 17/18 Falldown | 14 | 1100 | ECN4 | Weekend |  | 2021-02-14 00:01 | 2021-02-15 05:01 | 1 day(s) 05:00 Hrs | Letham Mill 17/18 Falldown | 18 | 1546 | 19 | 350 | 564
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 46 | 157680 | A46340 | 32100321 | Lochwinnoch Reserve | 14 | 1100 | AYR3 | Weekend |  | 2021-02-14 00:01 | 2021-02-15 05:01 | 1 day(s) 05:00 Hrs | Lochwinnoch Reserve | 14 | 100 | 14 | 800 | 700
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 47 | 156707 | A28130 | 44252510 | Wallers Ash Up Loop | 11 | 1500 | BML1 | Weekend |  | 2021-02-20 01:00 | 2021-02-22 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 60 | 452 | 60 | 1742 | 1290
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 47 | 157045 | A2452300 | 21500413 | Leyland 2 | 14 | 2100 | CGJ5 | Weekend |  | 2021-02-20 20:00 | 2021-02-21 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 5: Leyland 2 - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 132yds | 17 | 1100 | 17 | 1232 | 132
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 47 | 157046 | A25940 | 24200312 | Kingsbury Branch | 12 | 2100 | DBP1 | Weekend |  | 2021-02-20 22:00 | 2021-02-21 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Kingsbury Branch - Reballast, Formaion -Trax - CAT12 - 400yds | 28 | 830 | 28 | 1230 | 400
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 47 | 157046 | A347710 | 23100123 | Cheddington Up Fast | 12 | 1100 | LEC1 | Weekend |  | 2021-02-20 22:00 | 2021-02-21 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 5: Cheddington Up Fast - Reballast, Formation -Trax - CAT12 - 135yds | 36 | 97 | 36 | 232 | 169
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 47 | 157680 | A45290 | 31501719 | Lunan Bay Viaduct Up | 14 | 1100 | ECN4 | Weekend |  | 2021-02-21 00:01 | 2021-02-22 05:01 | 1 day(s) 05:00 Hrs | Lunan Bay Viaduct Up | 23 | 1756 | 24 | 220 | 224
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 48 | 157045 | A25790 | 21500413 | Leyland 2 | 14 | 2100 | CGJ5 | Weekend |  | 2021-02-27 20:00 | 2021-02-28 12:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 5: Leyland 2 - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 132yds | 17 | 1232 | 17 | 1364 | 132
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 48 | 157046 | A347700 | 23100123 | Cheddington Up Fast | 12 | 1100 | LEC1 | Weekend |  | 2021-02-27 22:00 | 2021-02-28 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 5: Cheddington Up Fast - Reballast, Formation -Trax - CAT12 - 135yds | 36 | 232 | 36 | 367 | 169
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 48 | 157046 | A52730 | 23502299 | Church Brampton | 14 | 2100 | HNR | Weekend |  | 2021-02-27 22:00 | 2021-02-28 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Church Brampton - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 186yds | 69 | 164 | 69 | 350 | 186
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 48 | 157680 | A47390 | 31501819 | Lunan Bay Viaduct Down | 14 | 2100 | ECN4 | Weekend |  | 2021-02-28 00:01 | 2021-03-01 05:01 | 1 day(s) 05:00 Hrs | Lunan Bay Viaduct Down | 24 | 15 | 24 | 220 | 205
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 48 | 157680 | A48440 | 32103417 | Dubbs Curve | 11 | 1100 | LGS1 | Weekend |  | 2021-02-28 00:01 | 2021-02-28 16:01 | 0 day(s) 16:00 Hrs | Dubbs Curve | 26 | 1200 | 26 | 1460 | 260
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A10550 | 52100120 | Churchdown | 11 | 1100 | BAG2 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 89 | 6 | 89 | 300 | 294
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A11590 | 51300611 | Denchworth | 12 | 1100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Formation - Trax Cat: 12 | 62 | 1100 | 63 | 704 | 1364
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A12630 | 51400312 | Dennings | 11 | 1100 | WEY | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 122 | 176 | 122 | 968 | 792
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A13670 | 51340210 | Didcot Plat 3 | 11 | 2200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 52 | 1438 | 53 | 261 | 583
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A14710 | 51320913 | Didcot West (Rerail) | 2 | 2100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 53 | 644 | 53 | 970 | 326
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A15750 | 52100311 | Droitwich | 4 | 2100 | OWW | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/2 Rerail, Resleeper (Steel) Cat: 04 | 125 | 1650 | 126 | 100 | 210
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A16610 | 52100311 | Droitwich | 14 | 2100 | OWW | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 2/2 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 126 | 100 | 126 | 303 | 203
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A16790 | 51400521 | East Chord Loop Up | 11 | 1100 | WYL | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 95 | 0 | 95 | 616 | 616
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A18870 | 52100220 | Frocester | 14 | 1100 | BGL2 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 103 | 195 | 103 | 660 | 465
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A19910 | 51210320 | Half Way House | 4 | 3100 | MWB | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1Resleeper, Rerail - Cat: 04 | 0 | 528 | 1 | 792 | 2024
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A20950 | 52240322 | Hallen Marsh | 2 | 1100 | AFR | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 118 | 0 | 118 | 389 | 389
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A2190 | 52140120 | Yarnton - Hanborough | 2 | 3100 | OWW | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 67 | 1650 | 69 | 660 | 2530
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A21990 | 52100611 | Hampton Lovett | 4 | 1100 | OWW | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail, Resleeper (Steel) Cat: 04 | 127 | 1210 | 128 | 550 | 1100
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A24070 | 51100510 | Hayes (Including Platform) | 11 | 2200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/3 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 10 | 1120 | 10 | 1500 | 380
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A24080 | 51100510 | Hayes (Including Platform) | 11 | 2200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 3/3 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 10 | 1742 | 11 | 220 | 238
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A24930 | 51100510 | Hayes (Including Platform) | 14 | 2200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 2/3 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 10 | 1500 | 10 | 1742 | 242
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A25110 | 51300411 | Hinksey South down | 11 | 2100 | DCL | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 61 | 1716 | 62 | 675 | 719
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A26150 | 52200520 | Long Ashton Up | 11 | 1100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 122 | 1041 | 123 | 77 | 796
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A27190 | 51232019 | Maidenhead viaduct island | 11 | 2200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 23 | 425 | 23 | 745 | 320
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A29270 | 51210220 | Marlow | 11 | 3100 | MWB | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 2 | 1056 | 2 | 1188 | 132
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A31350 | GW13529 | Paddington Line 4 | 14 | 3204 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 0 | 1286 | 0 | 1542 | 256
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A3270 | 51100116 | Acton Main Line Station UM | 14 | 1100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 4 | 242 | 4 | 616 | 374
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A33430 | 51220213 | Pangbourne Station | 11 | 1200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 41 | 547 | 41 | 1138 | 591
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A34470 | 51322218 | Radley Dn | 11 | 2100 | DCL | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 58 | 1120 | 58 | 1516 | 396
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A35510 | 51300417 | Radley Up | 11 | 1100 | DCL | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 58 | 645 | 58 | 900 | 255
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A36550 | 51301310 | Rushey Platt Down | 11 | 2100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 77 | 1128 | 78 | 154 | 786
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A37590 | 52201320 | Saltford Tunnel Dn | 11 | 2100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 111 | 1217 | 112 | 440 | 983
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A38630 | 51451117 | Somerton Ground Frame | 11 | 1100 | CCL | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 126 | 210 | 126 | 1210 | 1000
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A39670 | 51105012 | Southall UR (Rerail) | 2 | 1200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 9 | 770 | 9 | 1144 | 374
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A40710 | 52100420 | Stonehouse Down | 11 | 2100 | BGL2 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 102 | 102 | 102 | 285 | 183
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A4130 | 51100116 | Acton Main Line Station UM | 15a | 1100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 2/2 Drain (Associated with Track Renewal) Cat: 15A | 4 | 593 | 4 | 683 | 90
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A41750 | 52100320 | Stonehouse Up | 11 | 1100 | BGL2 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 102 | 106 | 102 | 283 | 177
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A42790 | 51330117 | Swindon East Down | 11 | 2100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 76 | 593 | 76 | 1408 | 815
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A43830 | 52140116 | The Cummins | 4 | 3100 | WAH | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail, Resleeper (Steel) Cat: 04 | 133 | 462 | 133 | 1672 | 1210
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A44870 | 51320613 | Wantage Road | 2 | 2100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 60 | 812 | 61 | 264 | 1212
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A45910 | 51130216 | West Drayton 1 | 11 | 1200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 12 | 902 | 12 | 1408 | 506
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A47990 | 51130116 | West Drayton (Middle Job) | 11 | 1200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 12 | 1584 | 13 | 68 | 244
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A49030 | 51110412 | West Drayton (Rerail) | 2 | 2200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 13 | 418 | 13 | 1430 | 1012
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A50070 | 51440711 | Westbury Avoider | 2 | 2100 | WES | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 94 | 1111 | 96 | 1661 | 4070
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A51110 | 52201019 | Westerleigh | 11 | 2100 | SWB | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Rerail, Resleeper(Trax) Cat11 | 106 | 132 | 106 | 836 | 704
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A52150 | 51182518 | Wharncliffe Viaduct Dn | 11 | 2100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 7 | 726 | 7 | 1276 | 550
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A53190 | 52240621 | WSM TO UPHILL JN RERAIL | 2 | 3100 | WSM | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat: 02 | 137 | 1289 | 139 | 0 | 2231
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A5350 | 51400311 | Brewham | 11 | 1100 | WEY | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 124 | 1100 | 124 | 1628 | 528
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A54230 | 51400621 | East Chord Loop Down | 9 | 2100 | WYL | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper- Trax Cat: 09 | 95 | 0 | 95 | 616 | 616
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A55180 | 51210220 | Marlow | 4 | 3100 | MWB | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Resleeper, Rerail - Cat 04 | 1 | 1396 | 2 | 1056 | 1420
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A55280 | 51400121 | Theale to Wigmore | 11 | 2100 | BHL | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/2 CW Rerail, Resleeper, Reballast-Trax | 41 | 60 | 41 | 910 | 850
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A56140 | 51400121 | Theale to Wigmore | 11 | 2100 | BHL | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 2/2 CW Rerail, Resleeper, Reballast-Trax | 41 | 910 | 42 | 0 | 850
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A56320 | 51225515 | Cookham straight towards Bourne End | 4 | 3100 | WBB | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW Rerail, Resleeper (Steel) | 27 | 574 | 27 | 1704 | 1130
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A57360 | 51225815 | Cookham | 11 | 3100 | WBB | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW Rerail, Resleeper, Reballast-Trax | 26 | 1740 | 27 | 594 | 614
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A58220 | 51225815 | Cookham | 15a | 3100 | WBB | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW Drainage Assiciated | 27 | 110 | 27 | 550 | 440
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A58400 | 51210212 | Reading West Station | 11 | 2100 | BKE | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW Rerail, Resleeper, Reballast-Trax | 36 | 1478 | 37 | 7 | 289
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A59440 | 51201111 | Reading West | 11 | 1100 | BKE | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW Rerail, Resleeper, Reballast-Trax | 37 | 250 | 37 | 1319 | 1069
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A60300 | 51201111 | Reading West | 14 | 1100 | BKE | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW Rerail, Resleeper, Reballast, Formation-Trax | 37 | 122 | 37 | 250 | 128
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A60480 | 51201511 | Reading West Down | 11 | 2100 | BKE | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW Rerail, Resleeper, Reballast-Trax | 37 | 250 | 37 | 1257 | 1007
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A61340 | 51201511 | Reading West Down | 14 | 2100 | BKE | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CWRerail, Resleeper, Reballast, Formation-Trax | 37 | 117 | 37 | 250 | 133
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A61430 | 52201019 | Westerleigh | 7 | 2100 | SWB | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast - Trax Cat07 | 106 | 836 | 106 | 1313 | 477
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A7430 | 51400411 | Bruton Down | 14 | 2100 | WEY | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 126 | 640 | 126 | 1140 | 500
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A8470 | 51383419dm | CHOLSEY Down Main Platform | 11 | 2100 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 48 | 722 | 48 | 891 | 169
Keyes, Mr Gordon | Plain Line | TRACK.PL | Western | Babcock Rail | Bristol East | 20/21 | 48 | 157072 | A9510 | 51383619 imt | Cholsey UR (Including Platform) | 11 | 1200 | MLN1 | Weekend |  | 2021-03-06 01:00 | 2021-03-06 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 48 | 650 | 48 | 1026 | 376
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 49 | 157045 | A2452310 | 21500413 | Leyland 2 | 14 | 2100 | CGJ5 | Weekend |  | 2021-03-06 20:00 | 2021-03-07 12:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 5: Leyland 2 - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 132yds | 17 | 1364 | 17 | 1496 | 132
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 49 | 157046 | A347690 | 23100821 | Cheddington Down Fast | 12 | 2100 | LEC1 | Weekend |  | 2021-03-06 22:00 | 2021-03-07 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: Cheddington Down Fast - Reballast, Formaion -Trax - CAT12 - 149yds | 36 | 320 | 36 | 469 | 149
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 49 | 157046 | A347720 | 23100123 | Cheddington Up Fast | 12 | 1100 | LEC1 | Weekend |  | 2021-03-06 22:00 | 2021-03-07 14:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 5: Cheddington Up Fast - Reballast, Formation -Trax - CAT12 - 135yds | 36 | 367 | 36 | 502 | 169
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 49 | 157680 | A49490 | FD31303010 | OB55 Chalmers 09/10 Falldown | 11 | 1100 | ECN2 | Weekend |  | 2021-03-07 00:01 | 2021-03-08 05:01 | 1 day(s) 05:00 Hrs | OB55 Chalmers 09/10 Falldown | 18 | 1470 | 19 | 110 | 400
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 49 | 157680 | A50540 | 32103317 | Kilwinning Platform 2 | 12 | 2100 | LGS1 | Weekend |  | 2021-03-07 00:01 | 2021-03-08 05:01 | 1 day(s) 05:00 Hrs | Kilwinning Platform 2 | 25 | 1630 | 26 | 125 | 255
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 50 | 156707 | A6290 | HV0035df6 | Bedhampton 1 | 14 | 2100 | WPH2 | Weekend |  | 2021-03-13 00:45 | 2021-03-15 04:15 | 2 day(s) 03:30 Hrs | CORE: 1/2 Formation, Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 14 | 38 | 119 | 38 | 836 | 717
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 50 | 156707 | A7150 | HV0035df6 | Bedhampton 1 | 11 | 2100 | WPH2 | Weekend |  | 2021-03-13 00:45 | 2021-03-15 04:15 | 2 day(s) 03:30 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 38 | 836 | 38 | 1295 | 459
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 50 | 157045 | A2452320 | 21500413 | Leyland 2 | 14 | 2100 | CGJ5 | Weekend |  | 2021-03-13 20:00 | 2021-03-14 12:00 | 0 day(s) 16:00 Hrs | CORE: 4 of 5: Leyland 2 - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 132yds | 17 | 1496 | 17 | 1628 | 132
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 50 | 157046 | A352930 | 23100123 | Cheddington Up Fast | 12 | 1100 | LEC1 | Weekend |  | 2021-03-13 22:00 | 2021-03-14 14:00 | 0 day(s) 16:00 Hrs | CORE: 5 of 5: Cheddington Up Fast - Reballast, Formation -Trax - CAT12 - 135yds | 36 | 502 | 36 | 637 | 169
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 50 | 157046 | A58910 | 23277213s | Atherstone | 14 | 1200 | LEC2 | Weekend |  | 2021-03-13 22:00 | 2021-03-14 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: Atherstone - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 146yds | 101 | 700 | 101 | 846 | 146
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 50 | 157680 | A51590 | 32100917A | Ayr Station Platform 4A | 11 | 2100 | AYR6 | Weekend |  | 2021-03-14 00:01 | 2021-03-15 05:01 | 1 day(s) 05:00 Hrs | Ayr Station Platform 4A | 40 | 911 | 40 | 1078 | 167
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 50 | 157680 | A53690 | 32100917B | Ayr Station Platform 4B | 11 | 2100 | STR1 | Weekend |  | 2021-03-14 00:01 | 2021-03-15 05:01 | 1 day(s) 05:00 Hrs | Ayr Station Platform 4B | 40 | 1078 | 40 | 1230 | 152
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 50 | 157680 | A54740 | FD100118 | Haymarket Platform 2 - 12/12 Shortfall | 11 | 2100 | ECN2 | Weekend |  | 2021-03-14 00:01 | 2021-03-15 05:01 | 1 day(s) 05:00 Hrs | Haymarket Platform 2 - 12/13 Shortfall | 1 | 423 | 1 | 669 | 246
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | A1000 | 42300116 | Kearsney (Down) | 14 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 75 | 306 | 75 | 440 | 134 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T10270 | 42200120 | Lee Spur (Up) | 11 | 1100 | LEE | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 0 | 13 | 0 | 638 | 625 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T1090 | 42400512sf1 | New Cross (Down Fast) | 11 | 2100 | XTD | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 1393 | 5 | 223 | 590 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T11290 | 42200220 | Lee Spur (Down) | 11 | 2100 | LEE | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 0 | 0 | 0 | 638 | 638 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T12310 | 42300116 | Kearsney (Down) | 14 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 74 | 880 | 75 | 295 | 1175 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123120 | 42500120 | Wheeler Street Tnl Down to 43Pts | 2 | 2100 | SBJ | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 40 | 333 | 40 | 339 | 6 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123130 | 42300420 | Shepherdswell (Down) | 2 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 70 | 1082 | 70 | 1098 | 16 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123140 | 42500220 | Penge Tunnel (Up) | 2 | 1100 | VIR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rail Cat:02 | 5 | 1109 | 5 | 1120 | 11 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123150 | 42500320 | Denmark Hill to Shepards Lane Jcn Up 1 | 2 | 1100 | ATL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Re-rail Both Rails Cat: 02 | 4 | 623 | 4 | 631 | 8 | KENT-2021-17 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123160 | 42500320 | Denmark Hill to Shepards Lane Jcn Up 1 | 2 | 1100 | ATL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Re-rail Both Rails Cat: 02 | 4 | 1430 | 4 | 1438 | 8 | KENT-2021-17 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123180 | 42500420 | Denmark Hill to Shepards Lane Jcn Up 2 | 2 | 1100 | ATL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail Both Rails Cat:02 | 4 | 1239 | 5 | 1232 | 7 | KENT-2021-20 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123190 | 42500719 | Bromley South (Down Fast) | 2 | 2100 | VIR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail Both Rails Cat:02 | 10 | 1726 | 10 | 1736 | 10 | KENT-2021-19 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123200 | 42500719 | Bromley South (Down Fast) | 2 | 2100 | VIR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail Both Rails Cat:02 | 11 | 881 | 11 | 891 | 10 | KENT-2021-19 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123210 | 42400120 | South Bermondsey 2 (Down) | 2 | 2100 | BTH1 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail both Rails | 2 | 68 | 2 | 74 | 6 | KENT-2021-21
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123220 | 42400120 | South Bermondsey 2 (Down) | 2 | 2100 | BTH1 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail both Rails | 2 | 362 | 2 | 373 | 11 | KENT-2021-21
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T123320 | 42200715 | Lewisham to Blackheath Down | 11 | 2100 | BEX | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 6 | 275 | 6 | 1408 | 1133 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T124320 | 42300513 | Longfield to Meopham Down | 11 | 2100 | VIR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 24 | 1144 | 25 | 770 | 1386 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T13220 | 42300116 | Kearsney (Down) | 2 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 74 | 876 | 74 | 880 | 13 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T13230 | 42300116 | Kearsney (Down) | 2 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 75 | 295 | 75 | 306 | 11 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T13330 | 42600220 | Hastings Tunnel (Up) | 14 | 1100 | TTH | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 61 | 1088 | 61 | 1508 | 420 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T14350 | 42501113sf1 | Grove Tunnel to Crofton Rd Jcn (sf) Dn | 15ba | 2100 | ATL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Drainage Unassociated Cat:15ba | 3 | 1664 | 4 | 152 | 248 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T15370 | 42300220 | Grove Ferry (Down) | 9 | 2100 | ACR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper - Trax (all non steel sleeper types) Cat:09 | 76 | 450 | 76 | 1540 | 1090 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T16390 | 42300120 | Grove Ferry (Up) | 9 | 1100 | ACR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper - Trax (all non steel sleeper types) Cat:09 | 76 | 450 | 76 | 1540 | 1090 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T17410 | 42500420 | Denmark Hill to Shepards Lane Jcn Up 2 | 11 | 1100 | ATL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 1752 | 5 | 1232 | 1240 | KENT-2021-20 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T18430 | 42500320 | Denmark Hill to Shepards Lane Jcn Up 1 | 11 | 1100 | ATL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 631 | 4 | 1430 | 799 | KENT-2021-17 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T19450 | 42300520 | Buckland Jcn to Charlton Tunnel (Up) | 11 | 1100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 76 | 620 | 76 | 1131 | 511 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T2000 | 42400512sf1 | New Cross (Down Fast) | 2 | 2100 | XTD | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 4 | 1390 | 4 | 1393 | 3 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T2010 | 42400512sf1 | New Cross (Down Fast) | 2 | 2100 | XTD | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 5 | 223 | 5 | 234 | 11 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T20470 | 42300620 | Buckland Jcn to Charlton Tunnel (Down) | 11 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 76 | 20 | 76 | 540 | 520 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T2110 | 42500120 | Wheeler Street Tnl Down to 43Pts | 14 | 2100 | SBJ | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 40 | 339 | 40 | 575 | 236 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T21490 | 42500719 | Bromley South (Down Fast) | 11 | 2100 | VIR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 10 | 1736 | 11 | 881 | 905 | KENT-2021-19 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22400 | 42300116 | Kearsney (Down) | 2 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 75 | 440 | 75 | 456 | 16 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22410 | 42600220 | Hastings Tunnel (Up) | 2 | 1100 | TTH | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 61 | 1083 | 61 | 1088 | 5 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22420 | 42600220 | Hastings Tunnel (Up) | 15aa | 1100 | TTH | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Drainage Associated Cat:15aa | 61 | 1126 | 61 | 1498 | 372 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22430 | 42600220 | Hastings Tunnel (Up) | 2 | 1100 | TTH | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 61 | 1508 | 61 | 1513 | 5 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22440 | 42300120 | Grove Ferry (Up) | 2 | 1100 | ACR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 76 | 438 | 76 | 458 | 20 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22450 | 42300120 | Grove Ferry (Up) | 2 | 1100 | ACR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 76 | 1540 | 76 | 1560 | 20 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22460 | 42300220 | Grove Ferry (Down) | 2 | 2100 | ACR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 76 | 438 | 76 | 458 | 20 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22470 | 42300220 | Grove Ferry (Down) | 2 | 2100 | ACR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 76 | 1540 | 76 | 1560 | 20 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22480 | 42600214sf1 | Whatlington (Up) | 2 | 1100 | TTH | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 53 | 1390 | 53 | 1405 | 15 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22490 | 42600214sf1 | Whatlington (Up) | 2 | 1100 | TTH | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 54 | 247 | 54 | 262 | 15 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22500 | 42300520 | Buckland Jcn to Charlton Tunnel (Up) | 11 | 1100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 76 | 1142 | 76 | 1419 | 277 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22510 | 42300520 | Buckland Jcn to Charlton Tunnel (Up) | 16 | 1100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Resleeper, Rerail - Scarify/Skim (all non steel sleeper types) Cat:16 | 76 | 1131 | 76 | 1142 | 11 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22520 | 42300520 | Buckland Jcn to Charlton Tunnel (Up) | 2 | 1100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 76 | 1419 | 76 | 1430 | 11 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22530 | 42300620 | Buckland Jcn to Charlton Tunnel (Down) | 11 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 76 | 622 | 76 | 1131 | 509 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22540 | 42300620 | Buckland Jcn to Charlton Tunnel (Down) | 11 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 76 | 1142 | 76 | 1417 | 275 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22550 | 42300620 | Buckland Jcn to Charlton Tunnel (Down) | 16 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Resleeper, Rerail - Scarify/Skim (all non steel sleeper types) Cat:16 | 76 | 1131 | 76 | 1142 | 11 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22560 | 42300620 | Buckland Jcn to Charlton Tunnel (Down) | 2 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 76 | 10 | 76 | 20 | 10 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T22570 | 42300620 | Buckland Jcn to Charlton Tunnel (Down) | 2 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 76 | 1417 | 76 | 1427 | 10 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T3130 | 42600214sf1 | Whatlington (Up) | 14 | 1100 | TTH | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 53 | 1405 | 54 | 247 | 602 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T4150 | 42600120 | West St Leonards 6ft Drain | 15ba | 1100 | TTH | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Drainage Unassociated Cat:15ba | 60 | 1203 | 60 | 1435 | 232 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T5170 | 42400120 | South Bermondsey 2 (Down) | 11 | 2100 | BTH1 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 2 | 74 | 2 | 362 | 288 | KENT-2021-21 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T6190 | 42300420 | Shepherdswell (Down) | 11 | 2100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 70 | 1098 | 71 | 848 | 1510 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T7210 | 42500519 | Shepherds Lane Jcn to Clapham High Street (Up) | 11 | 1100 | ATL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 5 | 1489 | 6 | 585 | 856 | KENT-2021-16 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T8230 | 42300720 | Selling (Up) | 11 | 1100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 54 | 1342 | 55 | 198 | 616 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T9140 | 42300720 | Selling (Up) | 2 | 1100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 54 | 1327 | 54 | 1342 | 15 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T9150 | 42300720 | Selling (Up) | 2 | 1100 | FDM | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 55 | 198 | 55 | 214 | 16 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Kent | Colas | Tonbridge | 20/21 | 51 | 159909 | G4T9250 | 42500220 | Penge Tunnel (Up) | 11 | 1100 | VIR | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 5 | 1120 | 7 | 171 | 2571 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T166980 | 43401013df1 | Patcham Tunnel Dn | 11 | 2100 | VTB3 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 47 | 1427 | 48 | 231 | 564 | TON-SUS-1819-03 | CR
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T167930 | 43401013df1 | Patcham Tunnel Dn | 2 | 2100 | VTB3 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 48 | 231 | 48 | 248 | 17 | TON-SUS-1819-03 | CR
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T167940 | 43401013df1 | Patcham Tunnel Dn | 2 | 2100 | VTB3 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 47 | 1412 | 47 | 1427 | 15 | TON-SUS-1819-03 | CR
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T168040 | 43400214sf1 | Balcombe Jcn to Balcome Tnl (UF) | 11 | 1100 | VTB3 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail, Resleeper Reballast - Trax Cat:11 | 31 | 1543 | 32 | 32 | 232 | SUS-2021-09 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T169060 | VC0213 | Battersea Pier to Stewarts Lane (UP) | 11 | 1100 | BSF | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 0 | 1637 | 1 | 439 | 562 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T170080 | 43200220 | Carshalton Beeches (Down) | 11 | 2100 | NFE | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 13 | 1320 | 13 | 1699 | 379 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T171100 | 43200120 | Carshalton Beeches (Up) | 11 | 1100 | NFE | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 13 | 1320 | 13 | 1696 | 376 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T172120 | 43400120 | Clayton Tunnel Down (Shortfall) | 11 | 2100 | VTB3 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 44 | 1700 | 45 | 1502 | 1562 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T173030 | 43400120 | Clayton Tunnel Down (Shortfall) | 2 | 2100 | VTB3 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 44 | 1684 | 44 | 1700 | 16 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T173040 | 43400120 | Clayton Tunnel Down (Shortfall) | 2 | 2100 | VTB3 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 45 | 1502 | 45 | 1518 | 16 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T173140 | 43100220 | East Croydon - South Croydon (UF) | 11 | 1100 | VTB2 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 10 | 1168 | 11 | 602 | 1194 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T174160 | 43100120 | Merstham Tunnel to M25 - (Up) | 14 | 1100 | RED2 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 20 | 275 | 20 | 663 | 388 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T175180 | 43100320 | Star Lane Sub to Quarry Tunnel (UF) | 11 | 1100 | VTB2 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 16 | 1028 | 17 | 149 | 881 | SUS-2021-08 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T176200 | 43100910df1 | West Brompton - Stamford Bridge (Up) | 14 | 1100 | WLL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 1 | 1551 | 2 | 1001 | 1210 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177110 | 43100910df1 | West Brompton - Stamford Bridge (Up) | 2 | 1100 | WLL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 1 | 1542 | 1 | 1551 | 9 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177120 | 43100910df1 | West Brompton - Stamford Bridge (Up) | 2 | 1100 | WLL | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 2 | 1001 | 2 | 1010 | 9 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177130 | 43100220 | East Croydon - South Croydon (UF) | 2 | 1100 | VTB2 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 11 | 602 | 11 | 622 | 20 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177140 | 43100120 | Merstham Tunnel to M25 - (Up) | 2 | 1100 | RED2 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 20 | 263 | 20 | 275 | 12 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177150 | 43100120 | Merstham Tunnel to M25 - (Up) | 2 | 1100 | RED2 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 20 | 663 | 20 | 679 | 16 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177160 | 43200120 | Carshalton Beeches (Up) | 2 | 1100 | NFE | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 13 | 1309 | 13 | 1320 | 11 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177170 | 43200120 | Carshalton Beeches (Up) | 2 | 1100 | NFE | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 13 | 1696 | 13 | 1709 | 13 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177180 | 43200220 | Carshalton Beeches (Down) | 2 | 2100 | NFE | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 13 | 1309 | 13 | 1320 | 11 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177190 | 43200220 | Carshalton Beeches (Down) | 2 | 2100 | NFE | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 13 | 1699 | 13 | 1710 | 11 | SUS-1819-71
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177200 | 43100320 | Star Lane Sub to Quarry Tunnel (UF) | 2 | 1100 | VTB2 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail Both Rails Cat:02 | 16 | 1012 | 16 | 1028 | 16 | SUS-2021-08 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177210 | 43100320 | Star Lane Sub to Quarry Tunnel (UF) | 2 | 1100 | VTB2 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail Both Rails Cat:02 | 17 | 149 | 17 | 166 | 17 | SUS-2021-08 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177220 | 43400214sf1 | Balcombe Jcn to Balcome Tnl (UF) | 2 | 1100 | VTB3 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail Both Rails Cat:02 | 31 | 1533 | 31 | 1548 | 15 | SUS-2021-09 | APC
Bradfield, Ms Hailey | Plain Line | TRACK.PL | Sussex | Colas | Tonbridge | 20/21 | 51 | 159911 | G4T177230 | 43400214sf1 | Balcombe Jcn to Balcome Tnl (UF) | 2 | 1100 | VTB3 | Weekend |  | 2021-03-20 01:00 | 2021-03-21 04:00 | 1 day(s) 03:00 Hrs | CORE: Rerail Both Rails Cat:02 | 32 | 20 | 32 | 35 | 15 | SUS-2021-09 | APC
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A15700 | 41501212 | Ilford Dn Main | 11 | 2100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 6 | 1078 | 7 | 440 | 1122
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A18820 | 41219720 | Ipswich London Road Up Main | 11 | 1100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 69 | 1272 | 70 | 387 | 875
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A27240 | SF09126sf3df1 | Billericay Down (20/21) | 11 | 2100 | SSV | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 24 | 974 | 24 | 1325 | 351
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A28280 | 41501612sf2 | Ingatestone - Church Land Dn (Shortfall) (20/21) | 2 | 2100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 674 | 24 | 683 | 9
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A30270 | 41501818 | Ilford Station Dn Electric | 2 | 2152 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 7 | 536 | 7 | 549 | 13 | Categories of work changed. CC ref EA-2021-53 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A30280 | 41501818 | Ilford Station Dn Electric | 2 | 2152 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 7 | 1203 | 7 | 1215 | 12 | Categories of work changed. CC ref EA-2021-53 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A30290 | 41501818 | Ilford Station Dn Electric | 15aa | 2152 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Track Drainage - Associated Renewal Cat:15aa | 7 | 661 | 7 | 784 | 123 | Categories of work changed. CC ref EA-2021-53 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A30300 | 41501818 | Ilford Station Dn Electric | 15ac | 2152 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Track Drainage - Associated New Build Cat:15ac | 7 | 784 | 7 | 982 | 198 | Categories of work changed. CC ref EA-2021-53 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A30400 | 41400218df2 | Woodbridge Down | 16 | 2100 | ESK |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail, Resleeper (Concrete Sleepers) Cat: 16 | 77 | 865 | 77 | 882 | 17 | Job added to 20/21 workbank. CC ref EA-2021-52 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A31350 | 41400218df2 | Woodbridge Down | 11 | 2100 | ESK |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail, Resleeper, Reballast - Trax Cat: 11 | 77 | 882 | 78 | 1310 | 2188 | Job added to 20/21 workbank. CC ref EA-2021-52 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A31360 | 41400218df2 | Woodbridge Down | 11 | 2100 | ESK |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail, Resleeper, Reballast - Trax (TRACKTEX) Cat: 11 (T) | 78 | 1310 | 78 | 1753 | 443 | Job added to 20/21 workbank. CC ref EA-2021-52 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A31370 | 41400218df2 | Woodbridge Down | 11 | 2100 | ESK |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail, Resleeper, Reballast - Trax Cat: 11 | 78 | 1753 | 79 | 122 | 129 | Job added to 20/21 workbank. CC ref EA-2021-52 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A31380 | 41400218df2 | Woodbridge Down | 2 | 2100 | ESK |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat: 02 | 79 | 122 | 79 | 124 | 2 | Job added to 20/21 workbank. CC ref EA-2021-52 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A32390 | 41400919df1 | Cantley 2 Down | 2 | 2100 | NOL |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat: 02 | 9 | 1540 | 9 | 1543 | 3 | Job added to 20/21 workbank. CC ref EA-2021-51 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A32400 | 41400919df1 | Cantley 2 Down | 11 | 2100 | NOL |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail, Resleeper, Reballast - Trax (TRACKTEX) Cat: 11 (T) | 9 | 1543 | 10 | 252 | 469 | Job added to 20/21 workbank. CC ref EA-2021-51 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A32420 | 41400919df1 | Cantley 2 Down | 2 | 2100 | NOL |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat: 02 | 10 | 252 | 10 | 257 | 5 | Job added to 20/21 workbank. CC ref EA-2021-51 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A33430 | 41200513sf2df2 | Claydon - Barham Down (Shortfall) | 11 | 2100 | LTN1 |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail, Resleeper, Reballast - Trax Cat: 11 | 73 | 1631 | 74 | 200 | 329 | Job added to 20/21 workbank. CC ref EA-2021-50 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A33460 | 41200513sf2df2 | Claydon - Barham Down (Shortfall) | 2 | 2100 | LTN1 |  |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat: 02 | 74 | 200 | 74 | 212 | 12 | Job added to 20/21 workbank. CC ref EA-2021-50 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | A33470 | 41418419 | Somerleyton 1 | 2 | 1100 | NOL | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat: 02 | 20 | 879 | 20 | 902 | 23 | Two separate Somerleyton jobs combined into a single work item. CC ref EA-2021-55 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T13120 | 41501818 | Ilford Station Dn Electric | 14 | 2152 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail, Resleeper, Reballat, Formation - Trax Cat:14 | 7 | 549 | 7 | 1203 | 654 | Categories of work changed. CC ref EA-2021-53 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T15260 | 41418419 | Somerleyton 1 | 11 | 1100 | NOL | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail, Resleeper, Reballast - Trax Cat:11 | 18 | 226 | 20 | 879 | 4173 | Two separate Somerleyton jobs combined into a single work item. CC ref EA-2021-55 refers
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T364800 | 41219720 | Ipswich London Road Up Main | 11 | 1100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 70 | 399 | 70 | 645 | 246
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T364810 | 41219720 | Ipswich London Road Up Main | 2 | 1100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 69 | 1270 | 69 | 1272 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T364820 | 41219720 | Ipswich London Road Up Main | 2 | 1100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 70 | 387 | 70 | 399 | 12
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T364830 | 41219720 | Ipswich London Road Up Main | 44A | 1100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Baseplate Changing Cat:02 | 70 | 387 | 70 | 399 | 12
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T364840 | 41219720 | Ipswich London Road Up Main | 2 | 1100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 70 | 645 | 70 | 654 | 9
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T7320 | SF09108DF1 | Rayleigh Bank Dn | 2 | 2100 | SSV | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 31 | 188 | 31 | 205 | 17
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T8270 | SF09108DF1 | Rayleigh Bank Dn | 2 | 2100 | SSV | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 31 | 1431 | 31 | 1550 | 119
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T8280 | SF09108DF1 | Rayleigh Bank Dn | 11 | 2100 | SSV | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 31 | 205 | 31 | 1431 | 1226
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T9350 | SF09126sf3df1 | Billericay Down (20/21) | 2 | 2100 | SSV | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 24 | 972 | 24 | 974 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T9370 | 41501612sf2 | Ingatestone - Church Land Dn (Shortfall) (20/21) | 2 | 2100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Rerail - Both Rails Cat:02 | 24 | 1148 | 24 | 1163 | 15
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 50 | 156209 | G4T9380 | 41501612sf2 | Ingatestone - Church Land Dn (Shortfall) (20/21) | 14 | 2100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1/1 Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 24 | 683 | 24 | 1148 | 465
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | A29320 | 41200120 | Alresford to Great Bentley Down | 14 | 2100 | COC | Weekend |  | 2021-03-20 01:00 | 2021-03-22 05:00 | 2 day(s) 04:00 Hrs | CORE: Formation, Resleeper, Reballast, Rerail - Trax | 59 | 1246 | 60 | 1644 | 2158
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T10580 | 41501613sf1df2 | Maryland to Forest Gate Dn | 11 | 2100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-22 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 1327 | 4 | 1586 | 259
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T11500 | 41501613sf1df2 | Maryland to Forest Gate Dn | 2 | 2100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-22 05:00 | 2 day(s) 04:00 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 4 | 1586 | 4 | 1605 | 19
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T11510 | 41501613sf1df2 | Maryland to Forest Gate Dn | 11 | 2100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-22 05:00 | 2 day(s) 04:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 5 | 304 | 5 | 836 | 532
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T11520 | 41501613sf1df2 | Maryland to Forest Gate Dn | 2 | 2100 | LTN1 | Weekend |  | 2021-03-20 01:00 | 2021-03-22 05:00 | 2 day(s) 04:00 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 5 | 288 | 5 | 304 | 16
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T11870 | 41100218df2 | West Ham Down | 2 | 2100 | FSS1 | Weekend |  | 2021-03-20 01:00 | 2021-03-24 05:00 | 4 day(s) 04:00 Hrs | CORE: 1/2 Rerail - Both Rails Cat:02 | 3 | 1736 | 3 | 1738 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T12800 | 41100218df2 | West Ham Down | 11 | 2100 | FSS1 | Weekend |  | 2021-03-20 01:00 | 2021-03-23 04:00 | 3 day(s) 03:00 Hrs | CORE: 2/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 4 | 383 | 4 | 789 | 406
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T12810 | 41100218df2 | West Ham Down | 2 | 2100 | FSS1 | Weekend |  | 2021-03-20 01:00 | 2021-03-23 04:00 | 3 day(s) 03:00 Hrs | CORE: 2/2 Rerail - Both Rails Cat:02 | 4 | 789 | 4 | 791 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T12910 | 41100218df2 | West Ham Down | 11 | 2100 | FSS1 | Weekend |  | 2021-03-20 01:00 | 2021-03-24 05:00 | 4 day(s) 04:00 Hrs | CORE: 1/2 Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 1738 | 4 | 383 | 405
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T364940 | 41410519 | Cantley 1 Up | 11 | 1100 | NOL | Weekend |  | 2021-03-20 01:00 | 2021-03-22 05:00 | 2 day(s) 04:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 9 | 1515 | 10 | 331 | 576
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T364950 | 41410519 | Cantley 1 Up | 4 | 1100 | NOL | Weekend |  | 2021-03-20 01:00 | 2021-03-22 05:00 | 2 day(s) 04:00 Hrs | CORE: Resleeper, Rerail - Steel Cat:04 | 8 | 1660 | 9 | 1515 | 1615
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T365800 | 41410519 | Cantley 1 Up | 2 | 1100 | NOL | Weekend |  | 2021-03-20 01:00 | 2021-03-22 05:00 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 8 | 1644 | 8 | 1660 | 16
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T365890 | 41410519 | Cantley 1 Up | 4 | 1100 | NOL | Weekend |  | 2021-03-20 01:00 | 2021-03-22 05:00 | 2 day(s) 04:00 Hrs | CORE: Resleeper, Rerail - Steel Cat:04 | 10 | 331 | 11 | 430 | 1859
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A10370 | Leominster | Leominster Platform | 12 | 2100 | SHL | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReBallast, Formation -Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A10550 | Pheasants | Pheasants Curve | 11 | 1100 | SWM2 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReRail, ReSleeper, ReBallast-Trax | 160 | 990 | 160 | 1718 | 728
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A10560 | Pheasants | Pheasants Curve | 11 | 1100 | SWM2 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A11410 | Pheasants | Pheasants Curve | 11 | 1100 | SWM2 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A11590 | Shotton | Shotton | 11 | 1100 | WDB1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReRail, ReSleeper, ReBallast-Trax | 11 | 880 | 13 | 0 | 2640
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A11600 | Shotton | Shotton | 11 | 1100 | WDB1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A12450 | Shotton | Shotton | 11 | 1100 | WDB1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A12630 | Gwersyllt | Gwersyllt | 11 | 2100 | WDB1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReRail, ReSleeper, ReBallast-Trax | 3 | 440 | 3 | 880 | 440
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A12640 | Gwersyllt | Gwersyllt | 11 | 2100 | WDB1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A13490 | Gwersyllt | Gwersyllt | 11 | 2100 | WDB1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A13670 | Wrexham | Wrexham Central | 11 | 3100 | WDB1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReRail, ReSleeper, ReBallast-Trax | 0 | 330 | 0 | 1320 | 990
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A13680 | Wrexham | Wrexham Central | 11 | 3100 | WDB1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A14530 | Wrexham | Wrexham Central | 11 | 3100 | WDB1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A2190 | 53100118 | Emergency Ramp | 14 | 2100 | BSW | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReRail, ReSleeper, ReBallast, Formation - Trax | 10 | 1210 | 11 | 30 | 580
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A2200 | 53100118 | Emergency Ramp | 14 | 2100 | BSW | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReRail, ReSleeper, ReBallast, Formation - Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A3090 | 53100118 | Emergency Ramp | 14 | 2100 | BSW | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReRail, ReSleeper, ReBallast, Formation - Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A3270 | 53171115 | Emergency Ramp1 | 14 | 1100 | BSW | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReRail, ReSleeper, ReBallast, Formation - Trax | 10 | 1580 | 11 | 220 | 400
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A3280 | 53171115 | Emergency Ramp1 | 14 | 1100 | BSW | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReRail, ReSleeper, ReBallast, Formation - Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A4130 | 53171115 | Emergency Ramp1 | 14 | 1100 | BSW | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReRail, ReSleeper, ReBallast, Formation - Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A4310 | Bangor | Bangor | 11 | 2100 | CNH1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReRail, ReSleeper, ReBallast-Trax | 243 | 440 | 243 | 1500 | 1060
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A4320 | Bangor | Bangor | 11 | 2100 | CNH1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A5170 | Bangor | Bangor | 11 | 2100 | CNH1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A5350 | Llandudno | Llandudno Jnc | 11 | 2100 | CNH3 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReRail, ReSleeper, ReBallast-Trax | 222 | 880 | 223 | 0 | 880
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A5360 | Llandudno | Llandudno Jnc | 11 | 2100 | CNH3 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A6210 | Llandudno | Llandudno Jnc | 11 | 2100 | CNH3 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReRail, ReSleeper, ReBallast-Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A6390 | Little Mill | Little Mill | 12 | 1100 | HNL1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReBallast, Formation -Trax | 30 | 1100 | 30 | 1320 | 220
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A6400 | Little Mill | Little Mill | 12 | 1100 | HNL1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReBallast, Formation -Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A7250 | Little Mill | Little Mill | 12 | 1100 | HNL1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReBallast, Formation -Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A7430 | Ivy House | Ivy House | 12 | 1100 | HNL1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReBallast, Formation -Trax | 14 | 1120 | 14 | 1430 | 310
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A7440 | Ivy House | Ivy House | 12 | 1100 | HNL1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReBallast, Formation -Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A8290 | Ivy House | Ivy House | 12 | 1100 | HNL1 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReBallast, Formation -Trax
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A8470 | 53500118 | Machy to Dovey Jn | 4 | 3100 | SBA2 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReRail, ReSleeper - Steel | 76 | 951 | 78 | 1320 | 3889
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A8480 | 53500118 | Machy to Dovey Jn | 4 | 3100 | SBA2 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReRail, ReSleeper - Steel
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A9330 | 53500118 | Machy to Dovey Jn | 4 | 3100 | SBA2 | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 2nd CW ReRail, ReSleeper - Steel
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A9510 | Leominster | Leominster Platform | 12 | 2100 | SHL | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 1st CW ReBallast, Formation -Trax | 38 | 660 | 38 | 910 | 250
Keyes, Mr Gordon | Plain Line | TRACK.PL | Wales | Babcock Rail | Newport | 20/21 | 50 | 159540 | A9520 | Leominster | Leominster Platform | 12 | 2100 | SHL | Weekend |  | 2021-03-20 01:00 | 2021-03-20 17:00 | 0 day(s) 16:00 Hrs | CORE: 3rd CW ReBallast, Formation -Trax
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T363690 | 41200611sf2df1 | Roots & Shoots Dn (Shortfall) | 14 | 2100 | LTN1 | Weekend |  | 2021-03-20 02:00 | 2021-03-21 04:30 | 1 day(s) 02:30 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 78 | 605 | 78 | 1035 | 430
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T300960 | 41200813sf1 | Manningtree (Shortfall) Dn | 11 | 2100 | LTN1 | Weekend |  | 2021-03-20 02:15 | 2021-03-22 04:00 | 2 day(s) 01:45 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 59 | 951 | 59 | 1401 | 450
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T10320 | 41100808df1 | East Ham Dn | 2 | 2100 | FSS1 | Weekend |  | 2021-03-20 02:25 | 2021-03-22 06:25 | 2 day(s) 04:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 6 | 777 | 6 | 796 | 19
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | Anglia | Colas | Ipswich | 20/21 | 51 | 156209 | G4T9480 | 41100808df1 | East Ham Dn | 11 | 2100 | FSS1 | Weekend |  | 2021-03-20 02:25 | 2021-03-22 06:25 | 2 day(s) 04:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 6 | 796 | 6 | 1679 | 883
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 51 | 157045 | A2452330 | 21500413 | Leyland 2 | 14 | 2100 | CGJ5 | Weekend |  | 2021-03-20 20:00 | 2021-03-21 12:00 | 0 day(s) 16:00 Hrs | CORE: 5 of 5: Leyland 2 - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 132yds | 17 | 1628 | 17 | 0 | 132
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 51 | 157046 | A347590 | 23277213s | Atherstone | 14 | 1200 | LEC2 | Weekend |  | 2021-03-20 22:00 | 2021-03-21 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 3: Atherstone - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 101 | 846 | 101 | 993 | 147
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 51 | 157046 | A45520 | 24100719 | COT Kingswood Lane | 14 | 2100 | NAJ3 | Weekend |  | 2021-03-20 22:00 | 2021-03-21 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 2: COT Kingswood Lane - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 100yds | 2 | 1000 | 2 | 1100 | 100
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 51 | 157680 | A55790 | 32405420 | Cranoch Wood | 4 | 3100 | WHL | Weekend |  | 2021-03-21 00:01 | 2021-03-23 06:01 | 2 day(s) 06:00 Hrs | Cranoch Wood | 52 | 1320 | 54 | 220 | 2420
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 51 | 156707 | A9410 | 44401315df1 | Buriton foot crossing | 11 | 1100 | WPH1 | Weekend |  | 2021-03-21 00:40 | 2021-03-22 04:45 | 1 day(s) 04:05 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 57 | 450 | 57 | 926 | 476
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 51 | 159796 | A159920 | 111319 | Stretton Up | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 51 | 159796 | A3280 | 111319 | Stretton Up | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
South, Mrs Amanda Jayne (Amanda) | Plain Line | TRACK.PL | East Midlands | Amey | Peterborough | 20/21 | 51 | 159796 | A4130 | 111319 | Stretton Up | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A130150 | 124048 | Tapton North DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A130160 | 124048 | Tapton North DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A131010 | 124048 | Tapton North DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A131190 | 124108 | Whittington DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A131200 | 124108 | Whittington DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A132050 | 124108 | Whittington DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A132230 | 124049 | Wreakes Lane - Bradway DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A132240 | 124049 | Wreakes Lane - Bradway DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A133090 | 124049 | Wreakes Lane - Bradway DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A133270 | 125171 | Skellow Jcn - Booths UWC UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A133280 | 125171 | Skellow Jcn - Booths UWC UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A134130 | 125171 | Skellow Jcn - Booths UWC UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A134310 | 135016SF | Mastermans UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A134320 | 135016SF | Mastermans UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A135170 | 135016SF | Mastermans UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A135350 | 124177 | Brancliffe DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A135360 | 124177 | Brancliffe DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A136210 | 124177 | Brancliffe DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A136390 | 138123 | Furnaceway Viaduct UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A136400 | 138123 | Furnaceway Viaduct UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A137250 | 138123 | Furnaceway Viaduct UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A138470 | 27058 | North Lincoln Jcn UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A138480 | 27058 | North Lincoln Jcn UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A139330 | 27058 | North Lincoln Jcn UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A139510 | 125263 | Balderton UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A139520 | 125263 | Balderton UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A140370 | 125263 | Balderton UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A141590 | 131021 | Chevington Dn | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A141600 | 131021 | Chevington Dn | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A142450 | 131021 | Chevington Dn | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A142630 | 138083 | Morpeth Station Up | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A142640 | 138083 | Morpeth Station Up | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A143490 | 138083 | Morpeth Station Up | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A156150 | 125192 | Thorne | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A156160 | 125192 | Thorne | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A157010 | 125192 | Thorne | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A157190 | 125094 | Kirk Sandall Station | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A157200 | 125094 | Kirk Sandall Station | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A158050 | 125094 | Kirk Sandall Station | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A158230 | 125038 | Ponton Yard | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A158240 | 125038 | Ponton Yard | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A159090 | 125038 | Ponton Yard | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A159270 | 125264 | Bullpit Lane DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A159280 | 125264 | Bullpit Lane DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A160130 | 125264 | Bullpit Lane DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A218550 | 125245 | Egmanton UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A218560 | 125245 | Egmanton UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A2190 | 125092 | Dock Hills DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A219410 | 125245 | Egmanton UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A2200 | 125092 | Dock Hills DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A220630 | 125026 | Eccles Yard | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A220640 | 125026 | Eccles Yard | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A221490 | 125026 | Eccles Yard | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A221670 | 131169 | Stockton DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A221680 | 131169 | Stockton DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A222530 | 131169 | Stockton DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A223750 | 131226 | Durham UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A223760 | 131226 | Durham UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A224610 | 131226 | Durham UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A224790 | 136055 | Shipley - Frizinghall DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A224800 | 136055 | Shipley - Frizinghall DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A225650 | 136055 | Shipley - Frizinghall DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A225830 | 134036 | Bempton | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A225840 | 134036 | Bempton | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A226690 | 134036 | Bempton | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A233110 | 134038 | Seadale UWC - Filey UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A233120 | 134038 | Seadale UWC - Filey UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A233970 | 134038 | Seadale UWC - Filey UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A234150 | 133044SF | Danby | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A234160 | 133044SF | Danby | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A235010 | 133044SF | Danby | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A235190 | 133062B | Great Ayton | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A235200 | 133062B | Great Ayton | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A236050 | 133062B | Great Ayton | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A236230 | 125265 | Botany Bay L.C. | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 200yds | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A237270 | 132144 | Severus Curve | 11 | 1100 | ECM5 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 1029yds | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A238310 | 125099 | Muskham Viaduct Dn | 11 | 2100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: CAT11: Rerail, Resleeper, reballast - Trax: 396yds | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A239350 | 131024 | Little Mill | 11 | 1100 | ECM7 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 205yds | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A246630 | 131028 | Belford | 11 | 2100 | ECM7 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: CAT11: Rerail, Resleeper, Reballast - Trax: 1510yds | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A247670 | 133002 | Haltwhistle | 11 | 1100 | NEC2 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: CA14: Rerail, Resleeper, Reballast, Formation: Trax: 481yds | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A248710 | 125101 | Muskham Viaduct Up | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: CAT11: Rerail, Resleeper, reballast - Trax: 443yds | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A30310 | 125093 | Dock Hills UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A30320 | 125093 | Dock Hills UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A3090 | 125092 | Dock Hills DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A31170 | 125093 | Dock Hills UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A31350 | 136168 | Wakefield Viaduct | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A31360 | 136168 | Wakefield Viaduct | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A32210 | 136168 | Wakefield Viaduct | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A33430 | 136247 | Ardsley DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A33440 | 136247 | Ardsley DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A34290 | 136247 | Ardsley DN | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A34470 | 136075SF | Sandal & Agbrigg UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A34480 | 136075SF | Sandal & Agbrigg UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A35330 | 136075SF | Sandal & Agbrigg UP | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A8470 | 135187 | Hull Paragon Platform 2 | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 1st CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A8480 | 135187 | Hull Paragon Platform 2 | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 3rd CW (insert description) | 0 | 0 | 0 | 0 | 0
Walker, Mr Lee | Plain Line | TRACK.PL | London North East | Amey | Doncaster | 20/21 | 51 | 159798 | A9330 | 135187 | Hull Paragon Platform 2 | 11 | 1100 | ECM1 | Weekend | W/2020/0000000 | 2021-03-22 | 2021-03-22 | 0 day(s) 00:00 Hrs | CORE: 2nd CW (insert description) | 0 | 0 | 0 | 0 | 0
Shirley, Mr Martin John | Plain Line | TRACK.PL | Wessex | Babcock Rail | Eastleigh | 20/21 | 52 | 156707 | A29170 | 44600618B | Walton on Thames | 11 | 1200 | BML1 | Weekend |  | 2021-03-27 01:00 | 2021-03-29 04:00 | 2 day(s) 03:00 Hrs | CORE: 1/1 Reballast, Resleeper, Rerail - Trax (all non-steel sleeper types) Cat: 11 | 17 | 277 | 17 | 1122 | 845
N/A | Plain Line | TRACK.PL | London North West | Amey | Preston | 20/21 | 52 | 157045 | A2452540 | 21502117 | Balshaw Lane Short Item | 14 | 1100 | CGJ5 | Weekend |  | 2021-03-27 20:00 | 2021-03-28 12:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 1: Balshaw Lane Short Item - Rerail, Resleeper, Reballast Formation (Trax) - CAT14 - 113yds | 13 | 1740 | 14 | 93 | 113
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 52 | 157046 | A347600 | 23277213s | Atherstone | 14 | 1200 | LEC2 | Weekend |  | 2021-03-27 22:00 | 2021-03-28 14:00 | 0 day(s) 16:00 Hrs | CORE: 3 of 3: Atherstone - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 147yds | 101 | 993 | 994 | 1140 | 147
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 52 | 157046 | A352940 | 24100719 | COT Kingswood Lane | 14 | 2100 | NAJ3 | Weekend |  | 2021-03-27 22:00 | 2021-03-28 14:00 | 0 day(s) 16:00 Hrs | CORE: 2 of 2: COT Kingswood Lane - Rerail, Resleeper, Reballast, Formation - Trax - CAT14 - 100yds | 2 | 1100 | 2 | 1200 | 100
Paul Eamonson | Plain Line | TRACK.PL | London North West | Babcock Rail | Saltley | 20/21 | 52 | 157046 | A38310 | 23100720 | Bibbes Yard to Wolverton | 15aa | 1100 | LEC1 | Weekend |  | 2021-03-27 22:00 | 2021-03-28 14:00 | 0 day(s) 16:00 Hrs | CORE: 1 of 3: Bibbes Yard to Wolverton - Associated Drainage - CAT15aa - 674yds | 51 | 1436 | 52 | 350 | 674 |  | CR
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 52 | 157680 | A56840 | 32405320 | Magazine Burn | 4 | 3100 | WHL | Weekend |  | 2021-03-28 | 2021-03-29 05:00 | 1 day(s) 05:00 Hrs | Magazine Burn | 31 | 1060 | 32 | 200 | 900
Barclay, Mr Craig Grant | Plain Line | TRACK.PL | Scotland | Babcock Rail | Glasgow | 20/21 | 52 | 157680 | A52640 | FD31200111 | Dalmeny Station Up 11/12 Falldown | 11 | 1100 | ECN2 | Weekend |  | 2021-03-28 00:01 | 2021-03-28 16:01 | 0 day(s) 16:00 Hrs | Dalmeny Station Up 11/12 Falldown | 9 | 936 | 9 | 1060 | 208
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T1090 | 41605312 | Harlow Mill Up | 11 | 1100 | BGK | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 23 | 1465 | 24 | 530 | 825
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T1100 | 41605312 | Harlow Mill Up | 2 | 1100 | BGK | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 23 | 1459 | 23 | 1465 | 6
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T1940 | 41605312 | Harlow Mill Up | 2 | 1100 | BGK | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 24 | 530 | 24 | 535 | 5
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T2020 | 41605312 | Harlow Mill Up | 1 | 1100 | BGK | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - One Rail Only Cat:01 | 24 | 535 | 24 | 536 | 1
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T2120 | 41501918 | Romford - Gidea Park Dn Electric | 2 | 2152 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 13 | 630 | 13 | 672 | 42
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T2130 | 41501918 | Romford - Gidea Park Dn Electric | 2 | 2152 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 13 | 1023 | 13 | 1035 | 12
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T2980 | 41501918 | Romford - Gidea Park Dn Electric | 14 | 2152 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 13 | 708 | 13 | 1023 | 315
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T3170 | 41500719 | Stratford Dn Electric | 11 | 2152 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 3 | 88 | 3 | 1100 | 1012
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T4210 | 41501119 | Forest Gate Dn Electric | 14 | 2152 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Formation, Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:14 | 4 | 1285 | 5 | 1064 | 1539
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T5160 | 41501119 | Forest Gate Dn Electric | 1 | 2152 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - One Rail Only Cat:01 | 4 | 1269 | 4 | 1273 | 4
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T5170 | 41501119 | Forest Gate Dn Electric | 2 | 2152 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 4 | 1273 | 4 | 1285 | 12
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T5180 | 41501119 | Forest Gate Dn Electric | 2 | 2152 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Rerail - Both Rails Cat:02 | 5 | 1064 | 5 | 1066 | 2
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T5280 | 41200019 | Derby Road Up Loop | 11 | 3100 | FEL | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 74 | 677 | 75 | 190 | 1273
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T6320 | 41540914 | Ilford Station Up Electric | 11 | 1152 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 7 | 440 | 7 | 1122 | 682
Cooper, Mr Michael Paul (Mick) | Plain Line | TRACK.PL | N/A | Colas | Ipswich | 21/22 | 50 | 159908 | G4T7360 | NR09102df1 | C Line Norwich - Check Curve | 11 | 3100 | LTN1 | Weekend |  | 2022-03-19 01:00 | 2022-03-19 17:00 | 0 day(s) 16:00 Hrs | CORE: Reballast, Resleeper, Rerail - Trax (all non steel sleeper types) Cat:11 | 123 | 1030 | 123 | 1320 | 290