## Sheet1
2024/2025 blockades over 7 days
Route | Dates | Duration | Work type | Location | Comments
Scotland | 2nd March to 22nd July 24 | 20 weeks | Track Lowering S&T Works & OLE Works 6.5k of double track 13km of earthworks/drainage Station work | East Kilbride Branch between c/o Busby Jn to East Kilbride | By the end of the blockade - all stations works should be completed, new double track and S&T comissioned.
Scotland | 2025-05-01 | 7 days | Connections for platform 4 & 5 126 points and crossover Plain-line 114B catch points Good Loop Open to passengers | Aberdeen Station (full station closure) | Part of Aberdeen to Central Belt Project Works.
Scotland | 2025-09-01 | 8 Days | New bay platform & X-Over New north loop New crossover @ lunan bay Headway imporvements New Montrose workstation in Dundee New montrose CIP in Dundee | Aberdeen Station (full station closure) | Part of Aberdeen to Central Belt Project Works.
Anglia | 23rd December to 1st January 2024 | 10 days | Structure renewal | East Ham/ Barking Station Jn to Upminster / Dagenham Dock | Structure renewal; Barking Station Parade / Kennedy Street
Anglia | 25th December to 1st January 2024 | 8 days | Capital Delivery Signalling: | Royston / Whittlesford Parkway to Ely Dock Jn/Dullingham | Capital Delivery: Cambridge South Signalling: Cambridge re-signalling
Anglia | 13th January to 11th February | 30 days | Track Renewals | Ilford to Manor Park (Up Avoiding) | Track PL: Manor Park Up Avoiding
Anglia | 10th February to 18th February | 9 days | Capital Delivery | Royston / Whittlesford Parkway to Cambridge | Capital Delivery: Cambridge South
Anglia | 1st March to 30th November 2024 | 275 days | ASPRO | Lea Jn to Temple Mills East Jn | ASPRO: Decking of Anthems Way over High Meads Loop
Anglia | 2nd March to 28th April 2024 | 57 Days | Track S&C | Stowmarket Down Refuge Siding | Track: Stowmarket S&C
Anglia | 24th August to 1st September 2024 | 9 days | Capital Delivery | Royston / Whittlesford Parkway to Cambridge | Capital Delivery: Cambridge South
Anglia | 25th December to 1st January 2024 | 8 days | Capital Delivery | Chelmsford to Witham | Capital Delivery: Beaulieu New Station
Anglia | 19th October to 27th October 2024 | 9 days | Signalling | Coldham Lane Jn to Chippenham Jn | Signalling: Cambridge re-signalling
East Coast | TBC | TBC | ECDP | Kings Cross to Peterborough | ECDP will have something approaching that duration. Dates TBC, Duration TBC, Work type ECDP, location Kings Cross to Peterborough
East Coast | TBC | TBC | Track Renewals | Various locations Peterborough to Doncaster | Any track work PBO to DON could if we go midweek vice weekend strategy. Dates TBC, Duration TBC, Work type Domestic renewals location Peterborough to Doncaster
North & East | TBC | TBC | Capital Delivery | Bradford and Shipley | Likely will need blockades at Bradford and Shipley. Dates TBC, Duration TBC, Work type
North & East | TBC | TBC | TRU | Hope Valley | Potentially TRU Hope Valley blockade ( currently in 2023 ) may move into 2024. Huddersfield 31 days in April Huddersfield 9 days in July Dates TBC, Duration TBC
NW&C | 2024-01-01 | 14 days |  | West Coast Relief Lines - Harlesden Geotech | West Coast Relief Lines – 14 Day blockade for Harlesden Geotech. Main Lines remain open
NW&C | Febuary 2024 | 9 days |  | HS2 Water Orton | Water Orton Corridor – 9 day blockade HS2 Water Orton Corridor works
NW&C | Easter | 15 days |  | Crewe Hub | 15 Day Crewe blockade for Crewe Hub
NW&C | 2025-07-01 | 9 days |  | Trent Valley | 9 Day Blockade Trent Valley for HS2 Handsacre
NW&C | July to August 2025 | 7 weeks | Slab tracking | Liverpool 5th Parkway | 7 Week blockade Liverpool Sth Parkway for Liverpool Central Slab Tracking
NW&C | August BH | 10 days |  | Water Orten Corridor | Water Orton Corridor – 10 day blockade HS2 Water Orton Corridor works
NW&C | July to August 2025 | 49 days | Crewe Hub Works | Crewe | 49 Day blockade Crewe – Crewe Hub works
Kent & Sussex | August BH 2024 | 9 days | S&C Renewal | Streatham Hill to Sydenham / Beckenham Jn / Norwood Jn | Limits to be confirmed
Kent & Sussex | 2024-12-01 | 10 days | Victoria Plase 5 commissioning | Victoria Eastern / Blackfriars Jn / Herne Hill foul / Nunhead Jn foul | Commissioning blockade - likely wheels free requirement. Limits to be confirmed
Kent & Sussex | 2024-12-01 | 10 days | Dartford Jn S&C | Dartford foul | Limits to be confirmed
Kent & Sussex | 2023-12-01 | 9/10 days | S&C Renewal | Voltaire Road | For xmas 2023 a block for 9/10days for Voltaire Road Jn S&C renewal. It will block Victoria Eastern to Herne Hill, Peckham Rye and Nunhead.
Wessex | TBC | 16 days | Track renewals | Wilton Jn - Yeovil Jn | End of 16 day Blockade Wilton Jn – Yeovil Jn for track renewals. Rest of access is in 2023 EAS.
Wessex | TBC | 15 days | Bridge Reconstruction | Weybridge - Basingstoke | 15 day Weybridge – Basingstoke for Victoria Arch Bridge reconstruction
Wessex | TBC | 16 days | Earthworks | Yeovil Pen Mill - Dorchester | 16 day Yeovil Pen Mill – Dorchester West for Earthworks
Wessex | TBC | 9 days | Stage 5 commissioning | Bracknell / Blackwater - Reading | 9 day Bracknell/Blackwater – Reading for Feltham Resignalling Stage 5 Commissioning
Western | Week 41 - 44 | 23 days | Domestic Renewal | Bristol TM - Western SM | 06 Jan 2024 to 28 Jan 2024. Metrowest and Bristol West Domestic Renewal
Western | Weeks 46-48 Half term | 9 days | Domestic Renewal | Cowley Bridge - Okehampton / Barnstaple | Within 10 Feb 2024 to 25 Feb 2024
Wales | June-July 2024 | 9 days |  | Severn Tunnel | Severn Tunnel Saturday 29 June 2024 to Sunday 07 July 2024
Wales | July-August | 21 days |  | Severn Estuary Line | Severn estuary line Saturday 20 July to Friday 09 August 2024
Wales | 10th March 2023 - 20th March 2023 | 9 days | Track Renewals | Wexham to Bidston
Wales | 5th May 2023 - 22nd May 2023 | 16 days | Track Renewals & Structures Renewals | Welshpool to Machnlleth
Wales | 26th May 2023 - 5th June 2023 | 9 days | Track Renewals | Aberthaw to Bridgend
Wales | 9th June 2023 - 19th June 2023 | 10 days | Track Renewals | Patchway to Severn Tunnel Jn
Wales | 23rd July 2023 - 5th August 2023 | 12 days | Gauge Clearance Track Work | Newport to Gaer Jn ( just west of Newport )
Wales | 6th August - 21st August | 15 days | Gauge Clearance Track Work | Newport to Gaer Jn ( just west of Newport )
Wales | 2nd September 2023 - 16th September 2023 | 14 days | Track Renewals & Drainage Work | Moreton on Lugg ( about 5 miles north of Hereford ) to Leominster
Wales | 31st July 2023 - 5th August 2023 | 5 days | Embankment Stabilisation Work | Gloucester - Lydney
Wales | 6th August 2023 - 12th August 2023 | 6 days | Embankment Stabilisation Work | Gloucester - Lydney
Wales | 14th August 2023 - 18th August 2023 | 5 days | Embankment Stabilisation Work | Gloucester - Lydney
Wales | 20th July 2024 - 10th August 2024 | 21 days | Embankment Stabilisation Work | Gloucester - Lydney