## Slide 1
Project Construction Progress
Hither Green AfA

## Slide 2
Hither Green Access for All

## Slide 3
PL 1
PL 2&3
PL 4
PL 5
PL 6
Main Site Compound
(under construction)
New AfA Structure
New Fernbrook Rd Station Entrance
New Fernbrook Rd Station Entrance
Existing Subway Entrance
Existing Subway Entrance
New footbridge spanning over all 6 lines totalling 95m in length
4 new lifts & staircases servicing all platforms
New entrance at Springbank Rd & Fernbrook Rd
New link passageway connecting platforms 4&5
Widening of PL1 and PL6
350m of Gikkon sheet piled retaining wall on embankment.
Civil works (embankment retention, RC works, drainage)
New UKPN 650A Substation
M&E works (lighting, power)
SISS works (CCTV, PA, CIS, TVM, Oyster Readers)
Landscaping and fencing
Nature Reserve reinstatement and replanting
Hither Green AfA - Scope

## Slide 4
November 2024_Site Progress
Traffic Management lifted and footway/ parking bays back open for public use
Traffic Management Set up on Springbank Road
Vegetation clearance complete at Springbank Road embankment
Vegetation Clearance within the nature reserve
Vegetation Clearance within the nature reserve
Vegetation Clearance within the nature reserve

## Slide 5
December 2024_Site Progress
Constructing the access ramp in the nature reserve
Hoarding & debris netting erected on Platform 1
Cables raised in the depot
Constructing the access ramp in the nature reserve
Fernbrook Road Vegetation Clearance
Fernbrook Road Vegetation Clearance
Constructing the access ramp in the nature reserve
Site secured during the Christmas break

## Slide 6
January 2025_Site Progress
Posters installed around the station
Access ramp and site compound construction
S&T Cable slewed into split ducting
Community engagement session
Installing CBGM in the site compound
Shuttering installed for the concrete footings for the cabins
Installing scaffolding to the subway
Posters installed around the station
Posters installed around the station

## Slide 7
January 2025_Site Progress
Installing HV containment to the station wall above the subway
Asphalt installed in the site compound
Concrete footing for the site cabins
Starting the embankment regrade at Springbank Road
Installing high level containment on the station wall above the subway
Embankment regrade at Springbank Road
Embankment regrade at Springbank Road
2No. sheds now removed
Asbestos sheeting removal complete

## Slide 8
February 2025_Site Progress
Embankment regrade and working platform construction at Springbank Road
Plate testing on the working platform
Scaffold striked over the subway
Embankment regrade and working platform construction at Springbank Road
Site Cabins in Compound Area
UXO Survey locations marked out
Springbank Road UXO Surveys
Fernbrook Road HV diversion works
Staircase to platform 4/5 installed
CIS base set out ready for Week 49 possession
Springbank Road enabling – HV feeder diversion

## Slide 9
February 2025_Site Progress
Crawler Crane mobilised
Sheet Piles delivered
Springbank Road Piling platform construction – Bogmatts installed

## Slide 10
March 2025_Site Progress
Springbank Rd piling work
Press play

## Slide 11
March 2025_Site Progress
Springbank Rd: Installing sheet piles
Springbank Rd: Installing sheet piles
Vibration monitor installed
Platform 2/3 help point base

## Slide 12
April 2025_Site Progress
Springbank Road- Giken Piling
Springbank Road- Giken Piling
Fernbrook Road- Embankment Regrade
Platform 6- Billboards Removed & Platform Hoarding Installed
Springbank Road- Giken Piling
Fernbrook Road- Embankment Regrade

## Slide 13
April 2025_Site Progress
Platform 2/3 hoarding
DOO disconnected and reconnected following cable diversion
Platform 2/3- Benches relocated

## Slide 14
May 2025_Site Progress
Springbank Road- Giken Piling
Platform 2/3 Trial holes
Fernbrook Road – Piling Platform Construction
Fernbrook Road – Piling Platform Construction
I visited Hither Green Station, to see the £28 million work @NetworkRailSE
are doing to improve the station and make it step free. I appreciate the work they have conducted to include residents in their plans and mitigate their concerns about noise and to disruption. MP, J. Darby

## Slide 15
May 2025_Site Progress
Springbank Road – HV & S&T cable protection works
Springbank Road- Giken Piling
Springbank Road – Scaffolding works
Platform 1 – TVM Installed
Tree logs donated to Forster Park Primary School delivered to schools
Fernbrook Road- Relocated bus stops

## Slide 16
June 2025_Hither Green Site Progress
Springbang Rd – Piling completed and crane de-moblisation underway
Platform 2&3 – Lift and stair SFA piling behind platform hoarding
Fernbrook Rd – Piling commenced
Platform 4&5 – Lift and stair SFA piling
Steel fabrication underway

## Slide 17
June 2025_Hither Green Site Progress Rail Minister Visit - Wed 18th Jun

## Slide 18
June 2025_Hither Green Site Progress Rail Minister Visit - Wed 18th Jun

## Slide 19
July 2025_Hither Green Site Progress
Springbank Rd / Platform 1 - Lift and stair foundation works ongoing
Platform 2&3 – Lift and stair foundation works ongoing
PL 2&3
PL1

## Slide 20
July 2025_Hither Green Site Progress
Fernbrook Rd – Piling underway through to Sep 2025
Platform 4&5 - Lift and stair foundation works ongoing
PL 4&5
PL6

## Slide 21
July 2025_Hither Green Site Progress – Steel Lift Fabrication underway
Lift 1 fabrication
All steel procurement has been completed and shop fabrication underway.
Site install shall be in a series of possessions from Wk 27 (28th Sep 25) to Wk 05 (2nd May 26)