## Reference (hidden)
Sheet Name: | Reference
Description: | Example List of Valid Entries
| Status | Business Lead
| Scope Incomplete | Eastern: Anglia
| Scope Complete but not GBR Adopted | Eastern: East Coast
| Scope Complete and Adopted | Eastern: East Midlands
| Project Underway | Eastern: North & East Route
| Project Completed | NW&C: Central
| Project On Hold | NW&C: North West
| Project Cancelled | NW&C: West Coast South
Scotland
Southern: Kent
Southern: NR HS
Southern: Sussex
Southern: Wessex
W&W: Wales & Borders
W&W: Great Western

## Planning Schedule Example
Sheet Name: | Planning Schedule Example
Description: | Illustration of the structure of the Planning Schedule table
|  |  | Please note that the examples are illustrative only and do not accurately reflect the example capacity and commitments in real life. No significance should be placed on any of this illustrative data, for example dates, quantum’s etc. They are not intended to indicate future decisions or capacity allocation. |  |  |  | • Scope incomplete • Scope mature and project proposed • Scope determined • Project underway • Project completed
|  |  | Drop Down Menu | Drop Down Menu |  | Drop Down Menu |  |  | Drop Down Menu | Drop Down Menu |  |  |  | Drop Down Menu | [6 empty] | Drop Down Menu | Drop Down Menu
|  |  | Ability to select multiple entries |  |  | Ability to select multiple entries |  |  | Ability to select multiple entries | Ability to select multiple entries | [10 empty] | Ability to select multiple entries | Ability to select multiple entries
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
| Unique Project ID | Project Title | Project Status | Critical Outputs | Contingent Outputs | Expected Strategic Business Outcomes | Expected Strategic Business Outcomes (Detail) | Link to any Relevant Decision Documents | Geographic Scope | Adjacent Lines of Route impacted | Project Maturity Milestone Date | Expected Timetable Start Date | Expected Timetable End Date | Lead Business Unit | Project Reference Group | Stakeholders Consulted | Infrastructure Enablers | Rolling Stock Enablers | Timetable Enablers (Associated Service Changes) | Operational Enablers | Interfacing Project IDs | Confidential Information | Date last updated | Last update detail | Notes
| 0001 | Oxford Cowley Passenger Service Introduction Dec 29 | Scope incomplete | 2tph London Marylebone to Oxford Cowley. Expected to be the extension of 2 existing services from London Marylebone to Oxford through to Oxford Cowley. All other current passenger and freight services to be retained within the geographic footprint. | Capacity released at Oxford station in bay platforms, to accommodate further 2tph EWR services from Bedford/Cambridge | New connectivity Stimulate Economic Growth Environmental Reducing Road Congestion Increased capacity at Oxford | - New Connectivity: Delivering two new stations in Littlemore and Cowley, both historically deprived areas in Oxford, allowing for people to reach the city centre within 10minutes '- Stimulate Economic Growth: making it more accessible for people in Littlemore and Cowley to access jobs in Oxford and surrounding areas, as well as London '- Environmental: expected to reduce reliance on car journeys with more people using rail, noting that bus journeys are not desirable due to journey length and road infrastructure '- Reducing Road Congestion: expected to reduce road congestion in Cowley and Littlemore by providing an option for train journeys to Oxford with a quicker journey time '- Increased Capacity at Oxford: critical objective of Cowley is to release capacity in the bay platforms in Oxford for additional 2tph EWR services, without significant infrastructure spend |  | GW200, MD140, MD736 MD701 | MD736, GW103 East West Rail (LORs TBC) | February 2027 | 2029-12-01 | 2031-12-01 | Great Western Business Unit | Network Rail Chiltern EWR | NR W&W NR NW&C Chiltern GWR CrossCountry EWR Regional Freight DfT DfTO Rail Minister | Cowley Branch: '- Line speed upgrade to 50mph '- Upgraded signalling '- Two new stations, one at Cowley, one at Littlemore Thames Valley: '- Extension of Up Oxford Relief to Radley Junction '- Upgrade of Kennington Junction to 50mph '- Delivery of Oxford platform 5 Signalling commissioning System data change by Alstom | Cascade of rolling stock | None | Traincrew recruitment & training | 0005 & 0008 | None | 2026-08-19 | Initial population
| 0002 | MetroWest Phase 1 Portishead Line Passengerisation Dec 28 | Scope mature and project proposed | 1tph Portishead to Henbury. All other current passenger and freight services to be retained within the geographic footprint. |  | New connectivity Stimulate Economic Growth Environmental | - New Connectivity: Delivering two new stations at Pill and Porishead, in the suburban areas of Bristol, opening up connectivity towards the city centre and beyond '- Stimulate Economic Growth: making it more accessible for those in Portishead or Pill to access major employment areas such as Bristol, the Midlands or London '- Environmental: reducing the amount of car journeys made from Portishead or Pill to the city centre, helping shift the modal balance |  | GW548, GW528, GW530, GW105, GW450 | None | Decemeber 2026 | 2028-12-01 | 2033-12-01 | Great Western Business Unit | Network Rail West of England Combined Authority GWR | NR W&W GWR WECA DfT DfTO | Portishead Branch: '- Two new stations, one at Pill and one at Portishead '- Signalling and track upgrade - Double track around Pill to support freight movement Signalling commissioning | Cascade of rolling stock | None | Traincrew recruitment & training signaller training | 0003 | None | 2026-08-19 | Initial population | Note, Henbury is funded separately / Improves capacity slightly at Bristol Temple Meads as the service will connect to the Henbury service and operate as a through service, thus reducing platforming capacity with less trains terminating
| 0003 | MetroWest Phase 2 Henbury Line Passengerisation Dec 28 | Scope mature and project proposed | 1tph Henbury to Portishead. All other current passenger and freight services to be retained within the geographic footprint. |  | New connectivity Stimulate Economic Growth Environmental | - New Connectivity: Delivering two new stations, one at North Filton (Brabazon) and one at Henbury, in the suburban areas of Bristol, opening up connectivity to the city centre and beyond. Additionally, Brabazon is identified as one of the Government's new town schemes where increased housing growth is planned. Brabazon will also host a 20,000 arena and therefore provides connectivity during event times '- Stimulate Economic Growth: making it more accessible for those in Henbury and North Filton to access major employment areas such as Bristol and the wider country. Additionally, Brabazon is expected to attract a lot of growth so makes it more accessible for those from the Bristol city centre (as well as neighbouring counties) to Brabazon '- Environmental: helping to shift modal share with rail opportunites to the city centre, reducing reliance on car travel, and making it an attractive option in terms of journey times |  | Henbury Line, GW450, GW105 | None | Decemeber 2026 | 2028-12-01 | 2033-12-01 | Great Western Business Unit | Network Rail West of England Combined Authority GWR | NR W&W GWR WECA DfT DfTO | Henbury Line: '- Two new stations, one at North Filton (Brabazon) and one at Henbury '- Signalling changes '- Filton Chord line speed increase Signalling commissioning | Cascade of rolling stock | None | Traincrew recruitment & training, signaller training | 0002 | None | 2026-08-19 | Initial population | Project maturity is very low. Whilst Government funding has been agreed for Burns delivery, but delivery model with Welsh government nor detailed planning has been agreed or started (note, Portishead section is funded separately as part of phase 1). Improves capacity slightly at Bristol Temple Meads as the service will connect to the Portishead service and operate as a through service, thus reducing platforming capacity with less trains terminating
| 0004 | South Wales Mainline Dec 29 | Scope incomplete | An additional 2tph to 4tph services between Cardiff Central and Bristol/Cheltenham. Additional calls at the new Burns stations. All other current passenger and freight services to be retained within the geographic footprint. | None | New connectivity Stimulate Economic Growth Environmental | - New Connectivity: Delivery of 5 new stations on the South Wales Main Line providing new connectivity to communities in South Wales to the capital of Wales and elsewhere in the neighbouring areas '- Stimulate Economic Growth: provides access to major employment areas such as Cardiff and Bristol for those in communities that currently have no rail access and are reliant on car journeys. The production process itself of building 5 new stations will create major employment '- Environmental: a key target for Welsh Government is to provide a high quality public transport system for those across Wales, to encourage the modal shift from cars to public transport by making it readily accessible |  | GW900 | GW401, GW450, GW105, GW530, GW528, GW700 | December 2026 | 2029-12-01 | 2033-12-01 | Wales & Borders GBR | Network Rail Welsh Government Transport for Wales DfT | NR W&W TfW Operator Welsh Government DfT DfTO | Full scope TBC however, as a minimum: '- 5 new stations in South Wales '- South Wales Relief Line Upgrade '- Platform 3 intervention at Cardiff Central '- Extension of platform 4 at Newport '- Additional freight regulation loops between Newport and Severn Tunnel (location TBC) Signalling Commissioning of SWRL | New rolling stock will be sourced | None | Many, all of which TBC but as a minimum: Traincrew Recruitment & Training Signaller Training |  | None | 2026-08-19 | Initial population
| 0005 | Oxford to Stewartby Early to Mid-2030’s | Scope incomplete | An additional 2tph Oxford to Stewartby 2tph Bletchley to Stewartby All other current passenger and freight services to be retained within the geographic footprint. | None | New connectivity Stimulate Economic Growth Environmental | - New Connectivity: Construction of a new station in Stewartby that is closely aligned to the footprint of Universal Studies will provide connectivity for customers travelling to and from the theme park from the west (Oxford), WCML (via change at Bletchley) and the neighbouring areas of Bedfordshire. Stewartby will be relocated from its' current location, closer to the theme park '- Stimulate Economic Growth: will allow for more people to travel to the new theme park, open up job opportunities and increase the labour pool for those working at the new theme park '- Environmental: providing more rail options to the new theme park is envisaged to encourage modal change from travelling by road and more by rail |  | GW200, MD140, MD701 | MD736, GW103 East West Rail (LORs TBC) | Decemeber 2029 | 2032-12-01 | 2035-12-01 | West Coast South | Network Rail UK Government DfT DfTO EWR | NR NW&C NR Western NR NW&C DfT DfTO | Marston Vale Line: '- Closure of some current stations on the line '- Upgraded signalling '- Upgraded track layout east of Bletchley '- Relocated and upgraded Stewartby station with turnback facilities '- Additional freight loops between Oxford and Stewartby Signalling commissioning | Mix of rolling stock cascade and new rolling stock being sourced | None | Traincrew recruiemtn & training Instruction to a train operator to operate the Oxford to Stewartby service Signaller training |  | Some plans are not being publicly shared at this stage (i.e. specific dates) | 2026-08-19 | Initial population
| 0006 | Elizabeth Line Central Operating Section May 2027 | Project underway | Increase to 28tph operating in the Core Operating Section (COS) of the Elizabeth Line (an additional 4TPH). All other current passenger and freight services to be retained within the geographic footprint. | None | Demand response Stimulate Economic Growth | - Demand Response: Elizabeth Line passenger numbers have been increasing significantly year by year since Entry into Service. The COS was designed to accommodate 28tph and above, up until now it does not operate this level of service. TfL have purchased new rolling stock with DfT support, new services are being added in the COS to support the high demand of the line '- Stimulate Economic Growth: by providing additional trains and moving more people across London, this will support improving the quality of labour pools for major companies in and around London |  | GW103, EA1010, EA1011, EA1160 Central Operating Section | TfL Infrastructure | August 2026 | 2027-05-01 | 2028-05-01 | Great Western Business Unit | Network Rail TfL DfT GTS | NR Western NR Anglia GTS ORR TfL | None | Additional 10 new units ordered by TfL to be fully available by May 27 | None | London Paddington Crossrail: New train clearing process to be introduced to allow GTS to achieve a 1 minute dwell from passenger to ECS service New TIPLOC to be added west of Paddington station to allow services to clear the platform earlier | 0009 | None | 2026-08-19 | Initial population
| 0007 | Wessex May 2028 | Scope incomplete | Full recast of Wessex and the SWR timetable. All other current passenger and freight services to be retained within the geographic footprint. | None | Journey Time Improvements Stimulate Economic Growth Environmental | - Journey Time Improvements: The full recast of the timetable is expected to enable JTI for certain sections of the Wessex Business Unit '- Stimulate Economic Growth: Through additional services and targetted uplifts across certain corridors, this is expected to increase railway capacity allow more opportunities for people to move freely to access bigger employment hubs around the south, and into London '- Environmental: additional services and journey time improvements are expected to support the shift in modal change from road to rail |  | TBC | TBC | October 2026 | 2028-12-01 | 2033-12-01 | South West Railways Business Unit | Network Rail SWR DfTO DfT | NR Wessex NR Western DfTO DfT SWR | None | New rolling stock already sourced as well as cascade of existing stock | None | Updated Timetable Planning Rules and Sectional Running Times Traincrew training |  | None | 2026-08-19 | Initial population | Note that we have not been provided a copy of the exact TT changes proposed.
| 0008 | Mid to late 2030s Oxford to Cambridge May 2028 | Scope incomplete | Enabling full scope of EWR: 2tph Milton Keynes to Oxford (KO1) 2tph Oxford to Cambridge 1tph Stewartby to Bletchley 1tph Stewartby to Cambridge. All other current passenger and freight services to be retained within the geographic footprint. | Full route open for additional or diverted freight traffic | New connectivitiy Stimulate Economic Growth Environmental | - New Connectivity: Brand new railway open between Oxford and Cambridge, including a mix of existing national infrastructure with new bespoke infrastructure for EWR. This will provide connectivity between two major cities, as well as many locations in between. This also includes new stations at Stewartby, Tempsford '- Stimulate Economic Growth: Through both increased leisure and commuter travel. Opening up increased access to leisure markets east to west, as well as increasing options for employment. Additionally, the project itself will create additional jobs for construction '- Environmental: Expected to reduce reliance on car travel with new opportunities opened that do not currently exist. Greater modal share shift to rail |  | GW200, MD140, MD736, MD701, EA1161, EA1230, EA1530 | GW101, LN101, EA1160, MD101 | TBC | 2037-12-01 | 2042-12-01 | West Cost South Business Unit | Network Rail EWR DfT DfTO | NR Western NR Central NR Anglia NR East Midlands NR East Coast DfT DfTO Chiltern GWR CrossCountry GTR GA | Full infrastructure scope between Oxford and Cambridge, including new stations across the Marston Vale Line and at Tempsford Signalling and full route commissioning | Mix between rolling stock cascade and new rolling stock | Potential GWR Bristol to Oxford service to be extended onwards towards the EWR route to subsume one of the TPH specified | Traincrew Recruitment & Training Operater allocation Signaller recruitment & training | 0005 | Some plans are not being publicly shared at this stage (i.e. specific dates) | 2026-08-19 | Initial population
| 0009 | Shenfield to Heathrow Airport terminal 5 | Scope determined | Additional 2tph to Heathrow T5 all day SX, SO & Su. All other current passenger and freight services to be retained within the geographic footprint. | Additional 2tph to Heathrow T5 SX peaks and SO all day only | New connectivity Stimulate Economic Growth | - New connectivity: Additional service groups connecting Shenfield to Heathrow T5 to meet passenger demand and improve performance due to expectation that passenger overcrowding project to increase '- Stimulate Economic Growth: More opportunities for passengers to get to Heathrow conveniently for onward connections outside of the country |  | GW103, GW180 | CCOS EA1010, EA1011, EA1160 | Oct '26 | May '28 | n/a | Great Western Business Unit | Network Rail TfL DfT GTS | Network Rail TfL DfT GTS | HAL infrastructure readiness | Additional 10 class 345 funded by DfT |  | Driver and staff training | 0006 | None | 2026-08-19 | Initial population
| 0010 | Manchester to York December 2035 | Scope incomplete | Manchester Airport – Newcastle – 17 additional services for Weekdays and Saturdays with 14 additional services on Sundays Newcastle – Manchester Airport - 17 additional services for Weekdays and Saturdays with 14 additional services on Sundays Hull – Manchester Piccadilly - 16 additional services for Weekdays and Saturdays with 14 additional services on Sundays Manchester Piccadilly – Hull - 16 additional services for Weekdays and Saturdays with 14 additional services on Sundays Manchester Piccadilly – Huddersfield - 18 additional services for Weekdays and Saturdays with 15 additional services on Sundays Huddersfield – Manchester Piccadilly 18 additional services for Weekdays and Saturdays with 15 additional services on Sundays Leeds – Huddersfield - 18 additional services for Weekdays and Saturdays with 15 additional services on Sundays Huddersfield – Leeds - 18 additional services for Weekdays and Saturdays with 15 additional services on Sundays | TBC | New connectivitiy Journey Time Improvement Stimulate Economic Growth Environmental | - New Connectivity: New stations across the Transpennine Route will provide new connectivity to major locations such as Manchester, Liverpool, Leeds, York and Newcastle '- Journey Time Improvements: Expected across the route, particularly between Leeds and Manchester. Upgrades include electrification of the Transpennine Route enabling quicker running times '- Stimulate Economic Growth: More rail opportunities will be offered, along with quicker journey times and new stations, more people will have access to other areas of the north for job opportunities or leisure travel '- Environmental: Electrification of the route will allow for cleaner/greener trains to operate, reducing emissions. Additionally, the JTI and increase journey opportunities is expected to significantly support the modal shift from road to rail |  | NW5007, NW6001, NW6005, NW7001, NW7021, NW5021, LN860, LN862, LN872, LN600, LN618, LN854, LN902, (Transpennine Route in full) | LNE and NW&C | December 2030 | 2035-12-01 | 2040-12-01 | North East & North West in Partnership | Network Rail incl. TRU Board Transport for North Transport for Greater Manchester DfT DfTO | NR North East NR North West TfN TfGN DfT Northern TPE CrossCountry WMR | Electrification of full Transpennine Route (with no signalling upgrades) Commissioning of TRU route New or upgraded stations: Haxby Manches Manchester Oxford Road Huddersfield Manchester Piccadilly Platforms Manchester Airport Cross Gates White Rose Others to be developed and confirmed | Cascade of existing and new rolling stock | TBC | Train crew recruitment & training Signaller training Full update of TPRs including TIPLOCs and SRTs | 00011 | Initial timetable specification | 2026-08-19 | Initial population
| 0011 | Manchester to York December 2030 | Scope incomplete | Service Enhancement between Huddersfield, Leeds and York TPE 4 fast, 1 semi-fast; NTL 2 Huddersfield - Leeds, 1 Leeds -York (EMUs). All other current passenger and freight services to be retained within the geographic footprint. |  | More services Quicker journeys Reliability Improved stations Environmental benefits Freight benefits | - New Connectivity: New stations across the Transpennine Route will provide new connectivity to major locations such as Manchester, Liverpool, Leeds, York and Newcastle '- Journey Time Improvements: Expected across the route, particularly between Leeds and Manchester. Upgrades include electrification of the Transpennine Route enabling quicker running times '- Stimulate Economic Growth: More rail opportunities will be offered, along with quicker journey times and new stations, more people will have access to other areas of the north for job opportunities or leisure travel '- Environmental: Electrification of the route will allow for cleaner/greener trains to operate, reducing emissions. Additionally, the JTI and increase journey opportunities is expected to significantly support the modal shift from road to rail |  | NW5007, NW6001, NW6005, NW7001, NW7021, NW5021, LN860, LN862, LN872, LN600, LN618, LN854, LN902, (Transpennine Route in full) | LNE and NW&C | 2027-10-01 | 2030 - 2032 (new rolling stock to be introduced) |  | TRU | NR TRU Northern Intregration Board DfT | NR TRU Northern Intregration Board DfT | CTT3 CS2 | New rolling stock to be introduced | TBC | Train crew recruitment & training Signaller training Full update of TPRs including TIPLOCs and SRTs | 00010 | Initial timetable specification | 2026-08-19 | Initial population
| 0012 | London to Birmingham December 2036 | Scope mature and project proposed | 2tph Birmingham Curzton Street to Old Oak Common on new HS2 infrastructure. All other current passenger and freight services to be retained within the geographic footprint. | TBC | Journey Time Improvement Stimulate Economic Growth Environmental | - Journey Time Improvement: Expected quicker journey times between Birmingham and London '- Stimulate Economic Growth: Through additional services and quicker journey times, expected to support economic growth by allowing easier and quicker travel between two big cities '- Environmental: Expected to support modal shift from car to rail by offering attractive journey times |  | Full HS2 Route GW103, MD101, MD701 | NW&C Western | January 2027 | 2036-05-01 | 2040-05-01 | West Coast South (NW&C) | Network Rail HS2 DfT DfTO TfL | Network Rail HS2 DfT DfTO TfL | Full infrastructure scope between Birmingham and Old Oak Common. Commissioning of route and signalling. | New rolling stock to be sourced | None | Train crew recruitment & training Signaller recruitment training Operator allocation |  | Currently going through a Programme reset, details of which are not freely shared | 2026-08-19 | Initial population

## Key
Sheet Name: | Key
Description: | Overview of formatting used in workbook
Heading 1
Heading 2
Heading 3
Editable Input 1
Editable Input 2
Non-editable input 1
Non-editable input 2
Macro-pasted value
Formula 1
Formula 2
Warning Text
Description
Instruction
FALSE
TRUE