## Reference (hidden)
Sheet Name: | Reference
Description: | Example List of Valid Entries
| Project Status | Business Lead
| Scope Incomplete | Eastern: Anglia
| Scope Complete but not GBR Adopted | Eastern: East Coast
| Scope Complete and Adopted | Eastern: East Midlands
| Project Underway | Eastern: North & East Route
| Project Completed | NW&C: Central
| Project On Hold | NW&C: North West
| Project Cancelled | NW&C: West Coast South
Scotland
Southern: Kent
Southern: NR HS
Southern: Sussex
Southern: Wessex
W&W: Wales & Borders
W&W: Great Western

## Data Specification
Sheet Name: | Data Specification
Description: | Detail of data records to be included in a database that can be used to generate a Planning Schedule report; draft for review
| Header | Description | Source | Response Options | Changes since Version 3
1 | Unique Project ID | Unique reference for the project | n/a | Automatically generated numeric field
2 | Project Title | Short title for the timetable change project | NR to populate | Free-form short-hand description of the timetable change project
3 | Project Status | Current status of the timetable change project in the decision-making cycle | NR to populate | Drop-down list of valid entries, proposed as: • Scope incomplete • Scope mature and project proposed • Scope determined • Project underway • Project completed
4 | Critical Outputs | Summary of service specification based on detail held within the ICP (based on defined "aspirational" paths rather than "agreed" paths) | NR to populate | Drop-down list of valid Unique Reference Numbers from ICP. Multiple selections allowed.
5 | Contingent Outputs | Additional potential timetabling benefits which may emerge from project | NR to populate | Free-form text
6 | Expected Strategic Business Outcomes | Expected strategic outcomes from the timetable project | NR to populate | Drop-down list of defined entries ('Strategic KPIs') e.g. Connectivity, Environmental, Ease Road Congestion, Open up Opportunities, ., etc.) Multiple selections allowed.
7 | Expected Strategic Business Outcomes (Detail) | As above, but for adding more detail as required | NR to populate | Free-form text
8 | Link to any Relevant Decision Documents | Link to issued decision letter for this change | NR to populate | Document reference link
9 | Geographic Scope | Unique ID of infrastructure which is directly affected by the timetable change, based on Line of Route (LOR); can be used for geographical filtering of reports | NR to populate | Drop-down list of valid Line of Route' codes More than one LOR may apply
10 | Adjacent Lines of Route impacted | Description of adjacent lines of route which may be indirectly affected by the timetable change, including those on other IM infrastructure | NR to populate | Drop-down list of valid Line of Route' codes plus other IMs More than one LOR may apply
11 | Project Maturity Milestone Date | Date by which all information required for this project is to be populated in the Planning Schedule. This is expected to be 2 to 3 years in advance of the proposed TT change date. | NR to populate | Calendar Date (dd/mm/yyyy)
12 | Expected Timetable Start Date | Date when timetable change is expected to start | NR to populate | Calendar Date (dd/mm/yyyy)
13 | Expected Timetable End Date | Date when timetable change is expected to end (for temporary changes only) | NR to populate | Calendar Date (dd/mm/yyyy) or "Ongoing" (if not a temporary timetable change)
14 | Lead Business Unit | Definition of the lead Business Unit for the timetable change | NR to populate | Drop down list of valid entries
15 | Project Reference Group | List of participants in Project Reference Group | NR to populate | Form to be determined; individuals, roles, organisations
16 | Stakeholders Consulted | Details of stakeholders who are on the consultation list | NR to populate | Drop down list of valid entries; all organisations (comprising TOCs, FOCs, NR Routes, OA, other). Multiple selections allowed.
17 | Infrastructure Enablers | Details of any infrastructure changes that need to be in place for the timetable change to apply | IM to advise | Either a single free-form field or two fields- one with a selected generic category and one to allow more free-form definition
18 | Rolling Stock Enablers | Details of any rolling stock changes that need to be in place for the timetable change to apply | Operator / NR to advise | Either a single free-form field or two fields - one with a selected generic category (e.g. new stock, cascaded stock, etc.)and one to allow more free-form definition
19 | Timetable Enablers (Associated Service Changes) | Description of any associated service changes that are required to enable this timetable change to be implemented | NR to populate | Free-form text
20 | Operational Enablers | Details of any operational updates that need to be in place for the timetable change to apply | Operator / NR to advise | Either a single free-form field or two fields - one with a selected generic category (e.g. driver recruitment, signaler recruitment, etc.) and one to allow more free-form definition
21 | Interfacing Project IDs | Link to other timetable changes within the Planning Schedule which interface with this timetable change | NR to populate | Drop-down of all valid Unique Project IDs from Project Schedule Multiple selections allowed.
22 | Confidential Information | Definition of any information which should be treated as confidential | All parties to advise | Drop down list of all fields which should be treated as confident for this entry. Multiple selections allowed.
23 | Date last updated | Date that the row / column / entry was last updated | NR to populate | Calendar Date (dd/mm/yyyy)
24 | Last update detail | Short summary of what was changed | NR to populate | Free form description of change
25 | Notes | Any additional useful information | NR to populate | Free-form for any additional detail not explicitly captured elsewhere
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42